## OptimizedSchedule
wo_id | description | asset_tag | asset_class | area | task_type | priority | mandatory | selected | decision | estimated_cost_usd | mech_hours | elec_hours | inst_hours | civil_hours | total_craft_hours | duration_days | failure_prob | rul_days | consequence_score | likelihood_tier | consequence_tier | risk_score | risk_level | deferred_cost_usd | net_value_usd | predecessor_wo_id
WO-00001 | Overhaul – Electrical Equipment ELEC-0024 | ELEC-0024 | Elec | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 432608.5 | 239.5 | 22.7 | 8.5 | 6.5 | 277.2 | 35 | 0.65923 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5933.05 | -426675.45
WO-00002 | Replacement – Control Valve VLV-0026 | VLV-0026 | Vlv | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 113098 | 40.6 | 11.4 | 20 | 3.3 | 75.3 | 9 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3431.19 | -109666.81
WO-00003 | Inspection – Piping/Pipeline Segment PPL-0012 | PPL-0012 | Ppl | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 5185.61 | 9.5 | 1.6 | 4.4 | 0.4 | 15.9 | 2 | 0.099696 | 3614.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4803.35 | -382.26
WO-00004 | Cleaning – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 15844.97 | 5.4 | 0.4 | 1.1 | 2.5 | 9.4 | 1 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 64711.24
WO-00005 | Repair – Instrument/Analyser INST-0114 | INST-0114 | Inst | Offsites | Repair | Low | FALSE | FALSE | DEFER | 73788.26 | 17.4 | 28.4 | 3.2 | 5.3 | 54.3 | 7 | 0.92825 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.68 | -72451.58
WO-00006 | Inspection – Instrument/Analyser INST-0142 | INST-0142 | Inst | Offsites | Inspection | High | FALSE | TRUE | INCLUDE | 734.91 | 2.2 | 1 | 4.2 | 0.1 | 7.5 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 705.09
WO-00007 | Cleaning – Instrument/Analyser INST-0121 | INST-0121 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 6623.09 | 21.5 | 1.9 | 1.5 | 9 | 33.9 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5183.09
WO-00008 | Repair – Instrument/Analyser INST-0082 | INST-0082 | Inst | Tank-Farm | Repair | Medium | FALSE | FALSE | DEFER | 16266.45 | 14.3 | 21.1 | 2.9 | 9 | 47.3 | 6 | 0.84213 | 730 | 2 | 5 | 2 | 10 | HIGH | 1212.67 | -15053.78
WO-00009 | Testing – Instrument/Analyser INST-0007 | INST-0007 | Inst | Unit-100 | Testing | Medium | FALSE | FALSE | DEFER | 5051.36 | 10.8 | 18.8 | 8.9 | 1.1 | 39.6 | 5 | 0.96291 | 730 | 2 | 5 | 2 | 10 | HIGH | 1386.59 | -3664.77
WO-00010 | Testing – Instrument/Analyser INST-0111 | INST-0111 | Inst | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 11298.2 | 4.1 | 13.5 | 15.8 | 0.3 | 33.7 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -9858.2
WO-00011 | Replacement – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Replacement | Medium | FALSE | TRUE | INCLUDE | 18665.17 | 34.6 | 5 | 15.8 | 2.5 | 57.9 | 7 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | 22780.37
WO-00012 | Inspection – Control Valve VLV-0110 | VLV-0110 | Vlv | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 7232.51 | 2.2 | 1 | 2.3 | 0.2 | 5.7 | 1 | 0.37878 | 1096.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2032.63 | -5199.88
WO-00013 | Repair – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 73391.62 | 35.9 | 8 | 15 | 6.2 | 65.1 | 8 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -72006.06
WO-00014 | Calibration – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1653.01 | 1.3 | 4.9 | 11 | 0.2 | 17.4 | 2 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 31225.23
WO-00015 | Inspection – Control Valve VLV-0089 | VLV-0089 | Vlv | Unit-200 | Inspection | Medium | FALSE | FALSE | DEFER | 6359.44 | 8.4 | 1.5 | 1.1 | 0.3 | 11.3 | 1 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3326.16 | -3033.28
WO-00016 | Cleaning – Electrical Equipment ELEC-0008 | ELEC-0008 | Elec | Flare-System | Cleaning | Critical | FALSE | FALSE | DEFER | 23061.33 | 13 | 1.8 | 0.3 | 5 | 20.1 | 3 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5958.15 | -17103.18
WO-00017 | Calibration – Instrument/Analyser INST-0106 | INST-0106 | Inst | Offsites | Calibration | Critical | FALSE | TRUE | INCLUDE | 621.83 | 0.5 | 8.2 | 12.6 | 0 | 21.3 | 3 | 0.96519 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.87 | 768.04
WO-00018 | Overhaul – Reciprocating Compressor CMP-0017 | CMP-0017 | Cmp | Offsites | Overhaul | Critical | FALSE | TRUE | INCLUDE | 193398.98 | 76.1 | 33.8 | 17.6 | 15.8 | 143.3 | 18 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 155726.02
WO-00019 | Inspection – Instrument/Analyser INST-0048 | INST-0048 | Inst | Flare-System | Inspection | Low | FALSE | FALSE | DEFER | 1621.98 | 3.9 | 0.1 | 2.2 | 0.9 | 7.1 | 1 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | HIGH | 949.8 | -672.18
WO-00020 | Replacement – Electrical Equipment ELEC-0033 | ELEC-0033 | Elec | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 71220.87 | 37.5 | 16.9 | 8.7 | 3.7 | 66.8 | 8 | 0.23847 | 1602.4435 | 2.5 | 3 | 2 | 6 | MEDIUM | 2146.27 | -69074.6 | WO-00015
WO-00021 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | Pmp | Tank-Farm | Inspection | Critical | FALSE | TRUE | INCLUDE | 2928.69 | 9 | 1.8 | 1.4 | 0.5 | 12.7 | 2 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18327.69 | 15399
WO-00022 | Overhaul – Centrifugal Pump PMP-0039 | PMP-0039 | Pmp | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 339510.92 | 44.1 | 43.4 | 48.9 | 17.1 | 153.5 | 19 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15725.17 | -323785.75
WO-00023 | Cleaning – Control Valve VLV-0112 | VLV-0112 | Vlv | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 9022.56 | 7.6 | 1.2 | 0.1 | 8.6 | 17.5 | 2 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3419.43 | -5603.13
WO-00024 | Overhaul – Instrument/Analyser INST-0117 | INST-0117 | Inst | Flare-System | Overhaul | Medium | FALSE | TRUE | INCLUDE | 206394.95 | 233.9 | 15.3 | 14.4 | 7.3 | 270.9 | 34 | 0.86878 | 730 | 2 | 5 | 2 | 10 | HIGH | 1251.04 | -205143.91
WO-00025 | Testing – Control Valve VLV-0063 | VLV-0063 | Vlv | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 3914.39 | 18.3 | 9.6 | 17 | 0.1 | 45 | 6 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2078.14 | -1836.25
WO-00026 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | Elec | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 13871.67 | 9.7 | 1.7 | 1.9 | 5.7 | 19 | 2 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1934.16 | -11937.51
WO-00027 | Calibration – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Calibration | High | FALSE | TRUE | INCLUDE | 876.17 | 1.7 | 4.2 | 16.4 | 0.1 | 22.4 | 3 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | 4507.68
WO-00028 | Cleaning – Instrument/Analyser INST-0039 | INST-0039 | Inst | Utilities | Cleaning | High | FALSE | FALSE | DEFER | 13598.13 | 24.4 | 2 | 0.2 | 4.2 | 30.8 | 4 | 0.96419 | 730 | 2 | 5 | 2 | 10 | HIGH | 1388.43 | -12209.7
WO-00029 | Overhaul – Control Valve VLV-0104 | VLV-0104 | Vlv | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 303937.2 | 211.2 | 40.4 | 8.8 | 13.1 | 273.5 | 34 | 0.55849 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2996.99 | -300940.21
WO-00030 | Overhaul – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Overhaul | Critical | FALSE | FALSE | DEFER | 91427.47 | 119.5 | 25.3 | 15.9 | 19.1 | 179.8 | 22 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | -83562.45
WO-00031 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | Elec | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 13377.52 | 25.1 | 0.2 | 0.2 | 4.4 | 29.9 | 4 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1934.16 | -11443.36
WO-00032 | Replacement – Electrical Equipment ELEC-0085 | ELEC-0085 | Elec | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 92766.51 | 20.8 | 3.5 | 12.3 | 8 | 44.6 | 6 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7020.85 | -85745.66
WO-00033 | Calibration – Pressure Vessel VSL-0023 | VSL-0023 | Vsl | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1762.08 | 1.4 | 7.5 | 7.7 | 0.6 | 17.2 | 2 | 0.40366 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 87797.04 | 86034.96
WO-00034 | Replacement – Instrument/Analyser INST-0029 | INST-0029 | Inst | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 80206.91 | 33 | 11.1 | 5.8 | 7 | 56.9 | 7 | 0.95892 | 730 | 2 | 5 | 2 | 10 | HIGH | 1380.84 | -78826.07
WO-00035 | Inspection – Instrument/Analyser INST-0177 | INST-0177 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 3309.18 | 2.4 | 0.1 | 5 | 0.5 | 8 | 1 | 0.86611 | 730 | 2 | 5 | 2 | 10 | HIGH | 1247.2 | -2061.98
WO-00036 | Replacement – Instrument/Analyser INST-0141 | INST-0141 | Inst | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 117701.45 | 21.1 | 15.1 | 9.7 | 1.6 | 47.5 | 6 | 0.9166 | 730 | 2 | 5 | 2 | 10 | HIGH | 1319.9 | -116381.55
WO-00037 | Inspection – Heat Exchanger HX-0005 | HX-0005 | Hx | Offsites | Inspection | Critical | FALSE | TRUE | INCLUDE | 5600.54 | 4 | 1.5 | 4.1 | 0.7 | 10.3 | 1 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | HIGH | 33706.39 | 28105.85
WO-00038 | Calibration – Instrument/Analyser INST-0126 | INST-0126 | Inst | Unit-200 | Calibration | Medium | FALSE | FALSE | DEFER | 2972.41 | 0.5 | 4.2 | 17 | 0.2 | 21.9 | 3 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | HIGH | 978.78 | -1993.63
WO-00039 | Calibration – Storage Tank TNK-0019 | TNK-0019 | Tnk | Tank-Farm | Calibration | Critical | FALSE | TRUE | INCLUDE | 304.05 | 1.1 | 6.6 | 8.9 | 0.9 | 17.5 | 2 | 0.0041101 | 6049.2321 | 4 | 1 | 4 | 4 | LOW | 961.75 | 657.7
WO-00040 | Replacement – Instrument/Analyser INST-0175 | INST-0175 | Inst | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 102596.9 | 17.9 | 16.8 | 5.6 | 5.4 | 45.7 | 6 | 0.88589 | 730 | 2 | 5 | 2 | 10 | HIGH | 1275.68 | -101321.22 | WO-00037
WO-00041 | Calibration – Instrument/Analyser INST-0007 | INST-0007 | Inst | Unit-100 | Calibration | Medium | FALSE | FALSE | DEFER | 2413.68 | 1.7 | 9.9 | 14.8 | 0.8 | 27.2 | 3 | 0.96291 | 730 | 2 | 5 | 2 | 10 | HIGH | 1386.59 | -1027.09
WO-00042 | Repair – Instrument/Analyser INST-0033 | INST-0033 | Inst | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 52213.15 | 89.3 | 10.1 | 10.9 | 7.6 | 117.9 | 15 | 0.95645 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.28 | -50835.87
WO-00043 | Replacement – Control Valve VLV-0029 | VLV-0029 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 117474.92 | 30.6 | 5.3 | 10.6 | 4.6 | 51.1 | 6 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -114969.04
WO-00044 | Testing – Instrument/Analyser INST-0119 | INST-0119 | Inst | Tank-Farm | Testing | High | FALSE | FALSE | DEFER | 14805.56 | 13.7 | 18 | 10.4 | 1.7 | 43.8 | 5 | 0.89642 | 730 | 2 | 5 | 2 | 10 | HIGH | 1290.84 | -13514.72
WO-00045 | Inspection – Control Valve VLV-0018 | VLV-0018 | Vlv | Utilities | Inspection | High | FALSE | FALSE | DEFER | 7802.09 | 8.9 | 0.6 | 3.7 | 0.5 | 13.7 | 2 | 0.66617 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3574.81 | -4227.28
WO-00046 | Replacement – Control Valve VLV-0080 | VLV-0080 | Vlv | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 20643.16 | 36.6 | 10 | 14.2 | 2.9 | 63.7 | 8 | 0.49658 | 27.375 | 2.65 | 4 | 3 | 12 | HIGH | 2664.75 | -17978.41
WO-00047 | Cleaning – Control Valve VLV-0033 | VLV-0033 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 22590.42 | 6.6 | 1.2 | 1.7 | 4.6 | 14.1 | 2 | 0.52725 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2829.34 | -19761.08
WO-00048 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 36387.38 | 31.3 | 7.9 | 9.4 | 6.8 | 55.4 | 7 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -33881.5 | WO-00019
WO-00049 | Replacement – Control Valve VLV-0096 | VLV-0096 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 84321.48 | 17.1 | 6 | 8 | 1 | 32.1 | 4 | 0.64268 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3448.8 | -80872.68
WO-00050 | Inspection – Centrifugal Pump PMP-0052 | PMP-0052 | Pmp | Unit-300 | Inspection | High | FALSE | TRUE | INCLUDE | 2619.75 | 10 | 1.8 | 1.9 | 0.3 | 14 | 2 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17151.61 | 14531.86
WO-00051 | Repair – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Repair | Low | FALSE | FALSE | DEFER | 64606.38 | 19.6 | 7.2 | 9.5 | 8.8 | 45.1 | 6 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -63228.56
WO-00052 | Inspection – Pressure Vessel VSL-0022 | VSL-0022 | Vsl | Offsites | Inspection | Critical | FALSE | TRUE | INCLUDE | 4849.8 | 3.2 | 1.4 | 4.7 | 0.5 | 9.8 | 1 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | HIGH | 58166.81 | 53317.01
WO-00053 | Cleaning – Piping/Pipeline Segment PPL-0014 | PPL-0014 | Ppl | Unit-300 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 10804.4 | 23.5 | 0.7 | 1.7 | 4.2 | 30.1 | 4 | 0.078998 | 3950.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 3806.13 | -6998.27
WO-00054 | Replacement – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Replacement | Critical | FALSE | TRUE | INCLUDE | 9015.32 | 22.6 | 13.9 | 6.8 | 2 | 45.3 | 6 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 23862.92
WO-00055 | Inspection – Instrument/Analyser INST-0124 | INST-0124 | Inst | Unit-200 | Inspection | Low | FALSE | FALSE | DEFER | 7072.3 | 9.6 | 0.1 | 4 | 0.7 | 14.4 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5632.3
WO-00056 | Replacement – Heat Exchanger HX-0032 | HX-0032 | Hx | Tank-Farm | Replacement | Critical | FALSE | TRUE | INCLUDE | 37833.53 | 31.6 | 17.4 | 18.6 | 5.2 | 72.8 | 9 | 0.50931 | 2190 | 4 | 4 | 4 | 16 | HIGH | 59589.59 | 21756.06
WO-00057 | Calibration – Instrument/Analyser INST-0048 | INST-0048 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 2592.68 | 0.8 | 7.3 | 10.4 | 0.5 | 19 | 2 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | HIGH | 949.8 | -1642.88
WO-00058 | Calibration – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Calibration | High | FALSE | FALSE | DEFER | 2937.02 | 0.9 | 4.7 | 10 | 0.1 | 15.7 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1497.02
WO-00059 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | High | FALSE | TRUE | INCLUDE | 3766.42 | 3.3 | 0.7 | 4.2 | 0.2 | 8.4 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 85675.22
WO-00060 | Repair – Instrument/Analyser INST-0115 | INST-0115 | Inst | Utilities | Repair | High | FALSE | FALSE | DEFER | 46220.48 | 25.8 | 13 | 12.6 | 5.6 | 57 | 7 | 0.96766 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.43 | -44827.05
WO-00061 | Overhaul – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Overhaul | Low | FALSE | FALSE | DEFER | 332694.02 | 93.5 | 33.7 | 10.9 | 10.7 | 148.8 | 19 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | -325381.82
WO-00062 | Replacement – Control Valve VLV-0065 | VLV-0065 | Vlv | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 74595.34 | 29.3 | 7.7 | 22.3 | 4.1 | 63.4 | 8 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3625.6 | -70969.74
WO-00063 | Repair – Electrical Equipment ELEC-0057 | ELEC-0057 | Elec | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 60183.66 | 70.7 | 5.3 | 4.4 | 6.7 | 87.1 | 11 | 0.21302 | 1698.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1917.2 | -58266.46 | WO-00046
WO-00064 | Replacement – Reciprocating Compressor CMP-0001 | CMP-0001 | Cmp | Unit-200 | Replacement | High | FALSE | TRUE | INCLUDE | 94600.93 | 22.9 | 3.3 | 4.7 | 5 | 35.9 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 254524.07
WO-00065 | Repair – Control Valve VLV-0050 | VLV-0050 | Vlv | Utilities | Repair | Low | FALSE | FALSE | DEFER | 10642.74 | 26.1 | 17.8 | 8.6 | 5.3 | 57.8 | 7 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3189.72 | -7453.02
WO-00066 | Cleaning – Control Valve VLV-0061 | VLV-0061 | Vlv | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 10962.89 | 27.7 | 0.1 | 1.9 | 6 | 35.7 | 4 | 0.64915 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3483.48 | -7479.41
WO-00067 | Testing – Piping/Pipeline Segment PPL-0016 | PPL-0016 | Ppl | Offsites | Testing | Critical | FALSE | FALSE | DEFER | 7856.2 | 9.9 | 9.4 | 17.2 | 1.1 | 37.6 | 5 | 0.14302 | 2885.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6890.59 | -965.61
WO-00068 | Calibration – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Calibration | Critical | FALSE | TRUE | INCLUDE | 2003.44 | 0.8 | 2 | 11.1 | 0 | 13.9 | 2 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | 11569.69
WO-00069 | Overhaul – Control Valve VLV-0114 | VLV-0114 | Vlv | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 62923.13 | 95.1 | 35.5 | 21 | 24 | 175.6 | 22 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3549.3 | -59373.83
WO-00070 | Cleaning – Pressure Vessel VSL-0012 | VSL-0012 | Vsl | Utilities | Cleaning | High | FALSE | FALSE | DEFER | 24206.73 | 24.8 | 0.6 | 1.5 | 3.1 | 30 | 4 | 0.36396 | 334.4951 | 5 | 4 | 5 | 20 | CRITICAL | 79161.63 | 54954.9 | WO-00029
WO-00071 | Overhaul – Electrical Equipment ELEC-0026 | ELEC-0026 | Elec | Utilities | Overhaul | High | FALSE | FALSE | DEFER | 24843.17 | 94.8 | 48.1 | 21.3 | 7.6 | 171.8 | 21 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5492.41 | -19350.76
WO-00072 | Overhaul – Instrument/Analyser INST-0010 | INST-0010 | Inst | Unit-300 | Overhaul | Medium | FALSE | FALSE | DEFER | 507949.81 | 191.6 | 26.3 | 16.8 | 4.9 | 239.6 | 30 | 0.786 | 730 | 2 | 5 | 2 | 10 | HIGH | 1131.85 | -506817.96
WO-00073 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | Ppl | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2243.11 | 0.8 | 6.8 | 11 | 0.6 | 19.2 | 2 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8869.41 | 6626.3 | WO-00039
WO-00074 | Calibration – Instrument/Analyser INST-0169 | INST-0169 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 1621.58 | 1.9 | 5.4 | 4.3 | 0.2 | 11.8 | 1 | 0.83629 | 730 | 2 | 5 | 2 | 10 | HIGH | 1204.25 | -417.33
WO-00075 | Cleaning – Instrument/Analyser INST-0146 | INST-0146 | Inst | Offsites | Cleaning | Medium | FALSE | FALSE | DEFER | 14257.23 | 21.1 | 0.5 | 1.3 | 7.6 | 30.5 | 4 | 0.87445 | 730 | 2 | 5 | 2 | 10 | HIGH | 1259.2 | -12998.03
WO-00076 | Overhaul – Instrument/Analyser INST-0177 | INST-0177 | Inst | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 119671 | 122.8 | 41 | 46.2 | 15.9 | 225.9 | 28 | 0.86611 | 730 | 2 | 5 | 2 | 10 | HIGH | 1247.2 | -118423.8
WO-00077 | Calibration – Heat Exchanger HX-0021 | HX-0021 | Hx | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2272.41 | 0.7 | 8.6 | 5.2 | 0 | 14.5 | 2 | 0.51614 | 2190 | 4 | 4 | 4 | 16 | HIGH | 60387.91 | 58115.5
WO-00078 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 7104.07 | 5.4 | 0.5 | 2.7 | 0.4 | 9 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 82337.57
WO-00079 | Inspection – Instrument/Analyser INST-0073 | INST-0073 | Inst | Unit-100 | Inspection | Low | FALSE | FALSE | DEFER | 5453.77 | 3.1 | 1.6 | 1.8 | 0.7 | 7.2 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4013.77 | WO-00052
WO-00080 | Inspection – Reciprocating Compressor CMP-0015 | CMP-0015 | Cmp | Tank-Farm | Inspection | Critical | TRUE | TRUE | INCLUDE | 1241.92 | 9.6 | 0.9 | 3.5 | 0 | 14 | 2 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 162580.25 | 161338.33
WO-00081 | Overhaul – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Overhaul | Critical | TRUE | TRUE | INCLUDE | 533437.71 | 94.3 | 40.6 | 35.8 | 6.3 | 177 | 22 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | -519864.58
WO-00082 | Replacement – Heat Exchanger HX-0005 | HX-0005 | Hx | Offsites | Replacement | High | FALSE | FALSE | DEFER | 55890.67 | 41 | 9.8 | 8.9 | 7.3 | 67 | 8 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | HIGH | 33706.39 | -22184.28
WO-00083 | Overhaul – Electrical Equipment ELEC-0019 | ELEC-0019 | Elec | Unit-200 | Overhaul | High | FALSE | FALSE | DEFER | 339335.46 | 84.4 | 36.6 | 24.3 | 11.3 | 156.6 | 20 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4601.34 | -334734.12
WO-00084 | Cleaning – Instrument/Analyser INST-0117 | INST-0117 | Inst | Flare-System | Cleaning | Medium | FALSE | FALSE | DEFER | 15463.95 | 12.2 | 1.7 | 1.7 | 2.9 | 18.5 | 2 | 0.86878 | 730 | 2 | 5 | 2 | 10 | HIGH | 1251.04 | -14212.91
WO-00085 | Replacement – Control Valve VLV-0043 | VLV-0043 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 119967.21 | 19.7 | 7 | 12.8 | 3.4 | 42.9 | 5 | 0.41764 | 809.375 | 2.65 | 4 | 3 | 12 | HIGH | 2241.14 | -117726.07
WO-00086 | Overhaul – Instrument/Analyser INST-0167 | INST-0167 | Inst | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 144214.12 | 141.3 | 45.3 | 41.3 | 14 | 241.9 | 30 | 0.95101 | 730 | 2 | 5 | 2 | 10 | HIGH | 1369.46 | -142844.66
WO-00087 | Inspection – Instrument/Analyser INST-0141 | INST-0141 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 7100.03 | 7.7 | 1.1 | 4.5 | 0.1 | 13.4 | 2 | 0.9166 | 730 | 2 | 5 | 2 | 10 | HIGH | 1319.9 | -5780.13
WO-00088 | Replacement – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 18866.41 | 32.2 | 9 | 22.8 | 3.9 | 67.9 | 8 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -16734.24
WO-00089 | Calibration – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2070.19 | 1.8 | 5.3 | 10.2 | 0.2 | 17.5 | 2 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 46371.76
WO-00090 | Repair – Electrical Equipment ELEC-0077 | ELEC-0077 | Elec | Offsites | Repair | High | FALSE | FALSE | DEFER | 39001.81 | 39.4 | 9.6 | 10.7 | 7.4 | 67.1 | 8 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7273.03 | -31728.78
WO-00091 | Calibration – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 1963.41 | 1.6 | 4 | 14.1 | 0.2 | 19.9 | 2 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 30914.83
WO-00092 | Calibration – Electrical Equipment ELEC-0007 | ELEC-0007 | Elec | Offsites | Calibration | Low | FALSE | TRUE | INCLUDE | 1968.67 | 0.4 | 8.9 | 4.9 | 0.6 | 14.8 | 2 | 0.84418 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7597.65 | 5628.98 | WO-00053
WO-00093 | Cleaning – Control Valve VLV-0112 | VLV-0112 | Vlv | Unit-200 | Cleaning | High | FALSE | FALSE | DEFER | 20216.12 | 18.3 | 1.6 | 1.3 | 7.5 | 28.7 | 4 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3419.43 | -16796.69
WO-00094 | Calibration – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Calibration | High | FALSE | TRUE | INCLUDE | 866.15 | 2 | 3.8 | 7.8 | 0.9 | 14.5 | 2 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | 2082.09
WO-00095 | Replacement – Instrument/Analyser INST-0111 | INST-0111 | Inst | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 87183.62 | 16.3 | 4.9 | 13.7 | 3.2 | 38.1 | 5 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -85743.62
WO-00096 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Inspection | Critical | TRUE | TRUE | INCLUDE | 3341.33 | 4.5 | 0.1 | 3.5 | 0.6 | 8.7 | 1 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | -1950.75
WO-00097 | Replacement – Pressure Vessel VSL-0009 | VSL-0009 | Vsl | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 105372.64 | 38.3 | 9.4 | 13.3 | 2.9 | 63.9 | 8 | 0.23421 | 1546.4951 | 5 | 3 | 5 | 15 | HIGH | 50941.13 | -54431.51
WO-00098 | Repair – Piping/Pipeline Segment PPL-0045 | PPL-0045 | Ppl | Unit-100 | Repair | Critical | TRUE | TRUE | INCLUDE | 73031.8 | 28.6 | 12.1 | 4.9 | 3.8 | 49.4 | 6 | 0.25897 | 736.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12477.11 | -60554.69
WO-00099 | Cleaning – Heat Exchanger HX-0029 | HX-0029 | Hx | Unit-200 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 5551.51 | 26.1 | 0.2 | 0 | 8.8 | 35.1 | 4 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | HIGH | 26996.81 | 21445.3
WO-00100 | Replacement – Centrifugal Pump PMP-0061 | PMP-0061 | Pmp | Utilities | Replacement | High | FALSE | FALSE | DEFER | 73482.47 | 19.6 | 5 | 13.4 | 4.2 | 42.2 | 5 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | MEDIUM | 5761.08 | -67721.39
WO-00101 | Replacement – Centrifugal Pump PMP-0019 | PMP-0019 | Pmp | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 81236.69 | 47.9 | 5 | 4.9 | 5 | 62.8 | 8 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | MEDIUM | 2786.64 | -78450.05
WO-00102 | Cleaning – Electrical Equipment ELEC-0035 | ELEC-0035 | Elec | Offsites | Cleaning | Medium | FALSE | FALSE | DEFER | 17845.16 | 13.7 | 0.5 | 1.1 | 3.6 | 18.9 | 2 | 0.3627 | 1082.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 3264.29 | -14580.87
WO-00103 | Inspection – Pressure Vessel VSL-0001 | VSL-0001 | Vsl | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 2755.35 | 6.1 | 1 | 3.4 | 0.4 | 10.9 | 1 | 0.21575 | 1726.4951 | 5 | 3 | 5 | 15 | HIGH | 46925.07 | 44169.72
WO-00104 | Repair – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Repair | Critical | TRUE | TRUE | INCLUDE | 70570.85 | 65.9 | 20.5 | 13 | 4.9 | 104.3 | 13 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | -63712.99
WO-00105 | Cleaning – Instrument/Analyser INST-0112 | INST-0112 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 1612.76 | 4.2 | 1.7 | 0.1 | 6.2 | 12.2 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -172.76
WO-00106 | Inspection – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 7228.41 | 3.5 | 1.8 | 4.1 | 0.2 | 9.6 | 1 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 73327.8
WO-00107 | Replacement – Instrument/Analyser INST-0065 | INST-0065 | Inst | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 50764.32 | 20.8 | 20 | 8.6 | 8.5 | 57.9 | 7 | 0.94806 | 730 | 2 | 5 | 2 | 10 | HIGH | 1365.21 | -49399.11 | WO-00038
WO-00108 | Testing – Centrifugal Pump PMP-0037 | PMP-0037 | Pmp | Unit-200 | Testing | Critical | TRUE | TRUE | INCLUDE | 3770.09 | 9.6 | 15.2 | 6.4 | 1.6 | 32.8 | 4 | 0.82008 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17713.81 | 13943.72
WO-00109 | Cleaning – Heat Exchanger HX-0018 | HX-0018 | Hx | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 14191.21 | 18.5 | 0.1 | 0.3 | 3.3 | 22.2 | 3 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | HIGH | 33820.42 | 19629.21
WO-00110 | Inspection – Piping/Pipeline Segment PPL-0003 | PPL-0003 | Ppl | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 7422.22 | 6.1 | 1.2 | 2.4 | 0.3 | 10 | 1 | 0.25475 | 820.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12273.66 | 4851.44
WO-00111 | Replacement – Pressure Vessel VSL-0028 | VSL-0028 | Vsl | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 44519.28 | 31.5 | 11.1 | 23.7 | 3 | 69.3 | 9 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | HIGH | 58882.1 | 14362.82
WO-00112 | Inspection – Heat Exchanger HX-0025 | HX-0025 | Hx | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 3189.99 | 7.7 | 0.3 | 3.3 | 0.4 | 11.7 | 1 | 0.2607 | 1521.1654 | 4 | 3 | 4 | 12 | HIGH | 30502.19 | 27312.2
WO-00113 | Testing – Control Valve VLV-0098 | VLV-0098 | Vlv | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 6497.25 | 16.1 | 12.3 | 22.7 | 0.6 | 51.7 | 6 | 0.64153 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3442.61 | -3054.64
WO-00114 | Calibration – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1162.27 | 0.7 | 10 | 12.9 | 0.7 | 24.3 | 3 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | 1343.61
WO-00115 | Repair – Control Valve VLV-0038 | VLV-0038 | Vlv | Tank-Farm | Repair | Low | FALSE | FALSE | DEFER | 69222.36 | 59.8 | 11.7 | 2.4 | 6.5 | 80.4 | 10 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3387.34 | -65835.02
WO-00116 | Overhaul – Control Valve VLV-0050 | VLV-0050 | Vlv | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 111353.09 | 97.6 | 29.4 | 43.1 | 7.4 | 177.5 | 22 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3189.72 | -108163.37
WO-00117 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | Inst | Utilities | Calibration | Critical | FALSE | FALSE | DEFER | 2820.93 | 0.2 | 9.4 | 13.6 | 0.8 | 24 | 3 | 0.81141 | 730 | 2 | 5 | 2 | 10 | HIGH | 1168.43 | -1652.5
WO-00118 | Overhaul – Centrifugal Pump PMP-0067 | PMP-0067 | Pmp | Unit-300 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 379238.36 | 101.4 | 26.1 | 31.3 | 15.1 | 173.9 | 22 | 0.92495 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19978.83 | -359259.53
WO-00119 | Overhaul – Control Valve VLV-0060 | VLV-0060 | Vlv | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 140083.62 | 223.3 | 49 | 20.6 | 7.5 | 300.4 | 38 | 0.57589 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3090.38 | -136993.24
WO-00120 | Overhaul – Distillation Tower TWR-0011 | TWR-0011 | Twr | Unit-100 | Overhaul | Medium | FALSE | FALSE | DEFER | 526585.78 | 140 | 10.3 | 9.7 | 8.5 | 168.5 | 21 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | HIGH | 189640.61 | -336945.17 | WO-00098
WO-00121 | Cleaning – Instrument/Analyser INST-0044 | INST-0044 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 14510.99 | 11.7 | 1.9 | 0.7 | 8.7 | 23 | 3 | 0.9471 | 730 | 2 | 5 | 2 | 10 | HIGH | 1363.83 | -13147.16
WO-00122 | Overhaul – Electrical Equipment ELEC-0076 | ELEC-0076 | Elec | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 538159.22 | 95.4 | 35.7 | 11.7 | 13.5 | 156.3 | 20 | 0.50503 | 344.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4545.25 | -533613.97
WO-00123 | Inspection – Storage Tank TNK-0018 | TNK-0018 | Tnk | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 627.57 | 4.6 | 1.2 | 2.8 | 0.3 | 8.9 | 1 | 0.071498 | 3671.2321 | 4 | 2 | 4 | 8 | MEDIUM | 16730.59 | 16103.02
WO-00124 | Testing – Control Valve VLV-0053 | VLV-0053 | Vlv | Utilities | Testing | Medium | FALSE | TRUE | INCLUDE | 2321.97 | 9.5 | 17 | 18.7 | 0.7 | 45.9 | 6 | 0.65711 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3526.23 | 1204.26
WO-00125 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 3055.41 | 7.7 | 1.3 | 4.3 | 0 | 13.3 | 2 | 0.94369 | 730 | 2 | 5 | 2 | 10 | HIGH | 1358.91 | -1696.5
WO-00126 | Inspection – Centrifugal Pump PMP-0014 | PMP-0014 | Pmp | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 2021.65 | 2 | 1 | 3.1 | 0.7 | 6.8 | 1 | 0.84821 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18321.4 | 16299.75
WO-00127 | Inspection – Instrument/Analyser INST-0092 | INST-0092 | Inst | Unit-300 | Inspection | Low | FALSE | FALSE | DEFER | 5586.79 | 2.4 | 1.7 | 1.1 | 0.5 | 5.7 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4146.79
WO-00128 | Cleaning – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Cleaning | Low | FALSE | TRUE | INCLUDE | 15602 | 20.4 | 0.2 | 1.3 | 9 | 30.9 | 4 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 32388.52
WO-00129 | Overhaul – Centrifugal Pump PMP-0046 | PMP-0046 | Pmp | Unit-300 | Overhaul | Critical | FALSE | FALSE | DEFER | 216535.34 | 190.7 | 30.8 | 18.8 | 7.4 | 247.7 | 31 | 0.1139 | 2025.705 | 3 | 2 | 3 | 6 | MEDIUM | 2460.33 | -214075.01
WO-00130 | Overhaul – Instrument/Analyser INST-0126 | INST-0126 | Inst | Unit-200 | Overhaul | Critical | FALSE | FALSE | DEFER | 114522.78 | 43.9 | 10.2 | 47.1 | 5.5 | 106.7 | 13 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | HIGH | 978.78 | -113544 | WO-00048
WO-00131 | Overhaul – Heat Exchanger HX-0031 | HX-0031 | Hx | Unit-300 | Overhaul | Critical | FALSE | FALSE | DEFER | 158383.67 | 232.5 | 46.3 | 25 | 13 | 316.8 | 40 | 0.31048 | 1063.1652 | 4 | 3 | 4 | 12 | HIGH | 36326.65 | -122057.02
WO-00132 | Inspection – Instrument/Analyser INST-0005 | INST-0005 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 2767.07 | 3 | 0.2 | 3.2 | 0.1 | 6.5 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1327.07
WO-00133 | Overhaul – Centrifugal Pump PMP-0063 | PMP-0063 | Pmp | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 273735.18 | 67.5 | 8.2 | 16.1 | 8.7 | 100.5 | 13 | 0.55047 | 235.7051 | 3 | 4 | 3 | 12 | HIGH | 11890.05 | -261845.13 | WO-00065
WO-00134 | Repair – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 33663.66 | 45.3 | 22.5 | 13.3 | 2.7 | 83.8 | 10 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -32223.66
WO-00135 | Overhaul – Electrical Equipment ELEC-0004 | ELEC-0004 | Elec | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 345424.59 | 67.7 | 20.3 | 20.8 | 9.2 | 118 | 15 | 0.79103 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7119.3 | -338305.29
WO-00136 | Cleaning – Instrument/Analyser INST-0066 | INST-0066 | Inst | Offsites | Cleaning | Critical | FALSE | FALSE | DEFER | 13225.36 | 8.8 | 0.2 | 1.6 | 5.8 | 16.4 | 2 | 0.77693 | 730 | 2 | 5 | 2 | 10 | HIGH | 1118.77 | -12106.59
WO-00137 | Replacement – Electrical Equipment ELEC-0048 | ELEC-0048 | Elec | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 97463.88 | 47.1 | 17.8 | 16 | 4.8 | 85.7 | 11 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4217.99 | -93245.89 | WO-00091
WO-00138 | Inspection – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 5415.91 | 6.7 | 0.3 | 4.5 | 0.4 | 11.9 | 1 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | 1441.95
WO-00139 | Replacement – Reciprocating Compressor CMP-0002 | CMP-0002 | Cmp | Utilities | Replacement | Medium | FALSE | TRUE | INCLUDE | 105033.52 | 55.7 | 10.8 | 23.1 | 8.9 | 98.5 | 12 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 172649.17 | 67615.65
WO-00140 | Repair – Heat Exchanger HX-0015 | HX-0015 | Hx | Utilities | Repair | Medium | FALSE | TRUE | INCLUDE | 31786.28 | 77.6 | 19 | 15 | 2.6 | 114.2 | 14 | 0.37181 | 451.1654 | 4 | 4 | 4 | 16 | HIGH | 43502.04 | 11715.76
WO-00141 | Testing – Control Valve VLV-0004 | VLV-0004 | Vlv | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 4888.62 | 19.8 | 11.6 | 8 | 0.2 | 39.6 | 5 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | MEDIUM | 1675.84 | -3212.78
WO-00142 | Cleaning – Reciprocating Compressor CMP-0010 | CMP-0010 | Cmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 8371.15 | 18.6 | 0.7 | 0.9 | 8.9 | 29.1 | 4 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 307515.33 | 299144.18
WO-00143 | Calibration – Control Valve VLV-0069 | VLV-0069 | Vlv | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1833.78 | 2 | 3.9 | 8.2 | 0.1 | 14.2 | 2 | 0.57942 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3109.29 | 1275.51
WO-00144 | Cleaning – Control Valve VLV-0001 | VLV-0001 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 18423.08 | 12.1 | 0 | 1.3 | 10 | 23.4 | 3 | 0.63786 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3422.93 | -15000.15
WO-00145 | Inspection – Instrument/Analyser INST-0076 | INST-0076 | Inst | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 2685.08 | 5.4 | 0.5 | 2.4 | 0.6 | 8.9 | 1 | 0.79324 | 730 | 2 | 5 | 2 | 10 | HIGH | 1142.27 | -1542.81
WO-00146 | Replacement – Heat Exchanger HX-0013 | HX-0013 | Hx | Unit-100 | Replacement | High | FALSE | TRUE | INCLUDE | 9603.6 | 55.7 | 9.3 | 10.6 | 1.8 | 77.4 | 10 | 0.49943 | 2190 | 4 | 4 | 4 | 16 | HIGH | 58433.39 | 48829.79
WO-00147 | Repair – Instrument/Analyser INST-0095 | INST-0095 | Inst | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 5209.95 | 21.4 | 7.8 | 12.8 | 9.3 | 51.3 | 6 | 0.94927 | 730 | 2 | 5 | 2 | 10 | HIGH | 1366.94 | -3843.01
WO-00148 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 93071.68 | 46.6 | 6.4 | 7.2 | 4.2 | 64.4 | 8 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -90565.8
WO-00149 | Calibration – Instrument/Analyser INST-0135 | INST-0135 | Inst | Tank-Farm | Calibration | Low | FALSE | FALSE | DEFER | 2064.39 | 1.7 | 4.2 | 9.4 | 0 | 15.3 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -624.39
WO-00150 | Cleaning – Instrument/Analyser INST-0027 | INST-0027 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 8154.94 | 5.7 | 1.4 | 1.5 | 7.3 | 15.9 | 2 | 0.91997 | 730 | 2 | 5 | 2 | 10 | HIGH | 1324.76 | -6830.18
WO-00151 | Repair – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 60746.33 | 68.5 | 20.9 | 18.3 | 9.4 | 117.1 | 15 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | -19300.79
WO-00152 | Overhaul – Pressure Vessel VSL-0022 | VSL-0022 | Vsl | Offsites | Overhaul | Low | FALSE | FALSE | DEFER | 227784.38 | 203.8 | 35.1 | 11.2 | 6.8 | 256.9 | 32 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | HIGH | 58166.81 | -169617.57
WO-00153 | Repair – Control Valve VLV-0051 | VLV-0051 | Vlv | Offsites | Repair | High | FALSE | FALSE | DEFER | 76242.93 | 47.4 | 24.4 | 16.9 | 3.8 | 92.5 | 12 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2866.96 | -73375.97
WO-00154 | Testing – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Testing | Medium | FALSE | FALSE | DEFER | 938.18 | 12.8 | 17 | 17.6 | 0.5 | 47.9 | 6 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | 161.25 | WO-00025
WO-00155 | Replacement – Instrument/Analyser INST-0118 | INST-0118 | Inst | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 100339.4 | 19.4 | 14.5 | 19.7 | 2.7 | 56.3 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -98899.4 | WO-00145
WO-00156 | Calibration – Pressure Vessel VSL-0021 | VSL-0021 | Vsl | Flare-System | Calibration | Critical | TRUE | TRUE | INCLUDE | 440.8 | 0.4 | 5.6 | 18.9 | 0.6 | 25.5 | 3 | 0.27583 | 1150.4951 | 5 | 3 | 5 | 15 | HIGH | 59992.23 | 59551.43
WO-00157 | Testing – Instrument/Analyser INST-0056 | INST-0056 | Inst | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 7223.81 | 9.8 | 12.2 | 10.2 | 0.7 | 32.9 | 4 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | HIGH | 1103.88 | -6119.93
WO-00158 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Inspection | Medium | FALSE | FALSE | DEFER | 5645.44 | 3.6 | 0.8 | 1.6 | 0.6 | 6.6 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4205.44
WO-00159 | Replacement – Control Valve VLV-0058 | VLV-0058 | Vlv | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 23792.91 | 19.8 | 16.7 | 9.4 | 8 | 53.9 | 7 | 0.54217 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2909.45 | -20883.46 | WO-00011
WO-00160 | Inspection – Control Valve VLV-0063 | VLV-0063 | Vlv | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 5982.08 | 5.7 | 0.1 | 4.8 | 0.1 | 10.7 | 1 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2078.14 | -3903.94
WO-00161 | Replacement – Storage Tank TNK-0008 | TNK-0008 | Tnk | Offsites | Replacement | Low | FALSE | FALSE | DEFER | 61284.44 | 48.8 | 2.1 | 22.6 | 6.8 | 80.3 | 10 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | LOW | 1543.9 | -59740.54
WO-00162 | Calibration – Instrument/Analyser INST-0128 | INST-0128 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 2797.95 | 1.2 | 4.9 | 11.1 | 0.7 | 17.9 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1357.95
WO-00163 | Calibration – Centrifugal Pump PMP-0060 | PMP-0060 | Pmp | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 457.17 | 1.7 | 3.6 | 19.1 | 0.2 | 24.6 | 3 | 0.67091 | 1825 | 3 | 5 | 3 | 15 | HIGH | 14491.65 | 14034.48
WO-00164 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2492.37 | 1.5 | 9.7 | 8.3 | 0.8 | 20.3 | 3 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | 6923.67
WO-00165 | Cleaning – Instrument/Analyser INST-0151 | INST-0151 | Inst | Unit-300 | Cleaning | Low | FALSE | FALSE | DEFER | 11694.4 | 4.1 | 1.1 | 1.5 | 3.4 | 10.1 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10254.4
WO-00166 | Cleaning – Centrifugal Pump PMP-0032 | PMP-0032 | Pmp | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 5277.9 | 19.5 | 0.4 | 0.1 | 7.5 | 27.5 | 3 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | HIGH | 9543.04 | 4265.14
WO-00167 | Inspection – Instrument/Analyser INST-0161 | INST-0161 | Inst | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 6075.58 | 2.4 | 1.6 | 4.2 | 0.1 | 8.3 | 1 | 0.65143 | 452.2559 | 2 | 5 | 2 | 10 | HIGH | 938.05 | -5137.53
WO-00168 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 5281.03 | 2.5 | 1.9 | 1.8 | 0.7 | 6.9 | 1 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -4181.6
WO-00169 | Replacement – Storage Tank TNK-0013 | TNK-0013 | Tnk | Flare-System | Replacement | Critical | TRUE | TRUE | INCLUDE | 56859.21 | 37.8 | 20 | 4.5 | 1 | 63.3 | 8 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | LOW | 11354.04 | -45505.17
WO-00170 | Replacement – Instrument/Analyser INST-0012 | INST-0012 | Inst | Offsites | Replacement | Medium | FALSE | FALSE | DEFER | 106641.28 | 55.5 | 17.8 | 6.9 | 4.7 | 84.9 | 11 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -105201.28
WO-00171 | Replacement – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 81272.37 | 20.3 | 7.8 | 21.2 | 3.3 | 52.6 | 7 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -79944.67 | WO-00103
WO-00172 | Replacement – Control Valve VLV-0064 | VLV-0064 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 7705.73 | 21.3 | 5.1 | 14.1 | 2 | 42.5 | 5 | 0.65112 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3494.09 | -4211.64
WO-00173 | Repair – Control Valve VLV-0068 | VLV-0068 | Vlv | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 30276.47 | 23.5 | 14.4 | 16.1 | 6.3 | 60.3 | 8 | 0.63819 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3424.67 | -26851.8
WO-00174 | Cleaning – Instrument/Analyser INST-0092 | INST-0092 | Inst | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 12234.05 | 11.9 | 0.2 | 2 | 3.4 | 17.5 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10794.05
WO-00175 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Inspection | High | FALSE | TRUE | INCLUDE | 4819.43 | 5.5 | 0.5 | 2.7 | 0.7 | 9.4 | 1 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | 2492.77
WO-00176 | Repair – Electrical Equipment ELEC-0082 | ELEC-0082 | Elec | Utilities | Repair | Low | FALSE | FALSE | DEFER | 25895.01 | 26.2 | 28.8 | 16.6 | 4.1 | 75.7 | 9 | 0.68526 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6167.3 | -19727.71
WO-00177 | Overhaul – Electrical Equipment ELEC-0008 | ELEC-0008 | Elec | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 217850.21 | 207.9 | 39.6 | 20.5 | 16.1 | 284.1 | 36 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5958.15 | -211892.06 | WO-00015
WO-00178 | Inspection – Instrument/Analyser INST-0087 | INST-0087 | Inst | Unit-300 | Inspection | High | FALSE | FALSE | DEFER | 7717.44 | 6.4 | 1.2 | 3.4 | 0.6 | 11.6 | 1 | 0.95076 | 730 | 2 | 5 | 2 | 10 | HIGH | 1369.1 | -6348.34
WO-00179 | Testing – Instrument/Analyser INST-0019 | INST-0019 | Inst | Offsites | Testing | High | FALSE | FALSE | DEFER | 9514.19 | 14.1 | 13.1 | 9.8 | 0.1 | 37.1 | 5 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -8074.19
WO-00180 | Inspection – Control Valve VLV-0079 | VLV-0079 | Vlv | Unit-300 | Inspection | High | FALSE | FALSE | DEFER | 5499.45 | 9 | 0.6 | 2.3 | 0.7 | 12.6 | 2 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3315.02 | -2184.43 | WO-00168
WO-00181 | Testing – Electrical Equipment ELEC-0006 | ELEC-0006 | Elec | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 5775.78 | 3.8 | 7.5 | 22.7 | 0.5 | 34.5 | 4 | 0.30621 | 1330.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2755.87 | -3019.91
WO-00182 | Inspection – Control Valve VLV-0066 | VLV-0066 | Vlv | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 2036.35 | 9 | 0.3 | 1.1 | 0.5 | 10.9 | 1 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3450.07 | 1413.72
WO-00183 | Replacement – Control Valve VLV-0034 | VLV-0034 | Vlv | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 19738.66 | 59.1 | 14.2 | 21 | 7.8 | 102.1 | 13 | 0.54543 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2926.9 | -16811.76
WO-00184 | Replacement – Electrical Equipment ELEC-0068 | ELEC-0068 | Elec | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 42299.1 | 45.3 | 14.9 | 23 | 6.1 | 89.3 | 11 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1589.67 | -40709.43
WO-00185 | Overhaul – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 374022.58 | 125.3 | 41.2 | 32.6 | 4.2 | 203.3 | 25 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -372923.15
WO-00186 | Cleaning – Control Valve VLV-0088 | VLV-0088 | Vlv | Unit-100 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 22966.27 | 13.9 | 1.1 | 0.9 | 6.3 | 22.2 | 3 | 0.62881 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3374.35 | -19591.92
WO-00187 | Repair – Electrical Equipment ELEC-0067 | ELEC-0067 | Elec | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 73012.16 | 58.4 | 18.5 | 3 | 6.4 | 86.3 | 11 | 0.8538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7684.19 | -65327.97
WO-00188 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 331.95 | 1.4 | 4.3 | 14.4 | 0.6 | 20.7 | 3 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | 9084.09
WO-00189 | Overhaul – Control Valve VLV-0066 | VLV-0066 | Vlv | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 503845.46 | 161.1 | 10.9 | 26.6 | 10.2 | 208.8 | 26 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3450.07 | -500395.39 | WO-00126
WO-00190 | Cleaning – Instrument/Analyser INST-0032 | INST-0032 | Inst | Unit-200 | Cleaning | High | FALSE | FALSE | DEFER | 1249.55 | 18.6 | 1.5 | 1.5 | 2.5 | 24.1 | 3 | 0.93702 | 730 | 2 | 5 | 2 | 10 | HIGH | 1349.31 | 99.76
WO-00191 | Overhaul – Instrument/Analyser INST-0009 | INST-0009 | Inst | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 120166.45 | 124.1 | 11 | 12.8 | 17.4 | 165.3 | 21 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -118726.45
WO-00192 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | Inst | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 334.7 | 1.1 | 5.1 | 16.8 | 0.8 | 23.8 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 1105.3
WO-00193 | Cleaning – Piping/Pipeline Segment PPL-0015 | PPL-0015 | Ppl | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 6461.17 | 17.9 | 0.2 | 0.9 | 3.5 | 22.5 | 3 | 0.089098 | 3787.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4292.73 | -2168.44
WO-00194 | Overhaul – Instrument/Analyser INST-0049 | INST-0049 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 360602.64 | 112.1 | 20.1 | 16.5 | 22.2 | 170.9 | 21 | 0.63084 | 512.2559 | 2 | 5 | 2 | 10 | HIGH | 908.42 | -359694.22 | WO-00142
WO-00195 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | Elec | Utilities | Inspection | High | FALSE | FALSE | DEFER | 6125.76 | 5.3 | 0 | 3.1 | 0.1 | 8.5 | 1 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4834.45 | -1291.31
WO-00196 | Calibration – Instrument/Analyser INST-0079 | INST-0079 | Inst | Unit-300 | Calibration | Low | FALSE | TRUE | INCLUDE | 920 | 1.8 | 7.3 | 17.3 | 0.6 | 27 | 3 | 0.94074 | 730 | 2 | 5 | 2 | 10 | HIGH | 1354.67 | 434.67
WO-00197 | Replacement – Electrical Equipment ELEC-0080 | ELEC-0080 | Elec | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 68151.17 | 34.8 | 18.3 | 7.3 | 6.2 | 66.6 | 8 | 0.82033 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7382.93 | -60768.24 | WO-00164
WO-00198 | Replacement – Control Valve VLV-0120 | VLV-0120 | Vlv | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 104771.88 | 27.4 | 5.1 | 15.7 | 4.8 | 53 | 7 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2846.98 | -101924.9
WO-00199 | Inspection – Control Valve VLV-0108 | VLV-0108 | Vlv | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 2045.05 | 8.2 | 1.8 | 3.2 | 0.1 | 13.3 | 2 | 0.66731 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3580.94 | 1535.89
WO-00200 | Repair – Pressure Vessel VSL-0011 | VSL-0011 | Vsl | Unit-100 | Repair | Critical | FALSE | FALSE | DEFER | 60459.26 | 34.8 | 7.2 | 18.2 | 8.7 | 68.9 | 9 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | HIGH | 36127.93 | -24331.33
WO-00201 | Repair – Piping/Pipeline Segment PPL-0043 | PPL-0043 | Ppl | Tank-Farm | Repair | Low | FALSE | FALSE | DEFER | 9582.59 | 13.8 | 23.7 | 11.7 | 4.7 | 53.9 | 7 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6265.83 | -3316.76
WO-00202 | Repair – Instrument/Analyser INST-0088 | INST-0088 | Inst | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 6494.63 | 64.7 | 24.1 | 11.9 | 9.8 | 110.5 | 14 | 0.89303 | 730 | 2 | 5 | 2 | 10 | HIGH | 1285.97 | -5208.66
WO-00203 | Inspection – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 2067.41 | 8.6 | 2 | 1.4 | 0.1 | 12.1 | 2 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 45923.11
WO-00204 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Inspection | Critical | FALSE | TRUE | INCLUDE | 1107.34 | 9.1 | 1.6 | 4.5 | 0.7 | 15.9 | 2 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | 6757.68
WO-00205 | Repair – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Repair | High | FALSE | TRUE | INCLUDE | 25300.43 | 33.3 | 27 | 14.3 | 9.1 | 83.7 | 10 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -23972.73
WO-00206 | Testing – Electrical Equipment ELEC-0029 | ELEC-0029 | Elec | Unit-300 | Testing | Medium | FALSE | TRUE | INCLUDE | 9384.76 | 14 | 22.3 | 11.6 | 1.4 | 49.3 | 6 | 0.45763 | 611.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4118.71 | -5266.05
WO-00207 | Calibration – Instrument/Analyser INST-0006 | INST-0006 | Inst | Utilities | Calibration | Low | FALSE | FALSE | DEFER | 2711.44 | 1.4 | 2.5 | 6.9 | 1 | 11.8 | 1 | 0.96225 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.63 | -1325.81
WO-00208 | Testing – Instrument/Analyser INST-0057 | INST-0057 | Inst | Offsites | Testing | Medium | FALSE | FALSE | DEFER | 1033.59 | 8.9 | 19.2 | 19.1 | 0.2 | 47.4 | 6 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | HIGH | 1048.11 | 14.52
WO-00209 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | Elec | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 4249.75 | 3.9 | 0.1 | 1.3 | 0.9 | 6.2 | 1 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4834.45 | 584.7
WO-00210 | Testing – Instrument/Analyser INST-0029 | INST-0029 | Inst | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 7314.85 | 9.4 | 11.2 | 16.3 | 0.7 | 37.6 | 5 | 0.95892 | 730 | 2 | 5 | 2 | 10 | HIGH | 1380.84 | -5934.01
WO-00211 | Calibration – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 2652.36 | 0.5 | 6.2 | 7.6 | 0 | 14.3 | 2 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 45789.59 | WO-00206
WO-00212 | Cleaning – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 18374.25 | 6.1 | 2 | 2 | 5.7 | 15.8 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -16934.25
WO-00213 | Replacement – Instrument/Analyser INST-0163 | INST-0163 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 89820.11 | 53.7 | 16.7 | 20.2 | 5.2 | 95.8 | 12 | 0.93183 | 730 | 2 | 5 | 2 | 10 | HIGH | 1341.83 | -88478.28
WO-00214 | Calibration – Electrical Equipment ELEC-0014 | ELEC-0014 | Elec | Tank-Farm | Calibration | Low | FALSE | TRUE | INCLUDE | 570.86 | 0.2 | 8.2 | 14 | 0.5 | 22.9 | 3 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5975.81 | 5404.95
WO-00215 | Cleaning – Instrument/Analyser INST-0098 | INST-0098 | Inst | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 10507.52 | 13.9 | 1.2 | 1.5 | 6.5 | 23.1 | 3 | 0.96482 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.33 | -9118.19
WO-00216 | Calibration – Centrifugal Pump PMP-0032 | PMP-0032 | Pmp | Unit-300 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2174.74 | 1.7 | 2.5 | 16.1 | 0.5 | 20.8 | 3 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | HIGH | 9543.04 | 7368.3
WO-00217 | Calibration – Pressure Vessel VSL-0014 | VSL-0014 | Vsl | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2206.31 | 1 | 8.4 | 8.8 | 0.2 | 18.4 | 2 | 0.16034 | 2291.4951 | 5 | 3 | 5 | 15 | HIGH | 34874.61 | 32668.3
WO-00218 | Overhaul – Heat Exchanger HX-0009 | HX-0009 | Hx | Utilities | Overhaul | Critical | FALSE | FALSE | DEFER | 422121.16 | 209.1 | 38.3 | 15.3 | 11.3 | 274 | 34 | 0.41447 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48492.86 | -373628.3
WO-00219 | Calibration – Instrument/Analyser INST-0025 | INST-0025 | Inst | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 894.88 | 1.1 | 8.3 | 14.7 | 0.3 | 24.4 | 3 | 0.9248 | 730 | 2 | 5 | 2 | 10 | HIGH | 1331.72 | 436.84
WO-00220 | Cleaning – Heat Exchanger HX-0010 | HX-0010 | Hx | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 14187.23 | 6.3 | 1.7 | 1 | 5.8 | 14.8 | 2 | 0.41891 | 2190 | 4 | 4 | 4 | 16 | HIGH | 49012.24 | 34825.01
WO-00221 | Replacement – Instrument/Analyser INST-0025 | INST-0025 | Inst | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 43274.86 | 22.1 | 12.2 | 13.2 | 9 | 56.5 | 7 | 0.9248 | 730 | 2 | 5 | 2 | 10 | HIGH | 1331.72 | -41943.14
WO-00222 | Replacement – Control Valve VLV-0082 | VLV-0082 | Vlv | Tank-Farm | Replacement | High | FALSE | FALSE | DEFER | 16512.12 | 48.8 | 19.9 | 21.3 | 1.2 | 91.2 | 11 | 0.56312 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3021.85 | -13490.27
WO-00223 | Inspection – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Inspection | High | FALSE | TRUE | INCLUDE | 6673.77 | 6.7 | 1 | 3.2 | 0.3 | 11.2 | 1 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | 12327.01
WO-00224 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | Pmp | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 5380.49 | 7.9 | 1.3 | 2.3 | 0.8 | 12.3 | 2 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18327.69 | 12947.2
WO-00225 | Inspection – Instrument/Analyser INST-0021 | INST-0021 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 2044.07 | 7.1 | 0.6 | 1.5 | 0.2 | 9.4 | 1 | 0.91749 | 730 | 2 | 5 | 2 | 10 | HIGH | 1321.18 | -722.89
WO-00226 | Overhaul – Centrifugal Pump PMP-0050 | PMP-0050 | Pmp | Unit-200 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 370320.49 | 75.3 | 37.9 | 19.8 | 10.2 | 143.2 | 18 | 0.14641 | 1885.705 | 3 | 2 | 3 | 6 | MEDIUM | 3162.56 | -367157.93
WO-00227 | Calibration – Electrical Equipment ELEC-0061 | ELEC-0061 | Elec | Offsites | Calibration | Low | FALSE | TRUE | INCLUDE | 2887.48 | 1 | 2.3 | 8.2 | 0.2 | 11.7 | 1 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6951.19 | 4063.71
WO-00228 | Inspection – Instrument/Analyser INST-0180 | INST-0180 | Inst | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 7751.92 | 6.7 | 1 | 4.4 | 0 | 12.1 | 2 | 0.92781 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.05 | -6415.87
WO-00229 | Inspection – Instrument/Analyser INST-0149 | INST-0149 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 6821.76 | 6.2 | 0.1 | 4.3 | 0 | 10.6 | 1 | 0.79917 | 730 | 2 | 5 | 2 | 10 | HIGH | 1150.81 | -5670.95
WO-00230 | Calibration – Heat Exchanger HX-0028 | HX-0028 | Hx | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 1501.64 | 1.8 | 7.1 | 14 | 0.3 | 23.2 | 3 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | HIGH | 64199.97 | 62698.33
WO-00231 | Testing – Electrical Equipment ELEC-0023 | ELEC-0023 | Elec | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 2019.57 | 11.5 | 9.5 | 9.3 | 1.2 | 31.5 | 4 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1554.05 | -465.52 | WO-00197
WO-00232 | Calibration – Instrument/Analyser INST-0103 | INST-0103 | Inst | Unit-300 | Calibration | High | FALSE | FALSE | DEFER | 2632.64 | 0.6 | 5.7 | 4.1 | 0.7 | 11.1 | 1 | 0.96042 | 730 | 2 | 5 | 2 | 10 | HIGH | 1383.01 | -1249.63
WO-00233 | Cleaning – Control Valve VLV-0111 | VLV-0111 | Vlv | Offsites | Cleaning | Low | FALSE | FALSE | DEFER | 5063.21 | 23.7 | 1.6 | 1.8 | 2.4 | 29.5 | 4 | 0.54298 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2913.75 | -2149.46 | WO-00167
WO-00234 | Replacement – Centrifugal Pump PMP-0001 | PMP-0001 | Pmp | Offsites | Replacement | Critical | TRUE | TRUE | INCLUDE | 40584.87 | 21 | 6.8 | 15.1 | 3.2 | 46.1 | 6 | 0.85591 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18487.66 | -22097.21
WO-00235 | Cleaning – Instrument/Analyser INST-0037 | INST-0037 | Inst | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 21064.63 | 20.6 | 1.2 | 0.3 | 8.5 | 30.6 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -19624.63
WO-00236 | Replacement – Electrical Equipment ELEC-0023 | ELEC-0023 | Elec | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 11561.78 | 42.7 | 8.6 | 17 | 4.1 | 72.4 | 9 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1554.05 | -10007.73 | WO-00203
WO-00237 | Overhaul – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 41664.68 | 126 | 34.9 | 30.9 | 5.5 | 197.3 | 25 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | -23488.43
WO-00238 | Replacement – Centrifugal Pump PMP-0033 | PMP-0033 | Pmp | Offsites | Replacement | Critical | FALSE | TRUE | INCLUDE | 6660 | 16.1 | 11 | 10.2 | 7.2 | 44.5 | 6 | 0.80677 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17426.28 | 10766.28
WO-00239 | Calibration – Control Valve VLV-0106 | VLV-0106 | Vlv | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1002.14 | 1.2 | 8.4 | 10.2 | 0 | 19.8 | 2 | 0.64237 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3447.09 | 2444.95 | WO-00048
WO-00240 | Testing – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 14550.38 | 6 | 19.1 | 10.9 | 0.3 | 36.3 | 5 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -13164.82
WO-00241 | Overhaul – Instrument/Analyser INST-0003 | INST-0003 | Inst | Tank-Farm | Overhaul | Critical | FALSE | FALSE | DEFER | 330449.88 | 205.5 | 22.1 | 36 | 11.3 | 274.9 | 34 | 0.80391 | 730 | 2 | 5 | 2 | 10 | HIGH | 1157.63 | -329292.25
WO-00242 | Replacement – Pressure Vessel VSL-0013 | VSL-0013 | Vsl | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 114253.96 | 33.1 | 3.9 | 17.8 | 9.7 | 64.5 | 8 | 0.1682 | 2208.4953 | 5 | 3 | 5 | 15 | HIGH | 36583.08 | -77670.88
WO-00243 | Cleaning – Control Valve VLV-0026 | VLV-0026 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 10030.74 | 17.9 | 1.6 | 1.7 | 8.6 | 29.8 | 4 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3431.19 | -6599.55
WO-00244 | Inspection – Centrifugal Pump PMP-0038 | PMP-0038 | Pmp | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 4811.88 | 3.3 | 0.1 | 3 | 0.7 | 7.1 | 1 | 0.63144 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13639.2 | 8827.32
WO-00245 | Calibration – Centrifugal Pump PMP-0020 | PMP-0020 | Pmp | Unit-200 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2600.27 | 1.5 | 7.6 | 4.2 | 0.6 | 13.9 | 2 | 0.80713 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17433.92 | 14833.65
WO-00246 | Inspection – Centrifugal Pump PMP-0062 | PMP-0062 | Pmp | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 1757.45 | 8.6 | 1.5 | 4.8 | 1 | 15.9 | 2 | 0.61872 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13364.33 | 11606.88
WO-00247 | Inspection – Instrument/Analyser INST-0138 | INST-0138 | Inst | Utilities | Inspection | Low | FALSE | FALSE | DEFER | 7100.03 | 8.7 | 1.7 | 1.6 | 0.1 | 12.1 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5660.03
WO-00248 | Inspection – Electrical Equipment ELEC-0017 | ELEC-0017 | Elec | Unit-300 | Inspection | Low | FALSE | FALSE | DEFER | 3327.8 | 5.6 | 0.2 | 1.1 | 1 | 7.9 | 1 | 0.25422 | 1541.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2287.96 | -1039.84
WO-00249 | Repair – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Repair | Medium | FALSE | TRUE | INCLUDE | 24195.92 | 28.2 | 15.1 | 10.2 | 1.1 | 54.6 | 7 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 56360.29
WO-00250 | Testing – Centrifugal Pump PMP-0049 | PMP-0049 | Pmp | Unit-100 | Testing | High | FALSE | TRUE | INCLUDE | 8166.02 | 9 | 11.9 | 5.9 | 0.5 | 27.3 | 3 | 0.88977 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19218.98 | 11052.96
WO-00251 | Overhaul – Pressure Vessel VSL-0006 | VSL-0006 | Vsl | Unit-300 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 333845.33 | 209.8 | 17.5 | 9.2 | 4.8 | 241.3 | 30 | 0.43349 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 94283.4 | -239561.93
WO-00252 | Cleaning – Piping/Pipeline Segment PPL-0037 | PPL-0037 | Ppl | Tank-Farm | Cleaning | High | FALSE | FALSE | DEFER | 20396.44 | 25.3 | 1.3 | 0.8 | 3.2 | 30.6 | 4 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | HIGH | 13521.8 | -6874.64
WO-00253 | Replacement – Control Valve VLV-0023 | VLV-0023 | Vlv | Flare-System | Replacement | Low | FALSE | FALSE | DEFER | 105052.98 | 33.3 | 6.1 | 9.8 | 2.2 | 51.4 | 6 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3196.58 | -101856.4
WO-00254 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 695.06 | 3.5 | 1.6 | 3.1 | 0.6 | 8.8 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 744.94
WO-00255 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | Inst | Flare-System | Inspection | Critical | FALSE | FALSE | DEFER | 6935.57 | 3.5 | 0.1 | 3.3 | 0.1 | 7 | 1 | 0.94369 | 730 | 2 | 5 | 2 | 10 | HIGH | 1358.91 | -5576.66
WO-00256 | Calibration – Control Valve VLV-0073 | VLV-0073 | Vlv | Offsites | Calibration | High | FALSE | TRUE | INCLUDE | 1576.51 | 0.5 | 4.8 | 15.7 | 0.1 | 21.1 | 3 | 0.48307 | 183.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2592.27 | 1015.76
WO-00257 | Cleaning – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 15567.32 | 27.3 | 0.7 | 0.1 | 6.3 | 34.4 | 4 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | -8709.46
WO-00258 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Inspection | Low | FALSE | FALSE | DEFER | 4691.18 | 3.6 | 1.7 | 4.3 | 0.4 | 10 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3251.18
WO-00259 | Testing – Instrument/Analyser INST-0003 | INST-0003 | Inst | Tank-Farm | Testing | High | FALSE | FALSE | DEFER | 2374.14 | 8.6 | 16 | 5.7 | 0.8 | 31.1 | 4 | 0.80391 | 730 | 2 | 5 | 2 | 10 | HIGH | 1157.63 | -1216.51
WO-00260 | Testing – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Testing | Critical | FALSE | FALSE | DEFER | 6467.99 | 15.7 | 11.7 | 6.6 | 1.7 | 35.7 | 4 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -5090.17
WO-00261 | Inspection – Instrument/Analyser INST-0069 | INST-0069 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 3296.44 | 7.5 | 0.7 | 1.3 | 0.3 | 9.8 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1856.44
WO-00262 | Inspection – Centrifugal Pump PMP-0034 | PMP-0034 | Pmp | Unit-100 | Inspection | Critical | FALSE | TRUE | INCLUDE | 4557.53 | 2.9 | 0.6 | 3.6 | 0.7 | 7.8 | 1 | 0.32905 | 1161.7051 | 3 | 3 | 3 | 9 | MEDIUM | 7107.46 | 2549.93
WO-00263 | Replacement – Centrifugal Pump PMP-0004 | PMP-0004 | Pmp | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 33394.56 | 57.8 | 5.4 | 7.7 | 5 | 75.9 | 9 | 0.9286 | 1825 | 3 | 5 | 3 | 15 | HIGH | 20057.78 | -13336.78
WO-00264 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Inspection | Critical | FALSE | TRUE | INCLUDE | 1309.51 | 7.1 | 1.2 | 3.6 | 0.8 | 12.7 | 2 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 37489.01
WO-00265 | Repair – Storage Tank TNK-0008 | TNK-0008 | Tnk | Offsites | Repair | High | FALSE | FALSE | DEFER | 59189.96 | 82 | 22.7 | 8.5 | 3.5 | 116.7 | 15 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | LOW | 1543.9 | -57646.06
WO-00266 | Inspection – Centrifugal Pump PMP-0023 | PMP-0023 | Pmp | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3939.48 | 2.3 | 0 | 4.7 | 0.7 | 7.7 | 1 | 0.53872 | 289.705 | 3 | 4 | 3 | 12 | HIGH | 11636.29 | 7696.81
WO-00267 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Replacement | Critical | TRUE | TRUE | INCLUDE | 70611.87 | 54.4 | 13.7 | 16 | 5.1 | 89.2 | 11 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | -55051.1
WO-00268 | Calibration – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Calibration | Low | FALSE | FALSE | DEFER | 2946.75 | 0.8 | 5.1 | 10.8 | 0.4 | 17.1 | 2 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | -1917.89
WO-00269 | Calibration – Pressure Vessel VSL-0028 | VSL-0028 | Vsl | Flare-System | Calibration | Medium | FALSE | TRUE | INCLUDE | 1205.72 | 0.7 | 5.4 | 4.6 | 0.5 | 11.2 | 1 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | HIGH | 58882.1 | 57676.38
WO-00270 | Cleaning – Control Valve VLV-0011 | VLV-0011 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 5762.1 | 21.5 | 1.4 | 0.5 | 7 | 30.4 | 4 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3379.15 | -2382.95
WO-00271 | Repair – Reciprocating Compressor CMP-0015 | CMP-0015 | Cmp | Tank-Farm | Repair | Medium | FALSE | TRUE | INCLUDE | 12613.64 | 25.9 | 16.6 | 2.8 | 4.7 | 50 | 6 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 162580.25 | 149966.61
WO-00272 | Inspection – Instrument/Analyser INST-0122 | INST-0122 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 4003.62 | 9.9 | 1 | 3 | 0.6 | 14.5 | 2 | 0.94066 | 730 | 2 | 5 | 2 | 10 | HIGH | 1354.54 | -2649.08
WO-00273 | Inspection – Instrument/Analyser INST-0034 | INST-0034 | Inst | Offsites | Inspection | Critical | FALSE | FALSE | DEFER | 5612.42 | 5.2 | 0.6 | 1.1 | 0.8 | 7.7 | 1 | 0.95536 | 730 | 2 | 5 | 2 | 10 | HIGH | 1375.72 | -4236.7
WO-00274 | Calibration – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Calibration | Medium | FALSE | FALSE | DEFER | 1269.57 | 1.2 | 4 | 6.5 | 0.5 | 12.2 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 170.43
WO-00275 | Inspection – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 3829.06 | 5.6 | 0.4 | 3.3 | 0.1 | 9.4 | 1 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | -354.65
WO-00276 | Inspection – Instrument/Analyser INST-0035 | INST-0035 | Inst | Offsites | Inspection | Medium | FALSE | FALSE | DEFER | 4193.01 | 4.5 | 0.9 | 2.7 | 0.9 | 9 | 1 | 0.96694 | 730 | 2 | 5 | 2 | 10 | HIGH | 1392.4 | -2800.61
WO-00277 | Calibration – Electrical Equipment ELEC-0063 | ELEC-0063 | Elec | Flare-System | Calibration | Low | FALSE | TRUE | INCLUDE | 831.83 | 0.7 | 2.6 | 10.7 | 0.7 | 14.7 | 2 | 0.70669 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6360.25 | 5528.42
WO-00278 | Cleaning – Control Valve VLV-0065 | VLV-0065 | Vlv | Flare-System | Cleaning | Critical | TRUE | TRUE | INCLUDE | 16361.74 | 8.3 | 0.1 | 1.6 | 3.3 | 13.3 | 2 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3625.6 | -12736.14
WO-00279 | Testing – Control Valve VLV-0114 | VLV-0114 | Vlv | Tank-Farm | Testing | Medium | FALSE | FALSE | DEFER | 14471.06 | 13.1 | 11.6 | 20.7 | 0.4 | 45.8 | 6 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3549.3 | -10921.76
WO-00280 | Replacement – Heat Exchanger HX-0023 | HX-0023 | Hx | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 109960.5 | 55.8 | 13.7 | 6.2 | 5.3 | 81 | 10 | 0.40204 | 127.1654 | 4 | 4 | 4 | 16 | HIGH | 47038.68 | -62921.82
WO-00281 | Repair – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Repair | Critical | TRUE | TRUE | INCLUDE | 12795.42 | 13 | 22.3 | 10.2 | 8.5 | 54 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -11355.42
WO-00282 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Calibration | Critical | TRUE | TRUE | INCLUDE | 304.54 | 0.1 | 5.7 | 7.5 | 0.6 | 13.9 | 2 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | 17871.71
WO-00283 | Inspection – Control Valve VLV-0023 | VLV-0023 | Vlv | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 5980.9 | 3.7 | 1.3 | 4 | 0.1 | 9.1 | 1 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3196.58 | -2784.32
WO-00284 | Replacement – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 49797.79 | 12.5 | 17.1 | 15.2 | 5.5 | 50.3 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -48357.79
WO-00285 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 107439.62 | 45.4 | 18.7 | 22.2 | 9.9 | 96.2 | 12 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | -88438.84
WO-00286 | Calibration – Piping/Pipeline Segment PPL-0039 | PPL-0039 | Ppl | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2452.58 | 1.3 | 4.2 | 19.4 | 0.2 | 25.1 | 3 | 0.089837 | 3775.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 4328.35 | 1875.77
WO-00287 | Cleaning – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 4883.9 | 21.3 | 0.2 | 1.4 | 8.8 | 31.7 | 4 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | -1935.66
WO-00288 | Calibration – Control Valve VLV-0116 | VLV-0116 | Vlv | Utilities | Calibration | Medium | FALSE | TRUE | INCLUDE | 638.97 | 1.7 | 9.6 | 6.4 | 0.7 | 18.4 | 2 | 0.52354 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2809.43 | 2170.46
WO-00289 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Cleaning | Low | FALSE | FALSE | DEFER | 17955.75 | 15.7 | 1.2 | 0.5 | 5 | 22.4 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -16515.75
WO-00290 | Inspection – Instrument/Analyser INST-0106 | INST-0106 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 5022.06 | 3.5 | 1.7 | 3.3 | 0.4 | 8.9 | 1 | 0.96519 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.87 | -3632.19
WO-00291 | Overhaul – Distillation Tower TWR-0006 | TWR-0006 | Twr | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 575203.21 | 141.8 | 27.7 | 39.3 | 11.6 | 220.4 | 28 | 0.38082 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 279904.94 | -295298.27
WO-00292 | Replacement – Electrical Equipment ELEC-0078 | ELEC-0078 | Elec | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 22355.77 | 45.1 | 17.7 | 22.1 | 8.9 | 93.8 | 12 | 0.19668 | 1758.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 1770.15 | -20585.62
WO-00293 | Replacement – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 78361.23 | 57.6 | 15.1 | 13.9 | 7.2 | 93.8 | 12 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | -68945.19
WO-00294 | Repair – Reciprocating Compressor CMP-0010 | CMP-0010 | Cmp | Flare-System | Repair | Low | FALSE | TRUE | INCLUDE | 61530.83 | 47.9 | 11.1 | 11 | 4 | 74 | 9 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 307515.33 | 245984.5
WO-00295 | Overhaul – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Overhaul | Low | FALSE | FALSE | DEFER | 291152.96 | 109.6 | 34.9 | 29.8 | 6.6 | 180.9 | 23 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -289912.59
WO-00296 | Replacement – Control Valve VLV-0055 | VLV-0055 | Vlv | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 54746.52 | 18.7 | 12 | 18 | 8.9 | 57.6 | 7 | 0.44001 | 617.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2361.21 | -52385.31
WO-00297 | Testing – Piping/Pipeline Segment PPL-0043 | PPL-0043 | Ppl | Tank-Farm | Testing | Critical | FALSE | FALSE | DEFER | 10705.36 | 7.1 | 8.1 | 9.9 | 1.8 | 26.9 | 3 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6265.83 | -4439.53
WO-00298 | Overhaul – Control Valve VLV-0025 | VLV-0025 | Vlv | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 427856.76 | 214.4 | 35.7 | 39.6 | 7.5 | 297.2 | 37 | 0.55892 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2999.3 | -424857.46
WO-00299 | Replacement – Control Valve VLV-0051 | VLV-0051 | Vlv | Offsites | Replacement | High | FALSE | FALSE | DEFER | 19763.49 | 58.8 | 5.6 | 6.7 | 6.6 | 77.7 | 10 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2866.96 | -16896.53
WO-00300 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Inspection | Low | FALSE | FALSE | DEFER | 5048.3 | 8.1 | 1.6 | 1.6 | 0.6 | 11.9 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3608.3
WO-00301 | Inspection – Electrical Equipment ELEC-0019 | ELEC-0019 | Elec | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 2136.85 | 2 | 1 | 1.8 | 0.7 | 5.5 | 1 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4601.34 | 2464.49
WO-00302 | Replacement – Heat Exchanger HX-0001 | HX-0001 | Hx | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 79646.16 | 19 | 2.3 | 19.2 | 4.9 | 45.4 | 6 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48649.09 | -30997.07
WO-00303 | Cleaning – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 4779.59 | 14.8 | 0.4 | 1.8 | 7.5 | 24.5 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3339.59
WO-00304 | Cleaning – Control Valve VLV-0083 | VLV-0083 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 17067.52 | 22.8 | 0.2 | 0 | 2.9 | 25.9 | 3 | 0.57925 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3108.4 | -13959.12
WO-00305 | Overhaul – Instrument/Analyser INST-0089 | INST-0089 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 94830.05 | 122.2 | 26.5 | 12.6 | 22.3 | 183.6 | 23 | 0.939 | 730 | 2 | 5 | 2 | 10 | HIGH | 1352.17 | -93477.88
WO-00306 | Replacement – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Replacement | Low | FALSE | FALSE | DEFER | 63294.33 | 24.3 | 17.4 | 15.5 | 5.5 | 62.7 | 8 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -61854.33
WO-00307 | Repair – Piping/Pipeline Segment PPL-0037 | PPL-0037 | Ppl | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 65398.55 | 28.8 | 8 | 14.4 | 5.2 | 56.4 | 7 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | HIGH | 13521.8 | -51876.75
WO-00308 | Calibration – Piping/Pipeline Segment PPL-0004 | PPL-0004 | Ppl | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1026.88 | 0.6 | 5.9 | 8.4 | 0.7 | 15.6 | 2 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | HIGH | 15082.22 | 14055.34
WO-00309 | Overhaul – Instrument/Analyser INST-0115 | INST-0115 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 438422.86 | 142.1 | 37.9 | 17.4 | 18.8 | 216.2 | 27 | 0.96766 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.43 | -437029.43 | WO-00188
WO-00310 | Replacement – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 68936.66 | 52.5 | 6.5 | 18.7 | 9.6 | 87.3 | 11 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | -67907.8
WO-00311 | Overhaul – Storage Tank TNK-0002 | TNK-0002 | Tnk | Unit-300 | Overhaul | Medium | FALSE | FALSE | DEFER | 370216.52 | 238.4 | 31.9 | 12.8 | 4.9 | 288 | 36 | 0.058188 | 3954.2322 | 4 | 2 | 4 | 8 | MEDIUM | 13615.91 | -356600.61
WO-00312 | Overhaul – Heat Exchanger HX-0035 | HX-0035 | Hx | Flare-System | Overhaul | Medium | FALSE | FALSE | DEFER | 159385.54 | 109.5 | 39.8 | 27.5 | 21.4 | 198.2 | 25 | 0.38356 | 327.1654 | 4 | 4 | 4 | 16 | HIGH | 44876.21 | -114509.33
WO-00313 | Testing – Instrument/Analyser INST-0160 | INST-0160 | Inst | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 13383.3 | 6.6 | 17.2 | 4.4 | 2 | 30.2 | 4 | 0.74551 | 109.2559 | 2 | 5 | 2 | 10 | HIGH | 1073.53 | -12309.77
WO-00314 | Cleaning – Electrical Equipment ELEC-0009 | ELEC-0009 | Elec | Utilities | Cleaning | Medium | FALSE | FALSE | DEFER | 21379.69 | 7.9 | 1.7 | 0 | 5.5 | 15.1 | 2 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1991.99 | -19387.7
WO-00315 | Replacement – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 72434.25 | 55.6 | 7.9 | 15.6 | 8.9 | 88 | 11 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | -55777.66
WO-00316 | Inspection – Electrical Equipment ELEC-0077 | ELEC-0077 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 7576.65 | 2.4 | 1.2 | 3.3 | 0.8 | 7.7 | 1 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7273.03 | -303.62
WO-00317 | Inspection – Instrument/Analyser INST-0143 | INST-0143 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 6165.59 | 3.2 | 0.9 | 3.9 | 0.7 | 8.7 | 1 | 0.83804 | 730 | 2 | 5 | 2 | 10 | HIGH | 1206.78 | -4958.81 | WO-00231
WO-00318 | Replacement – Control Valve VLV-0084 | VLV-0084 | Vlv | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 116432.11 | 31.3 | 2.8 | 8.4 | 4.1 | 46.6 | 6 | 0.6521 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3499.35 | -112932.76
WO-00319 | Replacement – Instrument/Analyser INST-0009 | INST-0009 | Inst | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 8035.52 | 34.7 | 3.5 | 9.5 | 9.9 | 57.6 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -6595.52
WO-00320 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 3920.28 | 3.4 | 0.2 | 3.3 | 0.5 | 7.4 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -2480.28
WO-00321 | Repair – Storage Tank TNK-0015 | TNK-0015 | Tnk | Unit-300 | Repair | Critical | TRUE | TRUE | INCLUDE | 21241.18 | 92.9 | 17.5 | 6.7 | 8.6 | 125.7 | 16 | 0.031924 | 4647.2321 | 4 | 1 | 4 | 4 | LOW | 7470.16 | -13771.02
WO-00322 | Cleaning – Piping/Pipeline Segment PPL-0026 | PPL-0026 | Ppl | Flare-System | Cleaning | Critical | FALSE | FALSE | DEFER | 18318.92 | 10.7 | 1.7 | 0.5 | 8.7 | 21.6 | 3 | 0.23093 | 1285.7481 | 3.65 | 3 | 4 | 12 | HIGH | 11126.23 | -7192.69
WO-00323 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 3419.29 | 8.8 | 0.3 | 4.5 | 0.2 | 13.8 | 2 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | 2358.72
WO-00324 | Replacement – Instrument/Analyser INST-0114 | INST-0114 | Inst | Offsites | Replacement | Medium | FALSE | FALSE | DEFER | 18584.52 | 57.1 | 9.9 | 17.8 | 6.2 | 91 | 11 | 0.92825 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.68 | -17247.84
WO-00325 | Cleaning – Centrifugal Pump PMP-0065 | PMP-0065 | Pmp | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 22560.22 | 20.8 | 1.1 | 1.3 | 6.9 | 30.1 | 4 | 0.5288 | 334.705 | 3 | 4 | 3 | 12 | HIGH | 11421.98 | -11138.24
WO-00326 | Cleaning – Storage Tank TNK-0012 | TNK-0012 | Tnk | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 11645.68 | 22.2 | 1.9 | 1.9 | 8.6 | 34.6 | 4 | 0.011334 | 5499.2321 | 4 | 1 | 4 | 4 | LOW | 2652.22 | -8993.46
WO-00327 | Calibration – Heat Exchanger HX-0004 | HX-0004 | Hx | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 698.54 | 1 | 4.1 | 4.1 | 1 | 10.2 | 1 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | HIGH | 43691.97 | 42993.43
WO-00328 | Overhaul – Heat Exchanger HX-0024 | HX-0024 | Hx | Unit-100 | Overhaul | Critical | FALSE | FALSE | DEFER | 163679.09 | 178.6 | 26.3 | 41.7 | 24 | 270.6 | 34 | 0.45456 | 2190 | 4 | 4 | 4 | 16 | HIGH | 53183.64 | -110495.45
WO-00329 | Replacement – Centrifugal Pump PMP-0044 | PMP-0044 | Pmp | Offsites | Replacement | Critical | FALSE | FALSE | DEFER | 35748.99 | 12.9 | 9.1 | 4.3 | 2 | 28.3 | 4 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15461.89 | -20287.1 | WO-00317
WO-00330 | Inspection – Piping/Pipeline Segment PPL-0013 | PPL-0013 | Ppl | Unit-300 | Inspection | Critical | FALSE | TRUE | INCLUDE | 6017.98 | 2.8 | 1.7 | 1.9 | 0.1 | 6.5 | 1 | 0.15413 | 2692.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7426.16 | 1408.18
WO-00331 | Calibration – Instrument/Analyser INST-0015 | INST-0015 | Inst | Offsites | Calibration | Medium | FALSE | FALSE | DEFER | 918.53 | 1 | 2.9 | 19.8 | 0.1 | 23.8 | 3 | 0.7576 | 54.2559 | 2 | 5 | 2 | 10 | HIGH | 1090.94 | 172.41
WO-00332 | Repair – Control Valve VLV-0015 | VLV-0015 | Vlv | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 21101.18 | 32.6 | 25 | 6.9 | 1 | 65.5 | 8 | 0.56546 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3034.38 | -18066.8
WO-00333 | Inspection – Centrifugal Pump PMP-0051 | PMP-0051 | Pmp | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 7332.46 | 7.1 | 1.2 | 1.8 | 0.7 | 10.8 | 1 | 0.43309 | 745.705 | 3 | 4 | 3 | 12 | HIGH | 9354.8 | 2022.34
WO-00334 | Inspection – Pressure Vessel VSL-0004 | VSL-0004 | Vsl | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 7118.26 | 6.6 | 1.6 | 2.1 | 0.1 | 10.4 | 1 | 0.12966 | 2628.4951 | 5 | 2 | 5 | 10 | HIGH | 28201.02 | 21082.76
WO-00335 | Calibration – Instrument/Analyser INST-0158 | INST-0158 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1280.89 | 0 | 8.5 | 7.3 | 0.3 | 16.1 | 2 | 0.91367 | 730 | 2 | 5 | 2 | 10 | HIGH | 1315.69 | 34.8
WO-00336 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | Ppl | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 1132.77 | 2.2 | 1.8 | 2.2 | 0.7 | 6.9 | 1 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12169.06 | 11036.29 | WO-00205
WO-00337 | Cleaning – Instrument/Analyser INST-0052 | INST-0052 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 13602.28 | 16.5 | 0.8 | 1.2 | 9.7 | 28.2 | 4 | 0.88183 | 730 | 2 | 5 | 2 | 10 | HIGH | 1269.84 | -12332.44
WO-00338 | Overhaul – Instrument/Analyser INST-0086 | INST-0086 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 209480.22 | 216.7 | 13.7 | 43.7 | 9.1 | 283.2 | 35 | 0.63543 | 499.2559 | 2 | 5 | 2 | 10 | HIGH | 915.02 | -208565.2
WO-00339 | Calibration – Electrical Equipment ELEC-0048 | ELEC-0048 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1535.59 | 0.4 | 8.8 | 9.9 | 0.3 | 19.4 | 2 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4217.99 | 2682.4
WO-00340 | Overhaul – Storage Tank TNK-0004 | TNK-0004 | Tnk | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 414585.55 | 67.4 | 26.3 | 45.5 | 4.7 | 143.9 | 18 | 0.059482 | 3925.2322 | 4 | 2 | 4 | 8 | MEDIUM | 13918.82 | -400666.73
WO-00341 | Cleaning – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Cleaning | Low | FALSE | FALSE | DEFER | 22305.07 | 18.3 | 1.6 | 0.4 | 4.8 | 25.1 | 3 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | -18830.66
WO-00342 | Repair – Piping/Pipeline Segment PPL-0040 | PPL-0040 | Ppl | Unit-200 | Repair | Medium | FALSE | FALSE | DEFER | 45520.33 | 51.7 | 15.7 | 3.1 | 9 | 79.5 | 10 | 0.088296 | 3800.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4254.12 | -41266.21
WO-00343 | Overhaul – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 178472.38 | 108.6 | 13.2 | 38.3 | 15.1 | 175.2 | 22 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -177144.68
WO-00344 | Cleaning – Piping/Pipeline Segment PPL-0002 | PPL-0002 | Ppl | Unit-100 | Cleaning | High | FALSE | FALSE | DEFER | 24501.53 | 6.9 | 0.9 | 1 | 3.3 | 12.1 | 2 | 0.10207 | 3575.748 | 3.65 | 2 | 4 | 8 | MEDIUM | 4917.64 | -19583.89
WO-00345 | Cleaning – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 4776.27 | 7.7 | 1.7 | 0.6 | 7 | 17 | 2 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | 8796.86
WO-00346 | Repair – Centrifugal Pump PMP-0061 | PMP-0061 | Pmp | Utilities | Repair | Critical | TRUE | TRUE | INCLUDE | 59711.78 | 85.3 | 20.3 | 10.1 | 4.5 | 120.2 | 15 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | MEDIUM | 5761.08 | -53950.7
WO-00347 | Overhaul – Electrical Equipment ELEC-0079 | ELEC-0079 | Elec | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 90645.91 | 124.8 | 24.4 | 9.5 | 9.5 | 168.2 | 21 | 0.44675 | 669.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4020.78 | -86625.13
WO-00348 | Cleaning – Instrument/Analyser INST-0127 | INST-0127 | Inst | Utilities | Cleaning | Low | FALSE | FALSE | DEFER | 20348.02 | 17 | 1.7 | 1.6 | 2.8 | 23.1 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -18908.02
WO-00349 | Inspection – Heat Exchanger HX-0030 | HX-0030 | Hx | Unit-100 | Inspection | Critical | TRUE | TRUE | INCLUDE | 5016.6 | 8.3 | 0.7 | 3.4 | 0.4 | 12.8 | 2 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | HIGH | 47081.26 | 42064.66
WO-00350 | Inspection – Electrical Equipment ELEC-0085 | ELEC-0085 | Elec | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 1301.98 | 2.8 | 1.2 | 3.1 | 0.5 | 7.6 | 1 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7020.85 | 5718.87
WO-00351 | Inspection – Centrifugal Pump PMP-0064 | PMP-0064 | Pmp | Unit-300 | Inspection | Medium | FALSE | TRUE | INCLUDE | 2605.28 | 8.2 | 1.8 | 2.8 | 0.1 | 12.9 | 2 | 0.77315 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16700.13 | 14094.85
WO-00352 | Repair – Instrument/Analyser INST-0133 | INST-0133 | Inst | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 34265.5 | 30.4 | 5.1 | 12.6 | 9.2 | 57.3 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -32825.5 | WO-00004
WO-00353 | Replacement – Reciprocating Compressor CMP-0013 | CMP-0013 | Cmp | Flare-System | Replacement | Critical | FALSE | TRUE | INCLUDE | 78932.16 | 51.3 | 10.6 | 20.4 | 4.5 | 86.8 | 11 | 0.67268 | 331.9307 | 4.75 | 5 | 5 | 25 | CRITICAL | 234850.27 | 155918.11
WO-00354 | Cleaning – Centrifugal Pump PMP-0044 | PMP-0044 | Pmp | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 12152.47 | 27.5 | 1 | 0.8 | 5.2 | 34.5 | 4 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15461.89 | 3309.42
WO-00355 | Replacement – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 88134.26 | 27.8 | 8.9 | 16.3 | 1.5 | 54.5 | 7 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | -82356.25
WO-00356 | Overhaul – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Overhaul | High | FALSE | FALSE | DEFER | 280020.28 | 183.9 | 39.8 | 43.5 | 11.5 | 278.7 | 35 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | -274636.43
WO-00357 | Calibration – Centrifugal Pump PMP-0066 | PMP-0066 | Pmp | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 1829.05 | 1.3 | 6.4 | 16.4 | 0.2 | 24.3 | 3 | 0.22202 | 1579.705 | 3 | 3 | 3 | 9 | MEDIUM | 4795.66 | 2966.61
WO-00358 | Inspection – Centrifugal Pump PMP-0059 | PMP-0059 | Pmp | Tank-Farm | Inspection | Medium | FALSE | FALSE | DEFER | 3613.66 | 7.3 | 1 | 2.5 | 0.9 | 11.7 | 1 | 0.6343 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13700.81 | 10087.15 | WO-00090
WO-00359 | Cleaning – Instrument/Analyser INST-0090 | INST-0090 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 23801.28 | 14.2 | 1.6 | 0.3 | 4.3 | 20.4 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -22361.28
WO-00360 | Inspection – Centrifugal Pump PMP-0018 | PMP-0018 | Pmp | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 4313.36 | 3.5 | 1.3 | 1.8 | 0.1 | 6.7 | 1 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13798.72 | 9485.36 | WO-00096
WO-00361 | Cleaning – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 23474.82 | 15.8 | 0.1 | 1.1 | 6.5 | 23.5 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -22034.82
WO-00362 | Repair – Storage Tank TNK-0013 | TNK-0013 | Tnk | Flare-System | Repair | Low | FALSE | FALSE | DEFER | 50357.71 | 76.5 | 16.8 | 13.1 | 3.3 | 109.7 | 14 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | LOW | 11354.04 | -39003.67
WO-00363 | Overhaul – Instrument/Analyser INST-0175 | INST-0175 | Inst | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 109961.07 | 51.2 | 34.7 | 49.3 | 21.9 | 157.1 | 20 | 0.88589 | 730 | 2 | 5 | 2 | 10 | HIGH | 1275.68 | -108685.39
WO-00364 | Testing – Control Valve VLV-0011 | VLV-0011 | Vlv | Tank-Farm | Testing | Medium | FALSE | FALSE | DEFER | 10981.01 | 8.1 | 16 | 5.6 | 0.4 | 30.1 | 4 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3379.15 | -7601.86
WO-00365 | Replacement – Reciprocating Compressor CMP-0004 | CMP-0004 | Cmp | Unit-200 | Replacement | Critical | FALSE | TRUE | INCLUDE | 114652.62 | 59.8 | 8.7 | 18.2 | 4.7 | 91.4 | 11 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 234472.38
WO-00366 | Replacement – Instrument/Analyser INST-0132 | INST-0132 | Inst | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 31837.75 | 25.1 | 5.9 | 6.2 | 3 | 40.2 | 5 | 0.97003 | 730 | 2 | 5 | 2 | 10 | HIGH | 1396.84 | -30440.91
WO-00367 | Inspection – Centrifugal Pump PMP-0039 | PMP-0039 | Pmp | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3003.2 | 6.2 | 0.7 | 3.1 | 0 | 10 | 1 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15725.17 | 12721.97
WO-00368 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 17343.19 | 17.6 | 0.9 | 0.7 | 3.8 | 23 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -15903.19
WO-00369 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 3028.98 | 7.4 | 0.2 | 1.3 | 0.7 | 9.6 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 86412.66
WO-00370 | Calibration – Instrument/Analyser INST-0171 | INST-0171 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 2824.47 | 1.9 | 5.4 | 8.2 | 0.6 | 16.1 | 2 | 0.94889 | 730 | 2 | 5 | 2 | 10 | HIGH | 1366.41 | -1458.06
WO-00371 | Cleaning – Reciprocating Compressor CMP-0012 | CMP-0012 | Cmp | Unit-100 | Cleaning | Low | FALSE | TRUE | INCLUDE | 8722.69 | 5.5 | 0.4 | 0.3 | 3 | 9.2 | 1 | 0.71599 | 221.9307 | 4.75 | 5 | 5 | 25 | CRITICAL | 249970.39 | 241247.7
WO-00372 | Inspection – Electrical Equipment ELEC-0002 | ELEC-0002 | Elec | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 5053.75 | 9.6 | 0.7 | 3.1 | 0.7 | 14.1 | 2 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6708.41 | 1654.66 | WO-00073
WO-00373 | Overhaul – Instrument/Analyser INST-0143 | INST-0143 | Inst | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 493005.17 | 189.1 | 42 | 49.5 | 11.4 | 292 | 36 | 0.83804 | 730 | 2 | 5 | 2 | 10 | HIGH | 1206.78 | -491798.39
WO-00374 | Cleaning – Control Valve VLV-0016 | VLV-0016 | Vlv | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 16998.51 | 21.8 | 1.5 | 1.8 | 4.8 | 29.9 | 4 | 0.61237 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3286.11 | -13712.4 | WO-00257
WO-00375 | Replacement – Control Valve VLV-0090 | VLV-0090 | Vlv | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 73375.4 | 47.1 | 16.2 | 12.4 | 5.6 | 81.3 | 10 | 0.65442 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3511.79 | -69863.61
WO-00376 | Inspection – Centrifugal Pump PMP-0042 | PMP-0042 | Pmp | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 2527.83 | 9.3 | 0.6 | 4.9 | 0.2 | 15 | 2 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15665.17 | 13137.34
WO-00377 | Cleaning – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 17724.88 | 19.5 | 1.4 | 1.8 | 6.5 | 29.2 | 4 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 71716.76
WO-00378 | Replacement – Control Valve VLV-0030 | VLV-0030 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 86445.18 | 33.7 | 11.9 | 15.9 | 4.4 | 65.9 | 8 | 0.57791 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3101.23 | -83343.95
WO-00379 | Calibration – Centrifugal Pump PMP-0071 | PMP-0071 | Pmp | Tank-Farm | Calibration | Critical | FALSE | TRUE | INCLUDE | 2200.04 | 1.4 | 9.1 | 13.5 | 1 | 25 | 3 | 0.82667 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17856.16 | 15656.12
WO-00380 | Cleaning – Instrument/Analyser INST-0056 | INST-0056 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 18206.24 | 15.5 | 0.6 | 1.1 | 4.9 | 22.1 | 3 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | HIGH | 1103.88 | -17102.36
WO-00381 | Replacement – Instrument/Analyser INST-0061 | INST-0061 | Inst | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 25206.3 | 38 | 9.1 | 5.9 | 6.1 | 59.1 | 7 | 0.97132 | 730 | 2 | 5 | 2 | 10 | HIGH | 1398.7 | -23807.6
WO-00382 | Inspection – Centrifugal Pump PMP-0054 | PMP-0054 | Pmp | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 5022.52 | 6.5 | 1.5 | 2.4 | 0.2 | 10.6 | 1 | 0.79554 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17183.71 | 12161.19
WO-00383 | Cleaning – Reciprocating Compressor CMP-0001 | CMP-0001 | Cmp | Unit-200 | Cleaning | Low | FALSE | TRUE | INCLUDE | 1651.36 | 23.7 | 0.4 | 1.6 | 7.6 | 33.3 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 347473.64
WO-00384 | Testing – Centrifugal Pump PMP-0052 | PMP-0052 | Pmp | Unit-300 | Testing | Critical | FALSE | TRUE | INCLUDE | 4478.95 | 15.8 | 10.3 | 16.6 | 1.2 | 43.9 | 5 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17151.61 | 12672.66
WO-00385 | Inspection – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 1027.45 | 3 | 0.5 | 4.6 | 0.5 | 8.6 | 1 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | 1.41
WO-00386 | Repair – Control Valve VLV-0078 | VLV-0078 | Vlv | Utilities | Repair | Low | FALSE | FALSE | DEFER | 59325.56 | 44 | 26.5 | 15.4 | 7.7 | 93.6 | 12 | 0.50925 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2732.74 | -56592.82
WO-00387 | Cleaning – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Cleaning | Critical | TRUE | TRUE | INCLUDE | 13685.79 | 25.4 | 0.9 | 1.6 | 2.4 | 30.3 | 4 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | 1874.98
WO-00388 | Cleaning – Reciprocating Compressor CMP-0005 | CMP-0005 | Cmp | Flare-System | Cleaning | Low | FALSE | TRUE | INCLUDE | 2766.69 | 27.4 | 0 | 1.4 | 3.9 | 32.7 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 346358.31
WO-00389 | Replacement – Piping/Pipeline Segment PPL-0030 | PPL-0030 | Ppl | Tank-Farm | Replacement | Critical | FALSE | TRUE | INCLUDE | 8137.59 | 9.4 | 12 | 23.7 | 9.8 | 54.9 | 7 | 0.28825 | 140.7483 | 3.65 | 3 | 4 | 12 | HIGH | 13887.95 | 5750.36
WO-00390 | Overhaul – Control Valve VLV-0027 | VLV-0027 | Vlv | Unit-100 | Overhaul | Low | FALSE | FALSE | DEFER | 73766.65 | 144.4 | 33.2 | 18.5 | 16.2 | 212.3 | 27 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | HIGH | 2116.63 | -71650.02
WO-00391 | Inspection – Instrument/Analyser INST-0134 | INST-0134 | Inst | Tank-Farm | Inspection | High | FALSE | FALSE | DEFER | 2294.11 | 3.7 | 0.2 | 1.7 | 0.6 | 6.2 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -854.11
WO-00392 | Calibration – Distillation Tower TWR-0011 | TWR-0011 | Twr | Unit-100 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2683.66 | 1.9 | 7.3 | 7.2 | 0.1 | 16.5 | 2 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | HIGH | 189640.61 | 186956.95
WO-00393 | Testing – Heat Exchanger HX-0034 | HX-0034 | Hx | Flare-System | Testing | Low | FALSE | FALSE | DEFER | 14454.01 | 8.9 | 10.5 | 14.2 | 0.6 | 34.2 | 4 | 0.2662 | 1472.1654 | 4 | 3 | 4 | 12 | HIGH | 31144.9 | 16690.89 | WO-00363
WO-00394 | Replacement – Control Valve VLV-0059 | VLV-0059 | Vlv | Unit-100 | Replacement | High | FALSE | FALSE | DEFER | 47451.41 | 30.3 | 4.3 | 11.7 | 8.7 | 55 | 7 | 0.52703 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2828.17 | -44623.24
WO-00395 | Cleaning – Centrifugal Pump PMP-0009 | PMP-0009 | Pmp | Unit-300 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 10759.29 | 8.1 | 0 | 0.5 | 2.5 | 11.1 | 1 | 0.78238 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16899.41 | 6140.12
WO-00396 | Calibration – Instrument/Analyser INST-0173 | INST-0173 | Inst | Offsites | Calibration | High | FALSE | FALSE | DEFER | 2215.12 | 1.9 | 5.4 | 15.3 | 0.7 | 23.3 | 3 | 0.96759 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.33 | -821.79
WO-00397 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | High | FALSE | FALSE | DEFER | 65930.4 | 49.4 | 10.3 | 8.6 | 9.9 | 78.2 | 10 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -63424.52
WO-00398 | Testing – Instrument/Analyser INST-0019 | INST-0019 | Inst | Offsites | Testing | Medium | FALSE | FALSE | DEFER | 12231.17 | 17.1 | 19.9 | 8.2 | 1.3 | 46.5 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10791.17
WO-00399 | Calibration – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Calibration | Medium | FALSE | TRUE | INCLUDE | 960.38 | 0.4 | 4.6 | 11.7 | 0.6 | 17.3 | 2 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 47030.14
WO-00400 | Calibration – Electrical Equipment ELEC-0041 | ELEC-0041 | Elec | Offsites | Calibration | Critical | TRUE | TRUE | INCLUDE | 2093.22 | 0.5 | 5.8 | 9.4 | 0.2 | 15.9 | 2 | 0.4567 | 616.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4110.34 | 2017.12
WO-00401 | Replacement – Control Valve VLV-0004 | VLV-0004 | Vlv | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 34453.37 | 37.7 | 3.1 | 9.4 | 1.4 | 51.6 | 6 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | MEDIUM | 1675.84 | -32777.53 | WO-00202
WO-00402 | Cleaning – Instrument/Analyser INST-0060 | INST-0060 | Inst | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 9099.52 | 7.5 | 1.9 | 1.2 | 7.4 | 18 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -7659.52
WO-00403 | Calibration – Electrical Equipment ELEC-0071 | ELEC-0071 | Elec | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2709.86 | 0.8 | 7.5 | 7.7 | 0.7 | 16.7 | 2 | 0.82756 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7448.04 | 4738.18
WO-00404 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 7670.91 | 8.9 | 0.6 | 5 | 0.3 | 14.8 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -6230.91
WO-00405 | Repair – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 25758.52 | 49.4 | 21.3 | 4.3 | 4.8 | 79.8 | 10 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | -24367.94
WO-00406 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 580.71 | 0.5 | 7.7 | 6.5 | 0.4 | 15.1 | 2 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6437.74 | 5857.03
WO-00407 | Calibration – Heat Exchanger HX-0030 | HX-0030 | Hx | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 465.67 | 1.7 | 7.8 | 9.4 | 0.8 | 19.7 | 2 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | HIGH | 47081.26 | 46615.59
WO-00408 | Cleaning – Piping/Pipeline Segment PPL-0023 | PPL-0023 | Ppl | Utilities | Cleaning | Medium | FALSE | FALSE | DEFER | 14403.55 | 21.6 | 2 | 1.2 | 8.5 | 33.3 | 4 | 0.18038 | 2226.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8690.83 | -5712.72
WO-00409 | Repair – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 76452.94 | 25.8 | 8.3 | 12.6 | 5 | 51.7 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -75012.94
WO-00410 | Calibration – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Calibration | Critical | TRUE | TRUE | INCLUDE | 2808.8 | 0.8 | 7.7 | 7.1 | 0.5 | 16.1 | 2 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 35989.72
WO-00411 | Overhaul – Control Valve VLV-0027 | VLV-0027 | Vlv | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 334021.83 | 187.1 | 35.3 | 23.1 | 4.1 | 249.6 | 31 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | HIGH | 2116.63 | -331905.2
WO-00412 | Testing – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Testing | High | FALSE | FALSE | DEFER | 13873.83 | 7.9 | 9.2 | 12.7 | 1.4 | 31.2 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -12433.83
WO-00413 | Inspection – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3580.68 | 4.1 | 0.6 | 1.7 | 0.7 | 7.1 | 1 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 10602.92
WO-00414 | Replacement – Instrument/Analyser INST-0137 | INST-0137 | Inst | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 68694.19 | 33.6 | 16.3 | 23.1 | 2.2 | 75.2 | 9 | 0.96365 | 730 | 2 | 5 | 2 | 10 | HIGH | 1387.65 | -67306.54
WO-00415 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 2139.15 | 0.7 | 4.8 | 4.1 | 1 | 10.6 | 1 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | 16037.1
WO-00416 | Overhaul – Distillation Tower TWR-0012 | TWR-0012 | Twr | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 333104.76 | 48.1 | 15.3 | 34.2 | 14.3 | 111.9 | 14 | 0.3587 | 94.0539 | 5 | 4 | 5 | 20 | CRITICAL | 263641.88 | -69462.88
WO-00417 | Cleaning – Instrument/Analyser INST-0164 | INST-0164 | Inst | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 15434.46 | 23.6 | 0.1 | 1.4 | 7.7 | 32.8 | 4 | 0.96529 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.01 | -14044.45
WO-00418 | Inspection – Control Valve VLV-0115 | VLV-0115 | Vlv | Tank-Farm | Inspection | High | FALSE | FALSE | DEFER | 2182.51 | 3.6 | 1 | 1.5 | 0.7 | 6.8 | 1 | 0.48494 | 162.3748 | 2.65 | 4 | 3 | 12 | HIGH | 2602.31 | 419.8
WO-00419 | Inspection – Electrical Equipment ELEC-0009 | ELEC-0009 | Elec | Utilities | Inspection | High | FALSE | FALSE | DEFER | 2962.75 | 3.5 | 2 | 2.2 | 0.2 | 7.9 | 1 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1991.99 | -970.76
WO-00420 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 74672.62 | 48.7 | 8.6 | 16.5 | 5.3 | 79.1 | 10 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -73432.25
WO-00421 | Cleaning – Centrifugal Pump PMP-0042 | PMP-0042 | Pmp | Utilities | Cleaning | Medium | FALSE | TRUE | INCLUDE | 7957.4 | 20.9 | 1.6 | 0.9 | 9.9 | 33.3 | 4 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15665.17 | 7707.77
WO-00422 | Inspection – Instrument/Analyser INST-0055 | INST-0055 | Inst | Tank-Farm | Inspection | Medium | FALSE | FALSE | DEFER | 6421.99 | 6.8 | 1.1 | 3.1 | 0.9 | 11.9 | 1 | 0.90654 | 730 | 2 | 5 | 2 | 10 | HIGH | 1305.41 | -5116.58
WO-00423 | Cleaning – Heat Exchanger HX-0028 | HX-0028 | Hx | Unit-100 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 2172.64 | 14.8 | 1.8 | 1.4 | 2.4 | 20.4 | 3 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | HIGH | 64199.97 | 62027.33
WO-00424 | Repair – Instrument/Analyser INST-0011 | INST-0011 | Inst | Unit-100 | Repair | Medium | FALSE | FALSE | DEFER | 44641.37 | 10.1 | 18.6 | 3 | 3.9 | 35.6 | 4 | 0.79553 | 730 | 2 | 5 | 2 | 10 | HIGH | 1145.57 | -43495.8
WO-00425 | Repair – Control Valve VLV-0107 | VLV-0107 | Vlv | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 29908.06 | 87.1 | 27.9 | 2.4 | 3.2 | 120.6 | 15 | 0.5966 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3201.49 | -26706.57
WO-00426 | Calibration – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Calibration | Critical | FALSE | TRUE | INCLUDE | 1298.77 | 1.3 | 6.9 | 15.8 | 0.7 | 24.7 | 3 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | 4479.24
WO-00427 | Inspection – Electrical Equipment ELEC-0068 | ELEC-0068 | Elec | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 1582.18 | 9.5 | 1.8 | 4.2 | 0.1 | 15.6 | 2 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1589.67 | 7.49
WO-00428 | Inspection – Distillation Tower TWR-0007 | TWR-0007 | Twr | Flare-System | Inspection | Low | FALSE | TRUE | INCLUDE | 3326.04 | 4.1 | 1.7 | 1.6 | 0.6 | 8 | 1 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 271562.17 | 268236.13 | WO-00330
WO-00429 | Calibration – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Calibration | Low | FALSE | TRUE | INCLUDE | 421.85 | 1.8 | 7.1 | 11.3 | 0.7 | 20.9 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 1018.15 | WO-00323
WO-00430 | Overhaul – Instrument/Analyser INST-0098 | INST-0098 | Inst | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 325823.07 | 130.5 | 11 | 41.1 | 6.5 | 189.1 | 24 | 0.96482 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.33 | -324433.74 | WO-00356
WO-00431 | Replacement – Instrument/Analyser INST-0116 | INST-0116 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 37204.69 | 28.9 | 13.1 | 10.2 | 2.6 | 54.8 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -35764.69
WO-00432 | Testing – Instrument/Analyser INST-0103 | INST-0103 | Inst | Unit-300 | Testing | Low | FALSE | FALSE | DEFER | 7149.47 | 7.9 | 4.9 | 4.7 | 0.8 | 18.3 | 2 | 0.96042 | 730 | 2 | 5 | 2 | 10 | HIGH | 1383.01 | -5766.46
WO-00433 | Calibration – Electrical Equipment ELEC-0015 | ELEC-0015 | Elec | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 1177.95 | 1.9 | 5.4 | 8.4 | 0.4 | 16.1 | 2 | 0.2416 | 1590.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2174.38 | 996.43
WO-00434 | Repair – Piping/Pipeline Segment PPL-0034 | PPL-0034 | Ppl | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 30171.52 | 68.5 | 14.1 | 18.2 | 6.8 | 107.6 | 13 | 0.081176 | 3915.748 | 3.65 | 2 | 4 | 8 | MEDIUM | 3911.07 | -26260.45
WO-00435 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 7274.18 | 6.4 | 0.6 | 4.5 | 0.1 | 11.6 | 1 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | 38.02
WO-00436 | Cleaning – Heat Exchanger HX-0004 | HX-0004 | Hx | Unit-100 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 9155.54 | 15.4 | 0.5 | 0.3 | 2.3 | 18.5 | 2 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | HIGH | 43691.97 | 34536.43
WO-00437 | Testing – Instrument/Analyser INST-0004 | INST-0004 | Inst | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 8843.35 | 10.8 | 11.7 | 18.2 | 0.3 | 41 | 5 | 0.85899 | 730 | 2 | 5 | 2 | 10 | HIGH | 1236.94 | -7606.41 | WO-00370
WO-00438 | Cleaning – Distillation Tower TWR-0007 | TWR-0007 | Twr | Flare-System | Cleaning | Critical | FALSE | TRUE | INCLUDE | 12497.54 | 22.5 | 1.8 | 1.6 | 3.5 | 29.4 | 4 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 271562.17 | 259064.63
WO-00439 | Inspection – Instrument/Analyser INST-0024 | INST-0024 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 6398.13 | 9.3 | 1.9 | 2.2 | 0.8 | 14.2 | 2 | 0.86316 | 730 | 2 | 5 | 2 | 10 | HIGH | 1242.94 | -5155.19
WO-00440 | Repair – Instrument/Analyser INST-0037 | INST-0037 | Inst | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 44772.46 | 21.4 | 6.1 | 19.2 | 4.8 | 51.5 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -43332.46
WO-00441 | Replacement – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 48577.46 | 57.1 | 3.1 | 6.4 | 8.1 | 74.7 | 9 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -47199.64 | WO-00164
WO-00442 | Inspection – Pressure Vessel VSL-0010 | VSL-0010 | Vsl | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 855.01 | 3.8 | 0.5 | 1.1 | 0.2 | 5.6 | 1 | 0.28693 | 1046.4952 | 5 | 3 | 5 | 15 | HIGH | 62407.43 | 61552.42
WO-00443 | Repair – Control Valve VLV-0032 | VLV-0032 | Vlv | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 72062.39 | 43.9 | 12.3 | 20 | 7.9 | 84.1 | 11 | 0.59751 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3206.38 | -68856.01
WO-00444 | Replacement – Distillation Tower TWR-0005 | TWR-0005 | Twr | Tank-Farm | Replacement | High | FALSE | TRUE | INCLUDE | 41950.13 | 34.8 | 11.8 | 4.3 | 9.6 | 60.5 | 8 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | HIGH | 44001.97 | 2051.84
WO-00445 | Cleaning – Electrical Equipment ELEC-0060 | ELEC-0060 | Elec | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 6075.31 | 22.4 | 1.5 | 0.2 | 6.8 | 30.9 | 4 | 0.76691 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6902.2 | 826.89
WO-00446 | Repair – Control Valve VLV-0062 | VLV-0062 | Vlv | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 18075.11 | 88.7 | 16 | 3.7 | 2 | 110.4 | 14 | 0.34935 | 1279.3751 | 2.65 | 3 | 3 | 9 | MEDIUM | 1874.71 | -16200.4
WO-00447 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 62086.67 | 46.9 | 5.4 | 23.9 | 2.5 | 78.7 | 10 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | -43085.89
WO-00448 | Testing – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 12571.36 | 13.7 | 18.3 | 6.7 | 0 | 38.7 | 5 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 1612.24
WO-00449 | Inspection – Reciprocating Compressor CMP-0007 | CMP-0007 | Cmp | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 3247.37 | 3.8 | 1.8 | 4.5 | 0.8 | 10.9 | 1 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 339618.52 | 336371.15
WO-00450 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 957.92 | 7.2 | 1.3 | 2.5 | 0.5 | 11.5 | 1 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | 432.66
WO-00451 | Replacement – Electrical Equipment ELEC-0026 | ELEC-0026 | Elec | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 41129.16 | 29.8 | 12.9 | 23.1 | 5.8 | 71.6 | 9 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5492.41 | -35636.75
WO-00452 | Calibration – Control Valve VLV-0038 | VLV-0038 | Vlv | Tank-Farm | Calibration | Low | FALSE | TRUE | INCLUDE | 517.82 | 1.3 | 5.9 | 13.2 | 0 | 20.4 | 3 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3387.34 | 2869.52
WO-00453 | Testing – Control Valve VLV-0079 | VLV-0079 | Vlv | Unit-300 | Testing | High | FALSE | TRUE | INCLUDE | 550.49 | 5.8 | 7.6 | 19.6 | 1.2 | 34.2 | 4 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3315.02 | 2764.53
WO-00454 | Calibration – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 1189.73 | 0.9 | 5.1 | 12.3 | 0.5 | 18.8 | 2 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | 2284.68
WO-00455 | Overhaul – Heat Exchanger HX-0014 | HX-0014 | Hx | Unit-100 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 546377.23 | 140.6 | 46.5 | 31.1 | 19.4 | 237.6 | 30 | 0.3698 | 472.1654 | 4 | 4 | 4 | 16 | HIGH | 43266.74 | -503110.49
WO-00456 | Calibration – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Calibration | Low | FALSE | TRUE | INCLUDE | 940.1 | 0 | 3.3 | 4.3 | 0.9 | 8.5 | 1 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 47050.42 | WO-00444
WO-00457 | Calibration – Reciprocating Compressor CMP-0002 | CMP-0002 | Cmp | Utilities | Calibration | High | FALSE | TRUE | INCLUDE | 502.76 | 1.8 | 8 | 9.3 | 0.5 | 19.6 | 2 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 172649.17 | 172146.41
WO-00458 | Inspection – Distillation Tower TWR-0005 | TWR-0005 | Twr | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 4311.4 | 7.9 | 0.4 | 2.8 | 0.5 | 11.6 | 1 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | HIGH | 44001.97 | 39690.57
WO-00459 | Testing – Instrument/Analyser INST-0038 | INST-0038 | Inst | Unit-200 | Testing | Critical | FALSE | FALSE | DEFER | 12800 | 13.2 | 15.7 | 16.1 | 1.1 | 46.1 | 6 | 0.95252 | 730 | 2 | 5 | 2 | 10 | HIGH | 1371.63 | -11428.37
WO-00460 | Calibration – Centrifugal Pump PMP-0010 | PMP-0010 | Pmp | Tank-Farm | Calibration | Critical | FALSE | FALSE | DEFER | 2205.74 | 1 | 9 | 14.8 | 0.4 | 25.2 | 3 | 0.61598 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13305.23 | 11099.49 | WO-00148
WO-00461 | Inspection – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Inspection | Medium | FALSE | TRUE | INCLUDE | 3203.31 | 5.7 | 0.3 | 1.8 | 0.2 | 8 | 1 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | 2180.54
WO-00462 | Calibration – Instrument/Analyser INST-0129 | INST-0129 | Inst | Tank-Farm | Calibration | Critical | FALSE | FALSE | DEFER | 1272.23 | 0.3 | 2.9 | 5.4 | 0.4 | 9 | 1 | 0.59502 | 607.2559 | 2 | 4 | 2 | 8 | MEDIUM | 856.83 | -415.4
WO-00463 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 115576.32 | 34.4 | 16.8 | 6.6 | 3.4 | 61.2 | 8 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | -100015.55
WO-00464 | Replacement – Electrical Equipment ELEC-0053 | ELEC-0053 | Elec | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 79566.7 | 58.8 | 11.9 | 10.1 | 5.8 | 86.6 | 11 | 0.79521 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7156.92 | -72409.78
WO-00465 | Inspection – Centrifugal Pump PMP-0019 | PMP-0019 | Pmp | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 653.07 | 9.1 | 1.3 | 2.2 | 0.2 | 12.8 | 2 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | MEDIUM | 2786.64 | 2133.57 | WO-00264
WO-00466 | Repair – Instrument/Analyser INST-0057 | INST-0057 | Inst | Offsites | Repair | High | FALSE | FALSE | DEFER | 25332.85 | 37.6 | 26.2 | 18.1 | 9.2 | 91.1 | 11 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | HIGH | 1048.11 | -24284.74
WO-00467 | Inspection – Distillation Tower TWR-0009 | TWR-0009 | Twr | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 3855.98 | 4.4 | 1.8 | 1.1 | 0.6 | 7.9 | 1 | 0.052723 | 3696.054 | 5 | 2 | 5 | 10 | HIGH | 38751.19 | 34895.21
WO-00468 | Testing – Instrument/Analyser INST-0020 | INST-0020 | Inst | Utilities | Testing | Low | FALSE | FALSE | DEFER | 9926.89 | 19.1 | 5.5 | 11.2 | 0 | 35.8 | 4 | 0.7612 | 37.2559 | 2 | 5 | 2 | 10 | HIGH | 1096.12 | -8830.77
WO-00469 | Repair – Piping/Pipeline Segment PPL-0018 | PPL-0018 | Ppl | Unit-200 | Repair | Critical | FALSE | FALSE | DEFER | 4188.1 | 9.7 | 13.5 | 6.7 | 8.6 | 38.5 | 5 | 0.068723 | 4114.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 3311.1 | -877
WO-00470 | Calibration – Storage Tank TNK-0020 | TNK-0020 | Tnk | Flare-System | Calibration | High | FALSE | TRUE | INCLUDE | 1752.49 | 0.8 | 3.2 | 20 | 0.6 | 24.6 | 3 | 0.16756 | 2160.2321 | 4 | 3 | 4 | 12 | HIGH | 39208.79 | 37456.3
WO-00471 | Replacement – Control Valve VLV-0041 | VLV-0041 | Vlv | Offsites | Replacement | High | FALSE | FALSE | DEFER | 109158.75 | 50.7 | 16.6 | 16.3 | 9 | 92.6 | 12 | 0.41899 | 798.375 | 2.65 | 4 | 3 | 12 | HIGH | 2248.38 | -106910.37
WO-00472 | Calibration – Instrument/Analyser INST-0069 | INST-0069 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1332.45 | 1.2 | 10 | 19.8 | 0.5 | 31.5 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 107.55
WO-00473 | Repair – Piping/Pipeline Segment PPL-0020 | PPL-0020 | Ppl | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 78879.59 | 79.6 | 5.7 | 7.8 | 9.1 | 102.2 | 13 | 0.12468 | 3198.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6007.02 | -72872.57
WO-00474 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 2070.19 | 0.8 | 5.2 | 16.9 | 0.3 | 23.2 | 3 | 0.81141 | 730 | 2 | 5 | 2 | 10 | HIGH | 1168.43 | -901.76
WO-00475 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 2564.76 | 0.6 | 7.9 | 5.7 | 0.1 | 14.3 | 2 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6437.74 | 3872.98
WO-00476 | Inspection – Pressure Vessel VSL-0018 | VSL-0018 | Vsl | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 7612.97 | 9.2 | 0.1 | 4.4 | 0.5 | 14.2 | 2 | 0.39382 | 59.4951 | 5 | 4 | 5 | 20 | CRITICAL | 85654.78 | 78041.81
WO-00477 | Repair – Control Valve VLV-0044 | VLV-0044 | Vlv | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 47004.01 | 18.7 | 4.1 | 10.9 | 9.5 | 43.2 | 5 | 0.6655 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3571.26 | -43432.75
WO-00478 | Replacement – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Replacement | High | FALSE | FALSE | DEFER | 8556.03 | 55.6 | 7.9 | 18.1 | 7.2 | 88.8 | 11 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -7170.47
WO-00479 | Inspection – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 3449 | 4.5 | 1.4 | 4.3 | 0.2 | 10.4 | 1 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -1316.83
WO-00480 | Inspection – Piping/Pipeline Segment PPL-0001 | PPL-0001 | Ppl | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 2185.49 | 8.1 | 1.6 | 4.1 | 0.1 | 13.9 | 2 | 0.26868 | 541.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12944.99 | 10759.5
WO-00481 | Overhaul – Instrument/Analyser INST-0135 | INST-0135 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 595019.48 | 170.8 | 47.3 | 14.1 | 13 | 245.2 | 31 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -593579.48
WO-00482 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 77738.48 | 34.6 | 19.9 | 7.5 | 9.4 | 71.4 | 9 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -76498.11
WO-00483 | Overhaul – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Overhaul | Low | FALSE | FALSE | DEFER | 324232.1 | 93.1 | 48.5 | 46.3 | 23.5 | 211.4 | 26 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -322846.54
WO-00484 | Cleaning – Control Valve VLV-0067 | VLV-0067 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 11840.45 | 24.4 | 0 | 1.7 | 6 | 32.1 | 4 | 0.60745 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3259.71 | -8580.74
WO-00485 | Replacement – Pressure Vessel VSL-0011 | VSL-0011 | Vsl | Unit-100 | Replacement | Critical | FALSE | FALSE | DEFER | 47391.66 | 9.6 | 9.6 | 12.2 | 3 | 34.4 | 4 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | HIGH | 36127.93 | -11263.73
WO-00486 | Cleaning – Instrument/Analyser INST-0018 | INST-0018 | Inst | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 8626.51 | 23.9 | 0.2 | 1.2 | 3.3 | 28.6 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -7186.51
WO-00487 | Cleaning – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 16415.14 | 14.3 | 1 | 0.4 | 5.7 | 21.4 | 3 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -14282.97
WO-00488 | Cleaning – Instrument/Analyser INST-0053 | INST-0053 | Inst | Tank-Farm | Cleaning | Critical | TRUE | TRUE | INCLUDE | 11435.72 | 22.7 | 0.9 | 0.5 | 4.2 | 28.3 | 4 | 0.54637 | 720.2559 | 2 | 4 | 2 | 8 | MEDIUM | 786.77 | -10648.95
WO-00489 | Cleaning – Electrical Equipment ELEC-0022 | ELEC-0022 | Elec | Unit-300 | Cleaning | Critical | FALSE | FALSE | DEFER | 20941.14 | 22.5 | 0.9 | 0.4 | 8.9 | 32.7 | 4 | 0.31845 | 1278.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2866.08 | -18075.06 | WO-00157
WO-00490 | Replacement – Centrifugal Pump PMP-0018 | PMP-0018 | Pmp | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 103510.74 | 28.4 | 4.1 | 9.3 | 6.4 | 48.2 | 6 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13798.72 | -89712.02
WO-00491 | Cleaning – Instrument/Analyser INST-0179 | INST-0179 | Inst | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 11515.89 | 12 | 0.5 | 1.6 | 5.2 | 19.3 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10075.89
WO-00492 | Overhaul – Instrument/Analyser INST-0023 | INST-0023 | Inst | Unit-100 | Overhaul | Low | FALSE | FALSE | DEFER | 68742.3 | 128.1 | 29.3 | 27.2 | 20.3 | 204.9 | 26 | 0.74528 | 110.2559 | 2 | 5 | 2 | 10 | HIGH | 1073.21 | -67669.09
WO-00493 | Calibration – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1831.79 | 1.1 | 7.2 | 8.6 | 0.8 | 17.7 | 2 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | 5981.24
WO-00494 | Replacement – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Replacement | Critical | FALSE | FALSE | DEFER | 108824.09 | 52.1 | 9.6 | 22.2 | 2.1 | 86 | 11 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -107384.09
WO-00495 | Replacement – Instrument/Analyser INST-0006 | INST-0006 | Inst | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 70025.11 | 26.3 | 19 | 9.1 | 3.5 | 57.9 | 7 | 0.96225 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.63 | -68639.48
WO-00496 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Inspection | Critical | TRUE | TRUE | INCLUDE | 5983.92 | 5 | 2 | 3.8 | 0.1 | 10.9 | 1 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | 10672.67
WO-00497 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 7649.4 | 7.5 | 0.9 | 1.8 | 0.9 | 11.1 | 1 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | -1871.39 | WO-00445
WO-00498 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | Inst | Unit-300 | Calibration | Low | FALSE | FALSE | DEFER | 2337.31 | 0.6 | 6 | 7.6 | 0.4 | 14.6 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -897.31
WO-00499 | Calibration – Electrical Equipment ELEC-0065 | ELEC-0065 | Elec | Unit-200 | Calibration | High | FALSE | TRUE | INCLUDE | 2570.52 | 1.1 | 3.9 | 15.4 | 0.5 | 20.9 | 3 | 0.75345 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6781.01 | 4210.49
WO-00500 | Overhaul – Centrifugal Pump PMP-0058 | PMP-0058 | Pmp | Unit-100 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 386381.53 | 187.1 | 18.2 | 44.8 | 11.6 | 261.7 | 33 | 0.82968 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17921.13 | -368460.4
WO-00501 | Inspection – Reciprocating Compressor CMP-0017 | CMP-0017 | Cmp | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 6550.87 | 4.8 | 1 | 1.9 | 0.7 | 8.4 | 1 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 342574.13
WO-00502 | Replacement – Electrical Equipment ELEC-0074 | ELEC-0074 | Elec | Tank-Farm | Replacement | High | FALSE | FALSE | DEFER | 113684.13 | 9.6 | 4.4 | 15.8 | 7.3 | 37.1 | 5 | 0.48585 | 455.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4372.65 | -109311.48
WO-00503 | Cleaning – Centrifugal Pump PMP-0027 | PMP-0027 | Pmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 8641.27 | 17.3 | 1.3 | 1.9 | 5.6 | 26.1 | 3 | 0.79898 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17257.88 | 8616.61
WO-00504 | Cleaning – Instrument/Analyser INST-0024 | INST-0024 | Inst | Unit-100 | Cleaning | High | FALSE | FALSE | DEFER | 8621.32 | 10.1 | 2 | 0.4 | 8.3 | 20.8 | 3 | 0.86316 | 730 | 2 | 5 | 2 | 10 | HIGH | 1242.94 | -7378.38 | WO-00383
WO-00505 | Calibration – Control Valve VLV-0120 | VLV-0120 | Vlv | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 720.04 | 1.9 | 7.5 | 5.4 | 0.7 | 15.5 | 2 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2846.98 | 2126.94 | WO-00377
WO-00506 | Replacement – Piping/Pipeline Segment PPL-0008 | PPL-0008 | Ppl | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 34984.64 | 45.4 | 15.3 | 10.5 | 8.9 | 80.1 | 10 | 0.21919 | 1509.7483 | 3.65 | 3 | 4 | 12 | HIGH | 10560.48 | -24424.16
WO-00507 | Inspection – Electrical Equipment ELEC-0061 | ELEC-0061 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 5039.02 | 2.9 | 0.6 | 3 | 0.3 | 6.8 | 1 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6951.19 | 1912.17 | WO-00389
WO-00508 | Calibration – Storage Tank TNK-0001 | TNK-0001 | Tnk | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1731.6 | 1.7 | 6.6 | 11.7 | 0.3 | 20.3 | 3 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | HIGH | 50668.31 | 48936.71
WO-00509 | Inspection – Control Valve VLV-0048 | VLV-0048 | Vlv | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 2392.49 | 8.7 | 1.5 | 3.5 | 0 | 13.7 | 2 | 0.35245 | 1261.3751 | 2.65 | 4 | 3 | 12 | HIGH | 1891.34 | -501.15
WO-00510 | Overhaul – Instrument/Analyser INST-0074 | INST-0074 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 451608.27 | 132.8 | 8.7 | 15.7 | 15.8 | 173 | 22 | 0.92649 | 730 | 2 | 5 | 2 | 10 | HIGH | 1334.15 | -450274.12
WO-00511 | Inspection – Instrument/Analyser INST-0144 | INST-0144 | Inst | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 920.65 | 4.1 | 0.2 | 3.2 | 0.1 | 7.6 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 519.35
WO-00512 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | Ppl | Unit-100 | Calibration | Medium | FALSE | FALSE | DEFER | 2917.45 | 1.9 | 4.2 | 4.5 | 0.3 | 10.9 | 1 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8869.41 | 5951.96 | WO-00338
WO-00513 | Inspection – Centrifugal Pump PMP-0005 | PMP-0005 | Pmp | Tank-Farm | Inspection | High | FALSE | TRUE | INCLUDE | 3261.87 | 4.4 | 0.4 | 3.8 | 0.7 | 9.3 | 1 | 0.84976 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18354.81 | 15092.94
WO-00514 | Repair – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Repair | Critical | FALSE | TRUE | INCLUDE | 10044.83 | 21.8 | 14 | 13.8 | 6.3 | 55.9 | 7 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 4138.77 | WO-00217
WO-00515 | Testing – Control Valve VLV-0089 | VLV-0089 | Vlv | Unit-200 | Testing | Low | FALSE | FALSE | DEFER | 4923.44 | 8.5 | 16.5 | 22.9 | 1.3 | 49.2 | 6 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3326.16 | -1597.28
WO-00516 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Inspection | Critical | TRUE | TRUE | INCLUDE | 5179.19 | 8.6 | 1 | 2.4 | 1 | 13 | 2 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | 11477.4
WO-00517 | Overhaul – Instrument/Analyser INST-0091 | INST-0091 | Inst | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 525923.65 | 220.1 | 49.2 | 45.2 | 5 | 319.5 | 40 | 0.94394 | 730 | 2 | 5 | 2 | 10 | HIGH | 1359.27 | -524564.38
WO-00518 | Overhaul – Electrical Equipment ELEC-0014 | ELEC-0014 | Elec | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 396197.22 | 118.9 | 42.2 | 32.2 | 20.9 | 214.2 | 27 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5975.81 | -390221.41
WO-00519 | Inspection – Heat Exchanger HX-0001 | HX-0001 | Hx | Unit-100 | Inspection | Critical | TRUE | TRUE | INCLUDE | 3858.79 | 2 | 1.4 | 2.2 | 0.6 | 6.2 | 1 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48649.09 | 44790.3
WO-00520 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 5209.16 | 4.4 | 0.4 | 1.9 | 0.2 | 6.9 | 1 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | 2655.86
WO-00521 | Inspection – Storage Tank TNK-0001 | TNK-0001 | Tnk | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 3284.03 | 7.5 | 1 | 3.4 | 0.3 | 12.2 | 2 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | HIGH | 50668.31 | 47384.28
WO-00522 | Overhaul – Piping/Pipeline Segment PPL-0004 | PPL-0004 | Ppl | Unit-100 | Overhaul | Critical | FALSE | FALSE | DEFER | 182873.9 | 220.9 | 35.5 | 33.8 | 21.7 | 311.9 | 39 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | HIGH | 15082.22 | -167791.68
WO-00523 | Repair – Heat Exchanger HX-0018 | HX-0018 | Hx | Unit-200 | Repair | Critical | FALSE | FALSE | DEFER | 54873.42 | 41.1 | 10.7 | 3.9 | 9.5 | 65.2 | 8 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | HIGH | 33820.42 | -21053
WO-00524 | Replacement – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 84477.33 | 44.9 | 4.9 | 20.3 | 5.6 | 75.7 | 9 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | -43031.79
WO-00525 | Inspection – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Inspection | Medium | FALSE | TRUE | INCLUDE | 916.94 | 7.1 | 0.3 | 3.1 | 0 | 10.5 | 1 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 47525.01
WO-00526 | Repair – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 67432.86 | 96.2 | 27.5 | 10 | 4.6 | 138.3 | 17 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | -59619.83
WO-00527 | Testing – Control Valve VLV-0002 | VLV-0002 | Vlv | Utilities | Testing | Medium | FALSE | FALSE | DEFER | 14606.12 | 15.8 | 8 | 22.9 | 1.9 | 48.6 | 6 | 0.67434 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3618.69 | -10987.43
WO-00528 | Repair – Instrument/Analyser INST-0068 | INST-0068 | Inst | Flare-System | Repair | High | FALSE | FALSE | DEFER | 45771.76 | 94.9 | 6.4 | 17.6 | 1.5 | 120.4 | 15 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -44331.76
WO-00529 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | Ppl | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 4145.6 | 3.9 | 1.9 | 3.2 | 0.9 | 9.9 | 1 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12169.06 | 8023.46
WO-00530 | Inspection – Storage Tank TNK-0005 | TNK-0005 | Tnk | Flare-System | Inspection | High | FALSE | TRUE | INCLUDE | 6339.85 | 7.6 | 1.1 | 4.3 | 0.8 | 13.8 | 2 | 0.036789 | 4499.2321 | 4 | 1 | 4 | 4 | LOW | 8608.56 | 2268.71
WO-00531 | Testing – Instrument/Analyser INST-0084 | INST-0084 | Inst | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 10935.82 | 14.2 | 11.2 | 4 | 0.5 | 29.9 | 4 | 0.96708 | 730 | 2 | 5 | 2 | 10 | HIGH | 1392.6 | -9543.22
WO-00532 | Calibration – Reciprocating Compressor CMP-0008 | CMP-0008 | Cmp | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 1126.86 | 1.3 | 3.6 | 8.2 | 0.9 | 14 | 2 | 0.80752 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 281925.94 | 280799.08
WO-00533 | Replacement – Centrifugal Pump PMP-0053 | PMP-0053 | Pmp | Utilities | Replacement | High | FALSE | FALSE | DEFER | 61017.45 | 28.1 | 15.1 | 23.2 | 6.3 | 72.7 | 9 | 0.71868 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15523.41 | -45494.04
WO-00534 | Replacement – Control Valve VLV-0029 | VLV-0029 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 69932.56 | 24.6 | 2 | 21.3 | 4.9 | 52.8 | 7 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -67426.68
WO-00535 | Inspection – Centrifugal Pump PMP-0041 | PMP-0041 | Pmp | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 6794.62 | 3.4 | 0.8 | 4.4 | 0.5 | 9.1 | 1 | 0.79812 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17239.43 | 10444.81
WO-00536 | Replacement – Reciprocating Compressor CMP-0007 | CMP-0007 | Cmp | Flare-System | Replacement | Medium | FALSE | TRUE | INCLUDE | 87251.78 | 58.9 | 11.9 | 17.8 | 4.5 | 93.1 | 12 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 339618.52 | 252366.74 | WO-00024
WO-00537 | Repair – Centrifugal Pump PMP-0047 | PMP-0047 | Pmp | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 56838.33 | 94.1 | 19.3 | 12.4 | 3.7 | 129.5 | 16 | 0.60929 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13160.57 | -43677.76
WO-00538 | Repair – Electrical Equipment ELEC-0002 | ELEC-0002 | Elec | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 52412.67 | 29.4 | 18.1 | 15.6 | 9.5 | 72.6 | 9 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6708.41 | -45704.26 | WO-00425
WO-00539 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 3655.78 | 3 | 2 | 2.7 | 0.5 | 8.2 | 1 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -2556.35
WO-00540 | Overhaul – Instrument/Analyser INST-0030 | INST-0030 | Inst | Flare-System | Overhaul | Low | FALSE | FALSE | DEFER | 591045.95 | 137.7 | 8.4 | 18.2 | 23.6 | 187.9 | 23 | 0.88342 | 730 | 2 | 5 | 2 | 10 | HIGH | 1272.12 | -589773.83
WO-00541 | Replacement – Electrical Equipment ELEC-0032 | ELEC-0032 | Elec | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 75755.37 | 12 | 12.4 | 6.5 | 8.4 | 39.3 | 5 | 0.53526 | 160.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4817.3 | -70938.07
WO-00542 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 4024.07 | 2.8 | 0.7 | 1.3 | 0.3 | 5.1 | 1 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 34774.45
WO-00543 | Inspection – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 6956.37 | 2.6 | 1.1 | 2.8 | 0.9 | 7.4 | 1 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | -4008.13
WO-00544 | Inspection – Reciprocating Compressor CMP-0014 | CMP-0014 | Cmp | Unit-100 | Inspection | Medium | FALSE | TRUE | INCLUDE | 6140.48 | 7.8 | 1.4 | 1.1 | 0.3 | 10.6 | 1 | 0.38692 | 935.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 135084.24 | 128943.76
WO-00545 | Cleaning – Pressure Vessel VSL-0025 | VSL-0025 | Vsl | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 15452.68 | 11.1 | 0.5 | 1.9 | 7.8 | 21.3 | 3 | 0.04163 | 3821.4951 | 5 | 1 | 5 | 5 | MEDIUM | 9054.44 | -6398.24
WO-00546 | Testing – Heat Exchanger HX-0029 | HX-0029 | Hx | Unit-200 | Testing | High | FALSE | TRUE | INCLUDE | 8944.37 | 8 | 11.9 | 18.5 | 0.8 | 39.2 | 5 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | HIGH | 26996.81 | 18052.44
WO-00547 | Calibration – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Calibration | Medium | FALSE | TRUE | INCLUDE | 747.05 | 1.9 | 4.8 | 10.7 | 0.7 | 18.1 | 2 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | 352.38
WO-00548 | Overhaul – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 395099.09 | 220.6 | 41.6 | 42.6 | 9.2 | 314 | 39 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | -387286.06
WO-00549 | Cleaning – Instrument/Analyser INST-0040 | INST-0040 | Inst | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 2060.58 | 22.5 | 0.6 | 0.6 | 4.1 | 27.8 | 3 | 0.90208 | 730 | 2 | 5 | 2 | 10 | HIGH | 1299 | -761.58
WO-00550 | Replacement – Control Valve VLV-0054 | VLV-0054 | Vlv | Utilities | Replacement | Critical | FALSE | FALSE | DEFER | 74554.82 | 38.3 | 6.6 | 8.1 | 8.4 | 61.4 | 8 | 0.65259 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3501.98 | -71052.84

## Selected
wo_id | description | asset_tag | asset_class | area | task_type | priority | mandatory | selected | decision | estimated_cost_usd | mech_hours | elec_hours | inst_hours | civil_hours | total_craft_hours | duration_days | failure_prob | rul_days | consequence_score | likelihood_tier | consequence_tier | risk_score | risk_level | deferred_cost_usd | net_value_usd | predecessor_wo_id
WO-00004 | Cleaning – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 15844.97 | 5.4 | 0.4 | 1.1 | 2.5 | 9.4 | 1 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 64711.24
WO-00006 | Inspection – Instrument/Analyser INST-0142 | INST-0142 | Inst | Offsites | Inspection | High | FALSE | TRUE | INCLUDE | 734.91 | 2.2 | 1 | 4.2 | 0.1 | 7.5 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 705.09
WO-00011 | Replacement – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Replacement | Medium | FALSE | TRUE | INCLUDE | 18665.17 | 34.6 | 5 | 15.8 | 2.5 | 57.9 | 7 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | 22780.37
WO-00014 | Calibration – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1653.01 | 1.3 | 4.9 | 11 | 0.2 | 17.4 | 2 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 31225.23
WO-00017 | Calibration – Instrument/Analyser INST-0106 | INST-0106 | Inst | Offsites | Calibration | Critical | FALSE | TRUE | INCLUDE | 621.83 | 0.5 | 8.2 | 12.6 | 0 | 21.3 | 3 | 0.96519 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.87 | 768.04
WO-00018 | Overhaul – Reciprocating Compressor CMP-0017 | CMP-0017 | Cmp | Offsites | Overhaul | Critical | FALSE | TRUE | INCLUDE | 193398.98 | 76.1 | 33.8 | 17.6 | 15.8 | 143.3 | 18 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 155726.02
WO-00021 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | Pmp | Tank-Farm | Inspection | Critical | FALSE | TRUE | INCLUDE | 2928.69 | 9 | 1.8 | 1.4 | 0.5 | 12.7 | 2 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18327.69 | 15399
WO-00024 | Overhaul – Instrument/Analyser INST-0117 | INST-0117 | Inst | Flare-System | Overhaul | Medium | FALSE | TRUE | INCLUDE | 206394.95 | 233.9 | 15.3 | 14.4 | 7.3 | 270.9 | 34 | 0.86878 | 730 | 2 | 5 | 2 | 10 | HIGH | 1251.04 | -205143.91
WO-00027 | Calibration – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Calibration | High | FALSE | TRUE | INCLUDE | 876.17 | 1.7 | 4.2 | 16.4 | 0.1 | 22.4 | 3 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | 4507.68
WO-00033 | Calibration – Pressure Vessel VSL-0023 | VSL-0023 | Vsl | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1762.08 | 1.4 | 7.5 | 7.7 | 0.6 | 17.2 | 2 | 0.40366 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 87797.04 | 86034.96
WO-00037 | Inspection – Heat Exchanger HX-0005 | HX-0005 | Hx | Offsites | Inspection | Critical | FALSE | TRUE | INCLUDE | 5600.54 | 4 | 1.5 | 4.1 | 0.7 | 10.3 | 1 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | HIGH | 33706.39 | 28105.85
WO-00039 | Calibration – Storage Tank TNK-0019 | TNK-0019 | Tnk | Tank-Farm | Calibration | Critical | FALSE | TRUE | INCLUDE | 304.05 | 1.1 | 6.6 | 8.9 | 0.9 | 17.5 | 2 | 0.0041101 | 6049.2321 | 4 | 1 | 4 | 4 | LOW | 961.75 | 657.7
WO-00050 | Inspection – Centrifugal Pump PMP-0052 | PMP-0052 | Pmp | Unit-300 | Inspection | High | FALSE | TRUE | INCLUDE | 2619.75 | 10 | 1.8 | 1.9 | 0.3 | 14 | 2 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17151.61 | 14531.86
WO-00052 | Inspection – Pressure Vessel VSL-0022 | VSL-0022 | Vsl | Offsites | Inspection | Critical | FALSE | TRUE | INCLUDE | 4849.8 | 3.2 | 1.4 | 4.7 | 0.5 | 9.8 | 1 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | HIGH | 58166.81 | 53317.01
WO-00053 | Cleaning – Piping/Pipeline Segment PPL-0014 | PPL-0014 | Ppl | Unit-300 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 10804.4 | 23.5 | 0.7 | 1.7 | 4.2 | 30.1 | 4 | 0.078998 | 3950.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 3806.13 | -6998.27
WO-00054 | Replacement – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Replacement | Critical | FALSE | TRUE | INCLUDE | 9015.32 | 22.6 | 13.9 | 6.8 | 2 | 45.3 | 6 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 23862.92
WO-00056 | Replacement – Heat Exchanger HX-0032 | HX-0032 | Hx | Tank-Farm | Replacement | Critical | FALSE | TRUE | INCLUDE | 37833.53 | 31.6 | 17.4 | 18.6 | 5.2 | 72.8 | 9 | 0.50931 | 2190 | 4 | 4 | 4 | 16 | HIGH | 59589.59 | 21756.06
WO-00059 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | High | FALSE | TRUE | INCLUDE | 3766.42 | 3.3 | 0.7 | 4.2 | 0.2 | 8.4 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 85675.22
WO-00064 | Replacement – Reciprocating Compressor CMP-0001 | CMP-0001 | Cmp | Unit-200 | Replacement | High | FALSE | TRUE | INCLUDE | 94600.93 | 22.9 | 3.3 | 4.7 | 5 | 35.9 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 254524.07
WO-00068 | Calibration – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Calibration | Critical | FALSE | TRUE | INCLUDE | 2003.44 | 0.8 | 2 | 11.1 | 0 | 13.9 | 2 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | 11569.69
WO-00073 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | Ppl | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2243.11 | 0.8 | 6.8 | 11 | 0.6 | 19.2 | 2 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8869.41 | 6626.3 | WO-00039
WO-00077 | Calibration – Heat Exchanger HX-0021 | HX-0021 | Hx | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2272.41 | 0.7 | 8.6 | 5.2 | 0 | 14.5 | 2 | 0.51614 | 2190 | 4 | 4 | 4 | 16 | HIGH | 60387.91 | 58115.5
WO-00078 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 7104.07 | 5.4 | 0.5 | 2.7 | 0.4 | 9 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 82337.57
WO-00080 | Inspection – Reciprocating Compressor CMP-0015 | CMP-0015 | Cmp | Tank-Farm | Inspection | Critical | TRUE | TRUE | INCLUDE | 1241.92 | 9.6 | 0.9 | 3.5 | 0 | 14 | 2 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 162580.25 | 161338.33
WO-00081 | Overhaul – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Overhaul | Critical | TRUE | TRUE | INCLUDE | 533437.71 | 94.3 | 40.6 | 35.8 | 6.3 | 177 | 22 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | -519864.58
WO-00089 | Calibration – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2070.19 | 1.8 | 5.3 | 10.2 | 0.2 | 17.5 | 2 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 46371.76
WO-00091 | Calibration – Heat Exchanger HX-0033 | HX-0033 | Hx | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 1963.41 | 1.6 | 4 | 14.1 | 0.2 | 19.9 | 2 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | HIGH | 32878.24 | 30914.83
WO-00092 | Calibration – Electrical Equipment ELEC-0007 | ELEC-0007 | Elec | Offsites | Calibration | Low | FALSE | TRUE | INCLUDE | 1968.67 | 0.4 | 8.9 | 4.9 | 0.6 | 14.8 | 2 | 0.84418 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7597.65 | 5628.98 | WO-00053
WO-00094 | Calibration – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Calibration | High | FALSE | TRUE | INCLUDE | 866.15 | 2 | 3.8 | 7.8 | 0.9 | 14.5 | 2 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | 2082.09
WO-00096 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Inspection | Critical | TRUE | TRUE | INCLUDE | 3341.33 | 4.5 | 0.1 | 3.5 | 0.6 | 8.7 | 1 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | -1950.75
WO-00098 | Repair – Piping/Pipeline Segment PPL-0045 | PPL-0045 | Ppl | Unit-100 | Repair | Critical | TRUE | TRUE | INCLUDE | 73031.8 | 28.6 | 12.1 | 4.9 | 3.8 | 49.4 | 6 | 0.25897 | 736.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12477.11 | -60554.69
WO-00099 | Cleaning – Heat Exchanger HX-0029 | HX-0029 | Hx | Unit-200 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 5551.51 | 26.1 | 0.2 | 0 | 8.8 | 35.1 | 4 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | HIGH | 26996.81 | 21445.3
WO-00103 | Inspection – Pressure Vessel VSL-0001 | VSL-0001 | Vsl | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 2755.35 | 6.1 | 1 | 3.4 | 0.4 | 10.9 | 1 | 0.21575 | 1726.4951 | 5 | 3 | 5 | 15 | HIGH | 46925.07 | 44169.72
WO-00104 | Repair – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Repair | Critical | TRUE | TRUE | INCLUDE | 70570.85 | 65.9 | 20.5 | 13 | 4.9 | 104.3 | 13 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | -63712.99
WO-00106 | Inspection – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 7228.41 | 3.5 | 1.8 | 4.1 | 0.2 | 9.6 | 1 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 73327.8
WO-00108 | Testing – Centrifugal Pump PMP-0037 | PMP-0037 | Pmp | Unit-200 | Testing | Critical | TRUE | TRUE | INCLUDE | 3770.09 | 9.6 | 15.2 | 6.4 | 1.6 | 32.8 | 4 | 0.82008 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17713.81 | 13943.72
WO-00109 | Cleaning – Heat Exchanger HX-0018 | HX-0018 | Hx | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 14191.21 | 18.5 | 0.1 | 0.3 | 3.3 | 22.2 | 3 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | HIGH | 33820.42 | 19629.21
WO-00110 | Inspection – Piping/Pipeline Segment PPL-0003 | PPL-0003 | Ppl | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 7422.22 | 6.1 | 1.2 | 2.4 | 0.3 | 10 | 1 | 0.25475 | 820.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12273.66 | 4851.44
WO-00112 | Inspection – Heat Exchanger HX-0025 | HX-0025 | Hx | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 3189.99 | 7.7 | 0.3 | 3.3 | 0.4 | 11.7 | 1 | 0.2607 | 1521.1654 | 4 | 3 | 4 | 12 | HIGH | 30502.19 | 27312.2
WO-00114 | Calibration – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1162.27 | 0.7 | 10 | 12.9 | 0.7 | 24.3 | 3 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | 1343.61
WO-00118 | Overhaul – Centrifugal Pump PMP-0067 | PMP-0067 | Pmp | Unit-300 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 379238.36 | 101.4 | 26.1 | 31.3 | 15.1 | 173.9 | 22 | 0.92495 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19978.83 | -359259.53
WO-00123 | Inspection – Storage Tank TNK-0018 | TNK-0018 | Tnk | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 627.57 | 4.6 | 1.2 | 2.8 | 0.3 | 8.9 | 1 | 0.071498 | 3671.2321 | 4 | 2 | 4 | 8 | MEDIUM | 16730.59 | 16103.02
WO-00124 | Testing – Control Valve VLV-0053 | VLV-0053 | Vlv | Utilities | Testing | Medium | FALSE | TRUE | INCLUDE | 2321.97 | 9.5 | 17 | 18.7 | 0.7 | 45.9 | 6 | 0.65711 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3526.23 | 1204.26
WO-00126 | Inspection – Centrifugal Pump PMP-0014 | PMP-0014 | Pmp | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 2021.65 | 2 | 1 | 3.1 | 0.7 | 6.8 | 1 | 0.84821 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18321.4 | 16299.75
WO-00128 | Cleaning – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Cleaning | Low | FALSE | TRUE | INCLUDE | 15602 | 20.4 | 0.2 | 1.3 | 9 | 30.9 | 4 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 32388.52
WO-00138 | Inspection – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 5415.91 | 6.7 | 0.3 | 4.5 | 0.4 | 11.9 | 1 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | 1441.95
WO-00139 | Replacement – Reciprocating Compressor CMP-0002 | CMP-0002 | Cmp | Utilities | Replacement | Medium | FALSE | TRUE | INCLUDE | 105033.52 | 55.7 | 10.8 | 23.1 | 8.9 | 98.5 | 12 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 172649.17 | 67615.65
WO-00140 | Repair – Heat Exchanger HX-0015 | HX-0015 | Hx | Utilities | Repair | Medium | FALSE | TRUE | INCLUDE | 31786.28 | 77.6 | 19 | 15 | 2.6 | 114.2 | 14 | 0.37181 | 451.1654 | 4 | 4 | 4 | 16 | HIGH | 43502.04 | 11715.76
WO-00142 | Cleaning – Reciprocating Compressor CMP-0010 | CMP-0010 | Cmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 8371.15 | 18.6 | 0.7 | 0.9 | 8.9 | 29.1 | 4 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 307515.33 | 299144.18
WO-00143 | Calibration – Control Valve VLV-0069 | VLV-0069 | Vlv | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1833.78 | 2 | 3.9 | 8.2 | 0.1 | 14.2 | 2 | 0.57942 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3109.29 | 1275.51
WO-00146 | Replacement – Heat Exchanger HX-0013 | HX-0013 | Hx | Unit-100 | Replacement | High | FALSE | TRUE | INCLUDE | 9603.6 | 55.7 | 9.3 | 10.6 | 1.8 | 77.4 | 10 | 0.49943 | 2190 | 4 | 4 | 4 | 16 | HIGH | 58433.39 | 48829.79
WO-00156 | Calibration – Pressure Vessel VSL-0021 | VSL-0021 | Vsl | Flare-System | Calibration | Critical | TRUE | TRUE | INCLUDE | 440.8 | 0.4 | 5.6 | 18.9 | 0.6 | 25.5 | 3 | 0.27583 | 1150.4951 | 5 | 3 | 5 | 15 | HIGH | 59992.23 | 59551.43
WO-00163 | Calibration – Centrifugal Pump PMP-0060 | PMP-0060 | Pmp | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 457.17 | 1.7 | 3.6 | 19.1 | 0.2 | 24.6 | 3 | 0.67091 | 1825 | 3 | 5 | 3 | 15 | HIGH | 14491.65 | 14034.48
WO-00164 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2492.37 | 1.5 | 9.7 | 8.3 | 0.8 | 20.3 | 3 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | 6923.67
WO-00166 | Cleaning – Centrifugal Pump PMP-0032 | PMP-0032 | Pmp | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 5277.9 | 19.5 | 0.4 | 0.1 | 7.5 | 27.5 | 3 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | HIGH | 9543.04 | 4265.14
WO-00169 | Replacement – Storage Tank TNK-0013 | TNK-0013 | Tnk | Flare-System | Replacement | Critical | TRUE | TRUE | INCLUDE | 56859.21 | 37.8 | 20 | 4.5 | 1 | 63.3 | 8 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | LOW | 11354.04 | -45505.17
WO-00175 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Inspection | High | FALSE | TRUE | INCLUDE | 4819.43 | 5.5 | 0.5 | 2.7 | 0.7 | 9.4 | 1 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | 2492.77
WO-00182 | Inspection – Control Valve VLV-0066 | VLV-0066 | Vlv | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 2036.35 | 9 | 0.3 | 1.1 | 0.5 | 10.9 | 1 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3450.07 | 1413.72
WO-00186 | Cleaning – Control Valve VLV-0088 | VLV-0088 | Vlv | Unit-100 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 22966.27 | 13.9 | 1.1 | 0.9 | 6.3 | 22.2 | 3 | 0.62881 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3374.35 | -19591.92
WO-00188 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Calibration | Critical | TRUE | TRUE | INCLUDE | 331.95 | 1.4 | 4.3 | 14.4 | 0.6 | 20.7 | 3 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | 9084.09
WO-00192 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | Inst | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 334.7 | 1.1 | 5.1 | 16.8 | 0.8 | 23.8 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 1105.3
WO-00196 | Calibration – Instrument/Analyser INST-0079 | INST-0079 | Inst | Unit-300 | Calibration | Low | FALSE | TRUE | INCLUDE | 920 | 1.8 | 7.3 | 17.3 | 0.6 | 27 | 3 | 0.94074 | 730 | 2 | 5 | 2 | 10 | HIGH | 1354.67 | 434.67
WO-00198 | Replacement – Control Valve VLV-0120 | VLV-0120 | Vlv | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 104771.88 | 27.4 | 5.1 | 15.7 | 4.8 | 53 | 7 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2846.98 | -101924.9
WO-00199 | Inspection – Control Valve VLV-0108 | VLV-0108 | Vlv | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 2045.05 | 8.2 | 1.8 | 3.2 | 0.1 | 13.3 | 2 | 0.66731 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3580.94 | 1535.89
WO-00203 | Inspection – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 2067.41 | 8.6 | 2 | 1.4 | 0.1 | 12.1 | 2 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 45923.11
WO-00204 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Inspection | Critical | FALSE | TRUE | INCLUDE | 1107.34 | 9.1 | 1.6 | 4.5 | 0.7 | 15.9 | 2 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | 6757.68
WO-00205 | Repair – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Repair | High | FALSE | TRUE | INCLUDE | 25300.43 | 33.3 | 27 | 14.3 | 9.1 | 83.7 | 10 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -23972.73
WO-00206 | Testing – Electrical Equipment ELEC-0029 | ELEC-0029 | Elec | Unit-300 | Testing | Medium | FALSE | TRUE | INCLUDE | 9384.76 | 14 | 22.3 | 11.6 | 1.4 | 49.3 | 6 | 0.45763 | 611.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4118.71 | -5266.05
WO-00211 | Calibration – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 2652.36 | 0.5 | 6.2 | 7.6 | 0 | 14.3 | 2 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 45789.59 | WO-00206
WO-00214 | Calibration – Electrical Equipment ELEC-0014 | ELEC-0014 | Elec | Tank-Farm | Calibration | Low | FALSE | TRUE | INCLUDE | 570.86 | 0.2 | 8.2 | 14 | 0.5 | 22.9 | 3 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5975.81 | 5404.95
WO-00216 | Calibration – Centrifugal Pump PMP-0032 | PMP-0032 | Pmp | Unit-300 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2174.74 | 1.7 | 2.5 | 16.1 | 0.5 | 20.8 | 3 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | HIGH | 9543.04 | 7368.3
WO-00217 | Calibration – Pressure Vessel VSL-0014 | VSL-0014 | Vsl | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 2206.31 | 1 | 8.4 | 8.8 | 0.2 | 18.4 | 2 | 0.16034 | 2291.4951 | 5 | 3 | 5 | 15 | HIGH | 34874.61 | 32668.3
WO-00219 | Calibration – Instrument/Analyser INST-0025 | INST-0025 | Inst | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 894.88 | 1.1 | 8.3 | 14.7 | 0.3 | 24.4 | 3 | 0.9248 | 730 | 2 | 5 | 2 | 10 | HIGH | 1331.72 | 436.84
WO-00220 | Cleaning – Heat Exchanger HX-0010 | HX-0010 | Hx | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 14187.23 | 6.3 | 1.7 | 1 | 5.8 | 14.8 | 2 | 0.41891 | 2190 | 4 | 4 | 4 | 16 | HIGH | 49012.24 | 34825.01
WO-00223 | Inspection – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Inspection | High | FALSE | TRUE | INCLUDE | 6673.77 | 6.7 | 1 | 3.2 | 0.3 | 11.2 | 1 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | 12327.01
WO-00224 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | Pmp | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 5380.49 | 7.9 | 1.3 | 2.3 | 0.8 | 12.3 | 2 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18327.69 | 12947.2
WO-00226 | Overhaul – Centrifugal Pump PMP-0050 | PMP-0050 | Pmp | Unit-200 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 370320.49 | 75.3 | 37.9 | 19.8 | 10.2 | 143.2 | 18 | 0.14641 | 1885.705 | 3 | 2 | 3 | 6 | MEDIUM | 3162.56 | -367157.93
WO-00227 | Calibration – Electrical Equipment ELEC-0061 | ELEC-0061 | Elec | Offsites | Calibration | Low | FALSE | TRUE | INCLUDE | 2887.48 | 1 | 2.3 | 8.2 | 0.2 | 11.7 | 1 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6951.19 | 4063.71
WO-00230 | Calibration – Heat Exchanger HX-0028 | HX-0028 | Hx | Unit-100 | Calibration | Critical | TRUE | TRUE | INCLUDE | 1501.64 | 1.8 | 7.1 | 14 | 0.3 | 23.2 | 3 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | HIGH | 64199.97 | 62698.33
WO-00234 | Replacement – Centrifugal Pump PMP-0001 | PMP-0001 | Pmp | Offsites | Replacement | Critical | TRUE | TRUE | INCLUDE | 40584.87 | 21 | 6.8 | 15.1 | 3.2 | 46.1 | 6 | 0.85591 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18487.66 | -22097.21
WO-00235 | Cleaning – Instrument/Analyser INST-0037 | INST-0037 | Inst | Unit-300 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 21064.63 | 20.6 | 1.2 | 0.3 | 8.5 | 30.6 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -19624.63
WO-00238 | Replacement – Centrifugal Pump PMP-0033 | PMP-0033 | Pmp | Offsites | Replacement | Critical | FALSE | TRUE | INCLUDE | 6660 | 16.1 | 11 | 10.2 | 7.2 | 44.5 | 6 | 0.80677 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17426.28 | 10766.28
WO-00244 | Inspection – Centrifugal Pump PMP-0038 | PMP-0038 | Pmp | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 4811.88 | 3.3 | 0.1 | 3 | 0.7 | 7.1 | 1 | 0.63144 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13639.2 | 8827.32
WO-00245 | Calibration – Centrifugal Pump PMP-0020 | PMP-0020 | Pmp | Unit-200 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2600.27 | 1.5 | 7.6 | 4.2 | 0.6 | 13.9 | 2 | 0.80713 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17433.92 | 14833.65
WO-00246 | Inspection – Centrifugal Pump PMP-0062 | PMP-0062 | Pmp | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 1757.45 | 8.6 | 1.5 | 4.8 | 1 | 15.9 | 2 | 0.61872 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13364.33 | 11606.88
WO-00249 | Repair – Pressure Vessel VSL-0019 | VSL-0019 | Vsl | Unit-200 | Repair | Medium | FALSE | TRUE | INCLUDE | 24195.92 | 28.2 | 15.1 | 10.2 | 1.1 | 54.6 | 7 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | CRITICAL | 80556.21 | 56360.29
WO-00250 | Testing – Centrifugal Pump PMP-0049 | PMP-0049 | Pmp | Unit-100 | Testing | High | FALSE | TRUE | INCLUDE | 8166.02 | 9 | 11.9 | 5.9 | 0.5 | 27.3 | 3 | 0.88977 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19218.98 | 11052.96
WO-00251 | Overhaul – Pressure Vessel VSL-0006 | VSL-0006 | Vsl | Unit-300 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 333845.33 | 209.8 | 17.5 | 9.2 | 4.8 | 241.3 | 30 | 0.43349 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 94283.4 | -239561.93
WO-00254 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 695.06 | 3.5 | 1.6 | 3.1 | 0.6 | 8.8 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 744.94
WO-00256 | Calibration – Control Valve VLV-0073 | VLV-0073 | Vlv | Offsites | Calibration | High | FALSE | TRUE | INCLUDE | 1576.51 | 0.5 | 4.8 | 15.7 | 0.1 | 21.1 | 3 | 0.48307 | 183.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2592.27 | 1015.76
WO-00262 | Inspection – Centrifugal Pump PMP-0034 | PMP-0034 | Pmp | Unit-100 | Inspection | Critical | FALSE | TRUE | INCLUDE | 4557.53 | 2.9 | 0.6 | 3.6 | 0.7 | 7.8 | 1 | 0.32905 | 1161.7051 | 3 | 3 | 3 | 9 | MEDIUM | 7107.46 | 2549.93
WO-00263 | Replacement – Centrifugal Pump PMP-0004 | PMP-0004 | Pmp | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 33394.56 | 57.8 | 5.4 | 7.7 | 5 | 75.9 | 9 | 0.9286 | 1825 | 3 | 5 | 3 | 15 | HIGH | 20057.78 | -13336.78
WO-00264 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Inspection | Critical | FALSE | TRUE | INCLUDE | 1309.51 | 7.1 | 1.2 | 3.6 | 0.8 | 12.7 | 2 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 37489.01
WO-00266 | Inspection – Centrifugal Pump PMP-0023 | PMP-0023 | Pmp | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3939.48 | 2.3 | 0 | 4.7 | 0.7 | 7.7 | 1 | 0.53872 | 289.705 | 3 | 4 | 3 | 12 | HIGH | 11636.29 | 7696.81
WO-00267 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Replacement | Critical | TRUE | TRUE | INCLUDE | 70611.87 | 54.4 | 13.7 | 16 | 5.1 | 89.2 | 11 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | -55051.1
WO-00269 | Calibration – Pressure Vessel VSL-0028 | VSL-0028 | Vsl | Flare-System | Calibration | Medium | FALSE | TRUE | INCLUDE | 1205.72 | 0.7 | 5.4 | 4.6 | 0.5 | 11.2 | 1 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | HIGH | 58882.1 | 57676.38
WO-00271 | Repair – Reciprocating Compressor CMP-0015 | CMP-0015 | Cmp | Tank-Farm | Repair | Medium | FALSE | TRUE | INCLUDE | 12613.64 | 25.9 | 16.6 | 2.8 | 4.7 | 50 | 6 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 162580.25 | 149966.61
WO-00277 | Calibration – Electrical Equipment ELEC-0063 | ELEC-0063 | Elec | Flare-System | Calibration | Low | FALSE | TRUE | INCLUDE | 831.83 | 0.7 | 2.6 | 10.7 | 0.7 | 14.7 | 2 | 0.70669 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6360.25 | 5528.42
WO-00278 | Cleaning – Control Valve VLV-0065 | VLV-0065 | Vlv | Flare-System | Cleaning | Critical | TRUE | TRUE | INCLUDE | 16361.74 | 8.3 | 0.1 | 1.6 | 3.3 | 13.3 | 2 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3625.6 | -12736.14
WO-00281 | Repair – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Repair | Critical | TRUE | TRUE | INCLUDE | 12795.42 | 13 | 22.3 | 10.2 | 8.5 | 54 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -11355.42
WO-00282 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Calibration | Critical | TRUE | TRUE | INCLUDE | 304.54 | 0.1 | 5.7 | 7.5 | 0.6 | 13.9 | 2 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | 17871.71
WO-00286 | Calibration – Piping/Pipeline Segment PPL-0039 | PPL-0039 | Ppl | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2452.58 | 1.3 | 4.2 | 19.4 | 0.2 | 25.1 | 3 | 0.089837 | 3775.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 4328.35 | 1875.77
WO-00288 | Calibration – Control Valve VLV-0116 | VLV-0116 | Vlv | Utilities | Calibration | Medium | FALSE | TRUE | INCLUDE | 638.97 | 1.7 | 9.6 | 6.4 | 0.7 | 18.4 | 2 | 0.52354 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2809.43 | 2170.46
WO-00294 | Repair – Reciprocating Compressor CMP-0010 | CMP-0010 | Cmp | Flare-System | Repair | Low | FALSE | TRUE | INCLUDE | 61530.83 | 47.9 | 11.1 | 11 | 4 | 74 | 9 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 307515.33 | 245984.5
WO-00296 | Replacement – Control Valve VLV-0055 | VLV-0055 | Vlv | Unit-100 | Replacement | Critical | TRUE | TRUE | INCLUDE | 54746.52 | 18.7 | 12 | 18 | 8.9 | 57.6 | 7 | 0.44001 | 617.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2361.21 | -52385.31
WO-00301 | Inspection – Electrical Equipment ELEC-0019 | ELEC-0019 | Elec | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 2136.85 | 2 | 1 | 1.8 | 0.7 | 5.5 | 1 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4601.34 | 2464.49
WO-00308 | Calibration – Piping/Pipeline Segment PPL-0004 | PPL-0004 | Ppl | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1026.88 | 0.6 | 5.9 | 8.4 | 0.7 | 15.6 | 2 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | HIGH | 15082.22 | 14055.34
WO-00321 | Repair – Storage Tank TNK-0015 | TNK-0015 | Tnk | Unit-300 | Repair | Critical | TRUE | TRUE | INCLUDE | 21241.18 | 92.9 | 17.5 | 6.7 | 8.6 | 125.7 | 16 | 0.031924 | 4647.2321 | 4 | 1 | 4 | 4 | LOW | 7470.16 | -13771.02
WO-00323 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 3419.29 | 8.8 | 0.3 | 4.5 | 0.2 | 13.8 | 2 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | 2358.72
WO-00327 | Calibration – Heat Exchanger HX-0004 | HX-0004 | Hx | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 698.54 | 1 | 4.1 | 4.1 | 1 | 10.2 | 1 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | HIGH | 43691.97 | 42993.43
WO-00330 | Inspection – Piping/Pipeline Segment PPL-0013 | PPL-0013 | Ppl | Unit-300 | Inspection | Critical | FALSE | TRUE | INCLUDE | 6017.98 | 2.8 | 1.7 | 1.9 | 0.1 | 6.5 | 1 | 0.15413 | 2692.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7426.16 | 1408.18
WO-00334 | Inspection – Pressure Vessel VSL-0004 | VSL-0004 | Vsl | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 7118.26 | 6.6 | 1.6 | 2.1 | 0.1 | 10.4 | 1 | 0.12966 | 2628.4951 | 5 | 2 | 5 | 10 | HIGH | 28201.02 | 21082.76
WO-00336 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | Ppl | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 1132.77 | 2.2 | 1.8 | 2.2 | 0.7 | 6.9 | 1 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12169.06 | 11036.29 | WO-00205
WO-00339 | Calibration – Electrical Equipment ELEC-0048 | ELEC-0048 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1535.59 | 0.4 | 8.8 | 9.9 | 0.3 | 19.4 | 2 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4217.99 | 2682.4
WO-00345 | Cleaning – Centrifugal Pump PMP-0074 | PMP-0074 | Pmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 4776.27 | 7.7 | 1.7 | 0.6 | 7 | 17 | 2 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13573.13 | 8796.86
WO-00346 | Repair – Centrifugal Pump PMP-0061 | PMP-0061 | Pmp | Utilities | Repair | Critical | TRUE | TRUE | INCLUDE | 59711.78 | 85.3 | 20.3 | 10.1 | 4.5 | 120.2 | 15 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | MEDIUM | 5761.08 | -53950.7
WO-00349 | Inspection – Heat Exchanger HX-0030 | HX-0030 | Hx | Unit-100 | Inspection | Critical | TRUE | TRUE | INCLUDE | 5016.6 | 8.3 | 0.7 | 3.4 | 0.4 | 12.8 | 2 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | HIGH | 47081.26 | 42064.66
WO-00350 | Inspection – Electrical Equipment ELEC-0085 | ELEC-0085 | Elec | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 1301.98 | 2.8 | 1.2 | 3.1 | 0.5 | 7.6 | 1 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7020.85 | 5718.87
WO-00351 | Inspection – Centrifugal Pump PMP-0064 | PMP-0064 | Pmp | Unit-300 | Inspection | Medium | FALSE | TRUE | INCLUDE | 2605.28 | 8.2 | 1.8 | 2.8 | 0.1 | 12.9 | 2 | 0.77315 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16700.13 | 14094.85
WO-00353 | Replacement – Reciprocating Compressor CMP-0013 | CMP-0013 | Cmp | Flare-System | Replacement | Critical | FALSE | TRUE | INCLUDE | 78932.16 | 51.3 | 10.6 | 20.4 | 4.5 | 86.8 | 11 | 0.67268 | 331.9307 | 4.75 | 5 | 5 | 25 | CRITICAL | 234850.27 | 155918.11
WO-00357 | Calibration – Centrifugal Pump PMP-0066 | PMP-0066 | Pmp | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 1829.05 | 1.3 | 6.4 | 16.4 | 0.2 | 24.3 | 3 | 0.22202 | 1579.705 | 3 | 3 | 3 | 9 | MEDIUM | 4795.66 | 2966.61
WO-00360 | Inspection – Centrifugal Pump PMP-0018 | PMP-0018 | Pmp | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 4313.36 | 3.5 | 1.3 | 1.8 | 0.1 | 6.7 | 1 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13798.72 | 9485.36 | WO-00096
WO-00361 | Cleaning – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 23474.82 | 15.8 | 0.1 | 1.1 | 6.5 | 23.5 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -22034.82
WO-00365 | Replacement – Reciprocating Compressor CMP-0004 | CMP-0004 | Cmp | Unit-200 | Replacement | Critical | FALSE | TRUE | INCLUDE | 114652.62 | 59.8 | 8.7 | 18.2 | 4.7 | 91.4 | 11 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 234472.38
WO-00367 | Inspection – Centrifugal Pump PMP-0039 | PMP-0039 | Pmp | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3003.2 | 6.2 | 0.7 | 3.1 | 0 | 10 | 1 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15725.17 | 12721.97
WO-00369 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Inspection | Critical | FALSE | TRUE | INCLUDE | 3028.98 | 7.4 | 0.2 | 1.3 | 0.7 | 9.6 | 1 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 86412.66
WO-00371 | Cleaning – Reciprocating Compressor CMP-0012 | CMP-0012 | Cmp | Unit-100 | Cleaning | Low | FALSE | TRUE | INCLUDE | 8722.69 | 5.5 | 0.4 | 0.3 | 3 | 9.2 | 1 | 0.71599 | 221.9307 | 4.75 | 5 | 5 | 25 | CRITICAL | 249970.39 | 241247.7
WO-00376 | Inspection – Centrifugal Pump PMP-0042 | PMP-0042 | Pmp | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 2527.83 | 9.3 | 0.6 | 4.9 | 0.2 | 15 | 2 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15665.17 | 13137.34
WO-00377 | Cleaning – Pressure Vessel VSL-0027 | VSL-0027 | Vsl | Unit-200 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 17724.88 | 19.5 | 1.4 | 1.8 | 6.5 | 29.2 | 4 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | CRITICAL | 89441.64 | 71716.76
WO-00379 | Calibration – Centrifugal Pump PMP-0071 | PMP-0071 | Pmp | Tank-Farm | Calibration | Critical | FALSE | TRUE | INCLUDE | 2200.04 | 1.4 | 9.1 | 13.5 | 1 | 25 | 3 | 0.82667 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17856.16 | 15656.12
WO-00382 | Inspection – Centrifugal Pump PMP-0054 | PMP-0054 | Pmp | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 5022.52 | 6.5 | 1.5 | 2.4 | 0.2 | 10.6 | 1 | 0.79554 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17183.71 | 12161.19
WO-00383 | Cleaning – Reciprocating Compressor CMP-0001 | CMP-0001 | Cmp | Unit-200 | Cleaning | Low | FALSE | TRUE | INCLUDE | 1651.36 | 23.7 | 0.4 | 1.6 | 7.6 | 33.3 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 347473.64
WO-00384 | Testing – Centrifugal Pump PMP-0052 | PMP-0052 | Pmp | Unit-300 | Testing | Critical | FALSE | TRUE | INCLUDE | 4478.95 | 15.8 | 10.3 | 16.6 | 1.2 | 43.9 | 5 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17151.61 | 12672.66
WO-00387 | Cleaning – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Cleaning | Critical | TRUE | TRUE | INCLUDE | 13685.79 | 25.4 | 0.9 | 1.6 | 2.4 | 30.3 | 4 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | 1874.98
WO-00388 | Cleaning – Reciprocating Compressor CMP-0005 | CMP-0005 | Cmp | Flare-System | Cleaning | Low | FALSE | TRUE | INCLUDE | 2766.69 | 27.4 | 0 | 1.4 | 3.9 | 32.7 | 4 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 346358.31
WO-00389 | Replacement – Piping/Pipeline Segment PPL-0030 | PPL-0030 | Ppl | Tank-Farm | Replacement | Critical | FALSE | TRUE | INCLUDE | 8137.59 | 9.4 | 12 | 23.7 | 9.8 | 54.9 | 7 | 0.28825 | 140.7483 | 3.65 | 3 | 4 | 12 | HIGH | 13887.95 | 5750.36
WO-00392 | Calibration – Distillation Tower TWR-0011 | TWR-0011 | Twr | Unit-100 | Calibration | Critical | FALSE | TRUE | INCLUDE | 2683.66 | 1.9 | 7.3 | 7.2 | 0.1 | 16.5 | 2 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | HIGH | 189640.61 | 186956.95
WO-00395 | Cleaning – Centrifugal Pump PMP-0009 | PMP-0009 | Pmp | Unit-300 | Cleaning | Critical | FALSE | TRUE | INCLUDE | 10759.29 | 8.1 | 0 | 0.5 | 2.5 | 11.1 | 1 | 0.78238 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16899.41 | 6140.12
WO-00399 | Calibration – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Calibration | Medium | FALSE | TRUE | INCLUDE | 960.38 | 0.4 | 4.6 | 11.7 | 0.6 | 17.3 | 2 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 47030.14
WO-00400 | Calibration – Electrical Equipment ELEC-0041 | ELEC-0041 | Elec | Offsites | Calibration | Critical | TRUE | TRUE | INCLUDE | 2093.22 | 0.5 | 5.8 | 9.4 | 0.2 | 15.9 | 2 | 0.4567 | 616.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4110.34 | 2017.12
WO-00403 | Calibration – Electrical Equipment ELEC-0071 | ELEC-0071 | Elec | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 2709.86 | 0.8 | 7.5 | 7.7 | 0.7 | 16.7 | 2 | 0.82756 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7448.04 | 4738.18
WO-00406 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 580.71 | 0.5 | 7.7 | 6.5 | 0.4 | 15.1 | 2 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6437.74 | 5857.03
WO-00407 | Calibration – Heat Exchanger HX-0030 | HX-0030 | Hx | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 465.67 | 1.7 | 7.8 | 9.4 | 0.8 | 19.7 | 2 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | HIGH | 47081.26 | 46615.59
WO-00410 | Calibration – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Calibration | Critical | TRUE | TRUE | INCLUDE | 2808.8 | 0.8 | 7.7 | 7.1 | 0.5 | 16.1 | 2 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 35989.72
WO-00413 | Inspection – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Inspection | High | FALSE | TRUE | INCLUDE | 3580.68 | 4.1 | 0.6 | 1.7 | 0.7 | 7.1 | 1 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 10602.92
WO-00415 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 2139.15 | 0.7 | 4.8 | 4.1 | 1 | 10.6 | 1 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | 16037.1
WO-00421 | Cleaning – Centrifugal Pump PMP-0042 | PMP-0042 | Pmp | Utilities | Cleaning | Medium | FALSE | TRUE | INCLUDE | 7957.4 | 20.9 | 1.6 | 0.9 | 9.9 | 33.3 | 4 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15665.17 | 7707.77
WO-00423 | Cleaning – Heat Exchanger HX-0028 | HX-0028 | Hx | Unit-100 | Cleaning | Medium | FALSE | TRUE | INCLUDE | 2172.64 | 14.8 | 1.8 | 1.4 | 2.4 | 20.4 | 3 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | HIGH | 64199.97 | 62027.33
WO-00426 | Calibration – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Calibration | Critical | FALSE | TRUE | INCLUDE | 1298.77 | 1.3 | 6.9 | 15.8 | 0.7 | 24.7 | 3 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | 4479.24
WO-00428 | Inspection – Distillation Tower TWR-0007 | TWR-0007 | Twr | Flare-System | Inspection | Low | FALSE | TRUE | INCLUDE | 3326.04 | 4.1 | 1.7 | 1.6 | 0.6 | 8 | 1 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 271562.17 | 268236.13 | WO-00330
WO-00429 | Calibration – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Calibration | Low | FALSE | TRUE | INCLUDE | 421.85 | 1.8 | 7.1 | 11.3 | 0.7 | 20.9 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 1018.15 | WO-00323
WO-00433 | Calibration – Electrical Equipment ELEC-0015 | ELEC-0015 | Elec | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 1177.95 | 1.9 | 5.4 | 8.4 | 0.4 | 16.1 | 2 | 0.2416 | 1590.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2174.38 | 996.43
WO-00436 | Cleaning – Heat Exchanger HX-0004 | HX-0004 | Hx | Unit-100 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 9155.54 | 15.4 | 0.5 | 0.3 | 2.3 | 18.5 | 2 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | HIGH | 43691.97 | 34536.43
WO-00438 | Cleaning – Distillation Tower TWR-0007 | TWR-0007 | Twr | Flare-System | Cleaning | Critical | FALSE | TRUE | INCLUDE | 12497.54 | 22.5 | 1.8 | 1.6 | 3.5 | 29.4 | 4 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 271562.17 | 259064.63
WO-00442 | Inspection – Pressure Vessel VSL-0010 | VSL-0010 | Vsl | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 855.01 | 3.8 | 0.5 | 1.1 | 0.2 | 5.6 | 1 | 0.28693 | 1046.4952 | 5 | 3 | 5 | 15 | HIGH | 62407.43 | 61552.42
WO-00444 | Replacement – Distillation Tower TWR-0005 | TWR-0005 | Twr | Tank-Farm | Replacement | High | FALSE | TRUE | INCLUDE | 41950.13 | 34.8 | 11.8 | 4.3 | 9.6 | 60.5 | 8 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | HIGH | 44001.97 | 2051.84
WO-00449 | Inspection – Reciprocating Compressor CMP-0007 | CMP-0007 | Cmp | Flare-System | Inspection | Medium | FALSE | TRUE | INCLUDE | 3247.37 | 3.8 | 1.8 | 4.5 | 0.8 | 10.9 | 1 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 339618.52 | 336371.15
WO-00450 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 957.92 | 7.2 | 1.3 | 2.5 | 0.5 | 11.5 | 1 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | 432.66
WO-00452 | Calibration – Control Valve VLV-0038 | VLV-0038 | Vlv | Tank-Farm | Calibration | Low | FALSE | TRUE | INCLUDE | 517.82 | 1.3 | 5.9 | 13.2 | 0 | 20.4 | 3 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3387.34 | 2869.52
WO-00453 | Testing – Control Valve VLV-0079 | VLV-0079 | Vlv | Unit-300 | Testing | High | FALSE | TRUE | INCLUDE | 550.49 | 5.8 | 7.6 | 19.6 | 1.2 | 34.2 | 4 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3315.02 | 2764.53
WO-00454 | Calibration – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Calibration | High | FALSE | TRUE | INCLUDE | 1189.73 | 0.9 | 5.1 | 12.3 | 0.5 | 18.8 | 2 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | 2284.68
WO-00455 | Overhaul – Heat Exchanger HX-0014 | HX-0014 | Hx | Unit-100 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 546377.23 | 140.6 | 46.5 | 31.1 | 19.4 | 237.6 | 30 | 0.3698 | 472.1654 | 4 | 4 | 4 | 16 | HIGH | 43266.74 | -503110.49
WO-00456 | Calibration – Heat Exchanger HX-0016 | HX-0016 | Hx | Flare-System | Calibration | Low | FALSE | TRUE | INCLUDE | 940.1 | 0 | 3.3 | 4.3 | 0.9 | 8.5 | 1 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | HIGH | 47990.52 | 47050.42 | WO-00444
WO-00457 | Calibration – Reciprocating Compressor CMP-0002 | CMP-0002 | Cmp | Utilities | Calibration | High | FALSE | TRUE | INCLUDE | 502.76 | 1.8 | 8 | 9.3 | 0.5 | 19.6 | 2 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 172649.17 | 172146.41
WO-00458 | Inspection – Distillation Tower TWR-0005 | TWR-0005 | Twr | Tank-Farm | Inspection | Medium | FALSE | TRUE | INCLUDE | 4311.4 | 7.9 | 0.4 | 2.8 | 0.5 | 11.6 | 1 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | HIGH | 44001.97 | 39690.57
WO-00461 | Inspection – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Inspection | Medium | FALSE | TRUE | INCLUDE | 3203.31 | 5.7 | 0.3 | 1.8 | 0.2 | 8 | 1 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | 2180.54
WO-00465 | Inspection – Centrifugal Pump PMP-0019 | PMP-0019 | Pmp | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 653.07 | 9.1 | 1.3 | 2.2 | 0.2 | 12.8 | 2 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | MEDIUM | 2786.64 | 2133.57 | WO-00264
WO-00467 | Inspection – Distillation Tower TWR-0009 | TWR-0009 | Twr | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 3855.98 | 4.4 | 1.8 | 1.1 | 0.6 | 7.9 | 1 | 0.052723 | 3696.054 | 5 | 2 | 5 | 10 | HIGH | 38751.19 | 34895.21
WO-00470 | Calibration – Storage Tank TNK-0020 | TNK-0020 | Tnk | Flare-System | Calibration | High | FALSE | TRUE | INCLUDE | 1752.49 | 0.8 | 3.2 | 20 | 0.6 | 24.6 | 3 | 0.16756 | 2160.2321 | 4 | 3 | 4 | 12 | HIGH | 39208.79 | 37456.3
WO-00475 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | Elec | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 2564.76 | 0.6 | 7.9 | 5.7 | 0.1 | 14.3 | 2 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6437.74 | 3872.98
WO-00476 | Inspection – Pressure Vessel VSL-0018 | VSL-0018 | Vsl | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 7612.97 | 9.2 | 0.1 | 4.4 | 0.5 | 14.2 | 2 | 0.39382 | 59.4951 | 5 | 4 | 5 | 20 | CRITICAL | 85654.78 | 78041.81
WO-00480 | Inspection – Piping/Pipeline Segment PPL-0001 | PPL-0001 | Ppl | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 2185.49 | 8.1 | 1.6 | 4.1 | 0.1 | 13.9 | 2 | 0.26868 | 541.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12944.99 | 10759.5
WO-00488 | Cleaning – Instrument/Analyser INST-0053 | INST-0053 | Inst | Tank-Farm | Cleaning | Critical | TRUE | TRUE | INCLUDE | 11435.72 | 22.7 | 0.9 | 0.5 | 4.2 | 28.3 | 4 | 0.54637 | 720.2559 | 2 | 4 | 2 | 8 | MEDIUM | 786.77 | -10648.95
WO-00493 | Calibration – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1831.79 | 1.1 | 7.2 | 8.6 | 0.8 | 17.7 | 2 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | 5981.24
WO-00496 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Inspection | Critical | TRUE | TRUE | INCLUDE | 5983.92 | 5 | 2 | 3.8 | 0.1 | 10.9 | 1 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | 10672.67
WO-00499 | Calibration – Electrical Equipment ELEC-0065 | ELEC-0065 | Elec | Unit-200 | Calibration | High | FALSE | TRUE | INCLUDE | 2570.52 | 1.1 | 3.9 | 15.4 | 0.5 | 20.9 | 3 | 0.75345 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6781.01 | 4210.49
WO-00500 | Overhaul – Centrifugal Pump PMP-0058 | PMP-0058 | Pmp | Unit-100 | Overhaul | Critical | TRUE | TRUE | INCLUDE | 386381.53 | 187.1 | 18.2 | 44.8 | 11.6 | 261.7 | 33 | 0.82968 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17921.13 | -368460.4
WO-00501 | Inspection – Reciprocating Compressor CMP-0017 | CMP-0017 | Cmp | Offsites | Inspection | Medium | FALSE | TRUE | INCLUDE | 6550.87 | 4.8 | 1 | 1.9 | 0.7 | 8.4 | 1 | 1 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 349125 | 342574.13
WO-00503 | Cleaning – Centrifugal Pump PMP-0027 | PMP-0027 | Pmp | Flare-System | Cleaning | High | FALSE | TRUE | INCLUDE | 8641.27 | 17.3 | 1.3 | 1.9 | 5.6 | 26.1 | 3 | 0.79898 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17257.88 | 8616.61
WO-00505 | Calibration – Control Valve VLV-0120 | VLV-0120 | Vlv | Unit-100 | Calibration | Medium | FALSE | TRUE | INCLUDE | 720.04 | 1.9 | 7.5 | 5.4 | 0.7 | 15.5 | 2 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2846.98 | 2126.94 | WO-00377
WO-00508 | Calibration – Storage Tank TNK-0001 | TNK-0001 | Tnk | Unit-200 | Calibration | Medium | FALSE | TRUE | INCLUDE | 1731.6 | 1.7 | 6.6 | 11.7 | 0.3 | 20.3 | 3 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | HIGH | 50668.31 | 48936.71
WO-00511 | Inspection – Instrument/Analyser INST-0144 | INST-0144 | Inst | Utilities | Inspection | Medium | FALSE | TRUE | INCLUDE | 920.65 | 4.1 | 0.2 | 3.2 | 0.1 | 7.6 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 519.35
WO-00513 | Inspection – Centrifugal Pump PMP-0005 | PMP-0005 | Pmp | Tank-Farm | Inspection | High | FALSE | TRUE | INCLUDE | 3261.87 | 4.4 | 0.4 | 3.8 | 0.7 | 9.3 | 1 | 0.84976 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18354.81 | 15092.94
WO-00514 | Repair – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Repair | Critical | FALSE | TRUE | INCLUDE | 10044.83 | 21.8 | 14 | 13.8 | 6.3 | 55.9 | 7 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 4138.77 | WO-00217
WO-00516 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Inspection | Critical | TRUE | TRUE | INCLUDE | 5179.19 | 8.6 | 1 | 2.4 | 1 | 13 | 2 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | 11477.4
WO-00519 | Inspection – Heat Exchanger HX-0001 | HX-0001 | Hx | Unit-100 | Inspection | Critical | TRUE | TRUE | INCLUDE | 3858.79 | 2 | 1.4 | 2.2 | 0.6 | 6.2 | 1 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48649.09 | 44790.3
WO-00520 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Inspection | High | FALSE | TRUE | INCLUDE | 5209.16 | 4.4 | 0.4 | 1.9 | 0.2 | 6.9 | 1 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | 2655.86
WO-00521 | Inspection – Storage Tank TNK-0001 | TNK-0001 | Tnk | Unit-200 | Inspection | Low | FALSE | TRUE | INCLUDE | 3284.03 | 7.5 | 1 | 3.4 | 0.3 | 12.2 | 2 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | HIGH | 50668.31 | 47384.28
WO-00525 | Inspection – Storage Tank TNK-0009 | TNK-0009 | Tnk | Unit-200 | Inspection | Medium | FALSE | TRUE | INCLUDE | 916.94 | 7.1 | 0.3 | 3.1 | 0 | 10.5 | 1 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | HIGH | 48441.95 | 47525.01
WO-00529 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | Ppl | Offsites | Inspection | Critical | TRUE | TRUE | INCLUDE | 4145.6 | 3.9 | 1.9 | 3.2 | 0.9 | 9.9 | 1 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | HIGH | 12169.06 | 8023.46
WO-00530 | Inspection – Storage Tank TNK-0005 | TNK-0005 | Tnk | Flare-System | Inspection | High | FALSE | TRUE | INCLUDE | 6339.85 | 7.6 | 1.1 | 4.3 | 0.8 | 13.8 | 2 | 0.036789 | 4499.2321 | 4 | 1 | 4 | 4 | LOW | 8608.56 | 2268.71
WO-00532 | Calibration – Reciprocating Compressor CMP-0008 | CMP-0008 | Cmp | Unit-100 | Calibration | High | FALSE | TRUE | INCLUDE | 1126.86 | 1.3 | 3.6 | 8.2 | 0.9 | 14 | 2 | 0.80752 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 281925.94 | 280799.08
WO-00535 | Inspection – Centrifugal Pump PMP-0041 | PMP-0041 | Pmp | Offsites | Inspection | Low | FALSE | TRUE | INCLUDE | 6794.62 | 3.4 | 0.8 | 4.4 | 0.5 | 9.1 | 1 | 0.79812 | 1825 | 3 | 5 | 3 | 15 | HIGH | 17239.43 | 10444.81
WO-00536 | Replacement – Reciprocating Compressor CMP-0007 | CMP-0007 | Cmp | Flare-System | Replacement | Medium | FALSE | TRUE | INCLUDE | 87251.78 | 58.9 | 11.9 | 17.8 | 4.5 | 93.1 | 12 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | CRITICAL | 339618.52 | 252366.74 | WO-00024
WO-00542 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | Vsl | Tank-Farm | Inspection | Low | FALSE | TRUE | INCLUDE | 4024.07 | 2.8 | 0.7 | 1.3 | 0.3 | 5.1 | 1 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | HIGH | 38798.52 | 34774.45
WO-00544 | Inspection – Reciprocating Compressor CMP-0014 | CMP-0014 | Cmp | Unit-100 | Inspection | Medium | FALSE | TRUE | INCLUDE | 6140.48 | 7.8 | 1.4 | 1.1 | 0.3 | 10.6 | 1 | 0.38692 | 935.9307 | 4.75 | 4 | 5 | 20 | CRITICAL | 135084.24 | 128943.76
WO-00545 | Cleaning – Pressure Vessel VSL-0025 | VSL-0025 | Vsl | Unit-200 | Cleaning | Critical | TRUE | TRUE | INCLUDE | 15452.68 | 11.1 | 0.5 | 1.9 | 7.8 | 21.3 | 3 | 0.04163 | 3821.4951 | 5 | 1 | 5 | 5 | MEDIUM | 9054.44 | -6398.24
WO-00546 | Testing – Heat Exchanger HX-0029 | HX-0029 | Hx | Unit-200 | Testing | High | FALSE | TRUE | INCLUDE | 8944.37 | 8 | 11.9 | 18.5 | 0.8 | 39.2 | 5 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | HIGH | 26996.81 | 18052.44
WO-00547 | Calibration – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Calibration | Medium | FALSE | TRUE | INCLUDE | 747.05 | 1.9 | 4.8 | 10.7 | 0.7 | 18.1 | 2 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | 352.38

## Deferred
wo_id | description | asset_tag | asset_class | area | task_type | priority | mandatory | selected | decision | estimated_cost_usd | mech_hours | elec_hours | inst_hours | civil_hours | total_craft_hours | duration_days | failure_prob | rul_days | consequence_score | likelihood_tier | consequence_tier | risk_score | risk_level | deferred_cost_usd | net_value_usd | predecessor_wo_id
WO-00001 | Overhaul – Electrical Equipment ELEC-0024 | ELEC-0024 | Elec | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 432608.5 | 239.5 | 22.7 | 8.5 | 6.5 | 277.2 | 35 | 0.65923 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5933.05 | -426675.45
WO-00002 | Replacement – Control Valve VLV-0026 | VLV-0026 | Vlv | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 113098 | 40.6 | 11.4 | 20 | 3.3 | 75.3 | 9 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3431.19 | -109666.81
WO-00003 | Inspection – Piping/Pipeline Segment PPL-0012 | PPL-0012 | Ppl | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 5185.61 | 9.5 | 1.6 | 4.4 | 0.4 | 15.9 | 2 | 0.099696 | 3614.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4803.35 | -382.26
WO-00005 | Repair – Instrument/Analyser INST-0114 | INST-0114 | Inst | Offsites | Repair | Low | FALSE | FALSE | DEFER | 73788.26 | 17.4 | 28.4 | 3.2 | 5.3 | 54.3 | 7 | 0.92825 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.68 | -72451.58
WO-00007 | Cleaning – Instrument/Analyser INST-0121 | INST-0121 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 6623.09 | 21.5 | 1.9 | 1.5 | 9 | 33.9 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5183.09
WO-00008 | Repair – Instrument/Analyser INST-0082 | INST-0082 | Inst | Tank-Farm | Repair | Medium | FALSE | FALSE | DEFER | 16266.45 | 14.3 | 21.1 | 2.9 | 9 | 47.3 | 6 | 0.84213 | 730 | 2 | 5 | 2 | 10 | HIGH | 1212.67 | -15053.78
WO-00009 | Testing – Instrument/Analyser INST-0007 | INST-0007 | Inst | Unit-100 | Testing | Medium | FALSE | FALSE | DEFER | 5051.36 | 10.8 | 18.8 | 8.9 | 1.1 | 39.6 | 5 | 0.96291 | 730 | 2 | 5 | 2 | 10 | HIGH | 1386.59 | -3664.77
WO-00010 | Testing – Instrument/Analyser INST-0111 | INST-0111 | Inst | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 11298.2 | 4.1 | 13.5 | 15.8 | 0.3 | 33.7 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -9858.2
WO-00012 | Inspection – Control Valve VLV-0110 | VLV-0110 | Vlv | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 7232.51 | 2.2 | 1 | 2.3 | 0.2 | 5.7 | 1 | 0.37878 | 1096.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2032.63 | -5199.88
WO-00013 | Repair – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 73391.62 | 35.9 | 8 | 15 | 6.2 | 65.1 | 8 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -72006.06
WO-00015 | Inspection – Control Valve VLV-0089 | VLV-0089 | Vlv | Unit-200 | Inspection | Medium | FALSE | FALSE | DEFER | 6359.44 | 8.4 | 1.5 | 1.1 | 0.3 | 11.3 | 1 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3326.16 | -3033.28
WO-00016 | Cleaning – Electrical Equipment ELEC-0008 | ELEC-0008 | Elec | Flare-System | Cleaning | Critical | FALSE | FALSE | DEFER | 23061.33 | 13 | 1.8 | 0.3 | 5 | 20.1 | 3 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5958.15 | -17103.18
WO-00019 | Inspection – Instrument/Analyser INST-0048 | INST-0048 | Inst | Flare-System | Inspection | Low | FALSE | FALSE | DEFER | 1621.98 | 3.9 | 0.1 | 2.2 | 0.9 | 7.1 | 1 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | HIGH | 949.8 | -672.18
WO-00020 | Replacement – Electrical Equipment ELEC-0033 | ELEC-0033 | Elec | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 71220.87 | 37.5 | 16.9 | 8.7 | 3.7 | 66.8 | 8 | 0.23847 | 1602.4435 | 2.5 | 3 | 2 | 6 | MEDIUM | 2146.27 | -69074.6 | WO-00015
WO-00022 | Overhaul – Centrifugal Pump PMP-0039 | PMP-0039 | Pmp | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 339510.92 | 44.1 | 43.4 | 48.9 | 17.1 | 153.5 | 19 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15725.17 | -323785.75
WO-00023 | Cleaning – Control Valve VLV-0112 | VLV-0112 | Vlv | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 9022.56 | 7.6 | 1.2 | 0.1 | 8.6 | 17.5 | 2 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3419.43 | -5603.13
WO-00025 | Testing – Control Valve VLV-0063 | VLV-0063 | Vlv | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 3914.39 | 18.3 | 9.6 | 17 | 0.1 | 45 | 6 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2078.14 | -1836.25
WO-00026 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | Elec | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 13871.67 | 9.7 | 1.7 | 1.9 | 5.7 | 19 | 2 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1934.16 | -11937.51
WO-00028 | Cleaning – Instrument/Analyser INST-0039 | INST-0039 | Inst | Utilities | Cleaning | High | FALSE | FALSE | DEFER | 13598.13 | 24.4 | 2 | 0.2 | 4.2 | 30.8 | 4 | 0.96419 | 730 | 2 | 5 | 2 | 10 | HIGH | 1388.43 | -12209.7
WO-00029 | Overhaul – Control Valve VLV-0104 | VLV-0104 | Vlv | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 303937.2 | 211.2 | 40.4 | 8.8 | 13.1 | 273.5 | 34 | 0.55849 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2996.99 | -300940.21
WO-00030 | Overhaul – Centrifugal Pump PMP-0026 | PMP-0026 | Pmp | Utilities | Overhaul | Critical | FALSE | FALSE | DEFER | 91427.47 | 119.5 | 25.3 | 15.9 | 19.1 | 179.8 | 22 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | HIGH | 7865.02 | -83562.45
WO-00031 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | Elec | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 13377.52 | 25.1 | 0.2 | 0.2 | 4.4 | 29.9 | 4 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1934.16 | -11443.36
WO-00032 | Replacement – Electrical Equipment ELEC-0085 | ELEC-0085 | Elec | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 92766.51 | 20.8 | 3.5 | 12.3 | 8 | 44.6 | 6 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7020.85 | -85745.66
WO-00034 | Replacement – Instrument/Analyser INST-0029 | INST-0029 | Inst | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 80206.91 | 33 | 11.1 | 5.8 | 7 | 56.9 | 7 | 0.95892 | 730 | 2 | 5 | 2 | 10 | HIGH | 1380.84 | -78826.07
WO-00035 | Inspection – Instrument/Analyser INST-0177 | INST-0177 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 3309.18 | 2.4 | 0.1 | 5 | 0.5 | 8 | 1 | 0.86611 | 730 | 2 | 5 | 2 | 10 | HIGH | 1247.2 | -2061.98
WO-00036 | Replacement – Instrument/Analyser INST-0141 | INST-0141 | Inst | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 117701.45 | 21.1 | 15.1 | 9.7 | 1.6 | 47.5 | 6 | 0.9166 | 730 | 2 | 5 | 2 | 10 | HIGH | 1319.9 | -116381.55
WO-00038 | Calibration – Instrument/Analyser INST-0126 | INST-0126 | Inst | Unit-200 | Calibration | Medium | FALSE | FALSE | DEFER | 2972.41 | 0.5 | 4.2 | 17 | 0.2 | 21.9 | 3 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | HIGH | 978.78 | -1993.63
WO-00040 | Replacement – Instrument/Analyser INST-0175 | INST-0175 | Inst | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 102596.9 | 17.9 | 16.8 | 5.6 | 5.4 | 45.7 | 6 | 0.88589 | 730 | 2 | 5 | 2 | 10 | HIGH | 1275.68 | -101321.22 | WO-00037
WO-00041 | Calibration – Instrument/Analyser INST-0007 | INST-0007 | Inst | Unit-100 | Calibration | Medium | FALSE | FALSE | DEFER | 2413.68 | 1.7 | 9.9 | 14.8 | 0.8 | 27.2 | 3 | 0.96291 | 730 | 2 | 5 | 2 | 10 | HIGH | 1386.59 | -1027.09
WO-00042 | Repair – Instrument/Analyser INST-0033 | INST-0033 | Inst | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 52213.15 | 89.3 | 10.1 | 10.9 | 7.6 | 117.9 | 15 | 0.95645 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.28 | -50835.87
WO-00043 | Replacement – Control Valve VLV-0029 | VLV-0029 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 117474.92 | 30.6 | 5.3 | 10.6 | 4.6 | 51.1 | 6 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -114969.04
WO-00044 | Testing – Instrument/Analyser INST-0119 | INST-0119 | Inst | Tank-Farm | Testing | High | FALSE | FALSE | DEFER | 14805.56 | 13.7 | 18 | 10.4 | 1.7 | 43.8 | 5 | 0.89642 | 730 | 2 | 5 | 2 | 10 | HIGH | 1290.84 | -13514.72
WO-00045 | Inspection – Control Valve VLV-0018 | VLV-0018 | Vlv | Utilities | Inspection | High | FALSE | FALSE | DEFER | 7802.09 | 8.9 | 0.6 | 3.7 | 0.5 | 13.7 | 2 | 0.66617 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3574.81 | -4227.28
WO-00046 | Replacement – Control Valve VLV-0080 | VLV-0080 | Vlv | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 20643.16 | 36.6 | 10 | 14.2 | 2.9 | 63.7 | 8 | 0.49658 | 27.375 | 2.65 | 4 | 3 | 12 | HIGH | 2664.75 | -17978.41
WO-00047 | Cleaning – Control Valve VLV-0033 | VLV-0033 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 22590.42 | 6.6 | 1.2 | 1.7 | 4.6 | 14.1 | 2 | 0.52725 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2829.34 | -19761.08
WO-00048 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 36387.38 | 31.3 | 7.9 | 9.4 | 6.8 | 55.4 | 7 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -33881.5 | WO-00019
WO-00049 | Replacement – Control Valve VLV-0096 | VLV-0096 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 84321.48 | 17.1 | 6 | 8 | 1 | 32.1 | 4 | 0.64268 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3448.8 | -80872.68
WO-00051 | Repair – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Repair | Low | FALSE | FALSE | DEFER | 64606.38 | 19.6 | 7.2 | 9.5 | 8.8 | 45.1 | 6 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -63228.56
WO-00055 | Inspection – Instrument/Analyser INST-0124 | INST-0124 | Inst | Unit-200 | Inspection | Low | FALSE | FALSE | DEFER | 7072.3 | 9.6 | 0.1 | 4 | 0.7 | 14.4 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5632.3
WO-00057 | Calibration – Instrument/Analyser INST-0048 | INST-0048 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 2592.68 | 0.8 | 7.3 | 10.4 | 0.5 | 19 | 2 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | HIGH | 949.8 | -1642.88
WO-00058 | Calibration – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Calibration | High | FALSE | FALSE | DEFER | 2937.02 | 0.9 | 4.7 | 10 | 0.1 | 15.7 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1497.02
WO-00060 | Repair – Instrument/Analyser INST-0115 | INST-0115 | Inst | Utilities | Repair | High | FALSE | FALSE | DEFER | 46220.48 | 25.8 | 13 | 12.6 | 5.6 | 57 | 7 | 0.96766 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.43 | -44827.05
WO-00061 | Overhaul – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Overhaul | Low | FALSE | FALSE | DEFER | 332694.02 | 93.5 | 33.7 | 10.9 | 10.7 | 148.8 | 19 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | -325381.82
WO-00062 | Replacement – Control Valve VLV-0065 | VLV-0065 | Vlv | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 74595.34 | 29.3 | 7.7 | 22.3 | 4.1 | 63.4 | 8 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3625.6 | -70969.74
WO-00063 | Repair – Electrical Equipment ELEC-0057 | ELEC-0057 | Elec | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 60183.66 | 70.7 | 5.3 | 4.4 | 6.7 | 87.1 | 11 | 0.21302 | 1698.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1917.2 | -58266.46 | WO-00046
WO-00065 | Repair – Control Valve VLV-0050 | VLV-0050 | Vlv | Utilities | Repair | Low | FALSE | FALSE | DEFER | 10642.74 | 26.1 | 17.8 | 8.6 | 5.3 | 57.8 | 7 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3189.72 | -7453.02
WO-00066 | Cleaning – Control Valve VLV-0061 | VLV-0061 | Vlv | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 10962.89 | 27.7 | 0.1 | 1.9 | 6 | 35.7 | 4 | 0.64915 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3483.48 | -7479.41
WO-00067 | Testing – Piping/Pipeline Segment PPL-0016 | PPL-0016 | Ppl | Offsites | Testing | Critical | FALSE | FALSE | DEFER | 7856.2 | 9.9 | 9.4 | 17.2 | 1.1 | 37.6 | 5 | 0.14302 | 2885.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6890.59 | -965.61
WO-00069 | Overhaul – Control Valve VLV-0114 | VLV-0114 | Vlv | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 62923.13 | 95.1 | 35.5 | 21 | 24 | 175.6 | 22 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3549.3 | -59373.83
WO-00070 | Cleaning – Pressure Vessel VSL-0012 | VSL-0012 | Vsl | Utilities | Cleaning | High | FALSE | FALSE | DEFER | 24206.73 | 24.8 | 0.6 | 1.5 | 3.1 | 30 | 4 | 0.36396 | 334.4951 | 5 | 4 | 5 | 20 | CRITICAL | 79161.63 | 54954.9 | WO-00029
WO-00071 | Overhaul – Electrical Equipment ELEC-0026 | ELEC-0026 | Elec | Utilities | Overhaul | High | FALSE | FALSE | DEFER | 24843.17 | 94.8 | 48.1 | 21.3 | 7.6 | 171.8 | 21 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5492.41 | -19350.76
WO-00072 | Overhaul – Instrument/Analyser INST-0010 | INST-0010 | Inst | Unit-300 | Overhaul | Medium | FALSE | FALSE | DEFER | 507949.81 | 191.6 | 26.3 | 16.8 | 4.9 | 239.6 | 30 | 0.786 | 730 | 2 | 5 | 2 | 10 | HIGH | 1131.85 | -506817.96
WO-00074 | Calibration – Instrument/Analyser INST-0169 | INST-0169 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 1621.58 | 1.9 | 5.4 | 4.3 | 0.2 | 11.8 | 1 | 0.83629 | 730 | 2 | 5 | 2 | 10 | HIGH | 1204.25 | -417.33
WO-00075 | Cleaning – Instrument/Analyser INST-0146 | INST-0146 | Inst | Offsites | Cleaning | Medium | FALSE | FALSE | DEFER | 14257.23 | 21.1 | 0.5 | 1.3 | 7.6 | 30.5 | 4 | 0.87445 | 730 | 2 | 5 | 2 | 10 | HIGH | 1259.2 | -12998.03
WO-00076 | Overhaul – Instrument/Analyser INST-0177 | INST-0177 | Inst | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 119671 | 122.8 | 41 | 46.2 | 15.9 | 225.9 | 28 | 0.86611 | 730 | 2 | 5 | 2 | 10 | HIGH | 1247.2 | -118423.8
WO-00079 | Inspection – Instrument/Analyser INST-0073 | INST-0073 | Inst | Unit-100 | Inspection | Low | FALSE | FALSE | DEFER | 5453.77 | 3.1 | 1.6 | 1.8 | 0.7 | 7.2 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4013.77 | WO-00052
WO-00082 | Replacement – Heat Exchanger HX-0005 | HX-0005 | Hx | Offsites | Replacement | High | FALSE | FALSE | DEFER | 55890.67 | 41 | 9.8 | 8.9 | 7.3 | 67 | 8 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | HIGH | 33706.39 | -22184.28
WO-00083 | Overhaul – Electrical Equipment ELEC-0019 | ELEC-0019 | Elec | Unit-200 | Overhaul | High | FALSE | FALSE | DEFER | 339335.46 | 84.4 | 36.6 | 24.3 | 11.3 | 156.6 | 20 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4601.34 | -334734.12
WO-00084 | Cleaning – Instrument/Analyser INST-0117 | INST-0117 | Inst | Flare-System | Cleaning | Medium | FALSE | FALSE | DEFER | 15463.95 | 12.2 | 1.7 | 1.7 | 2.9 | 18.5 | 2 | 0.86878 | 730 | 2 | 5 | 2 | 10 | HIGH | 1251.04 | -14212.91
WO-00085 | Replacement – Control Valve VLV-0043 | VLV-0043 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 119967.21 | 19.7 | 7 | 12.8 | 3.4 | 42.9 | 5 | 0.41764 | 809.375 | 2.65 | 4 | 3 | 12 | HIGH | 2241.14 | -117726.07
WO-00086 | Overhaul – Instrument/Analyser INST-0167 | INST-0167 | Inst | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 144214.12 | 141.3 | 45.3 | 41.3 | 14 | 241.9 | 30 | 0.95101 | 730 | 2 | 5 | 2 | 10 | HIGH | 1369.46 | -142844.66
WO-00087 | Inspection – Instrument/Analyser INST-0141 | INST-0141 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 7100.03 | 7.7 | 1.1 | 4.5 | 0.1 | 13.4 | 2 | 0.9166 | 730 | 2 | 5 | 2 | 10 | HIGH | 1319.9 | -5780.13
WO-00088 | Replacement – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 18866.41 | 32.2 | 9 | 22.8 | 3.9 | 67.9 | 8 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -16734.24
WO-00090 | Repair – Electrical Equipment ELEC-0077 | ELEC-0077 | Elec | Offsites | Repair | High | FALSE | FALSE | DEFER | 39001.81 | 39.4 | 9.6 | 10.7 | 7.4 | 67.1 | 8 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7273.03 | -31728.78
WO-00093 | Cleaning – Control Valve VLV-0112 | VLV-0112 | Vlv | Unit-200 | Cleaning | High | FALSE | FALSE | DEFER | 20216.12 | 18.3 | 1.6 | 1.3 | 7.5 | 28.7 | 4 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3419.43 | -16796.69
WO-00095 | Replacement – Instrument/Analyser INST-0111 | INST-0111 | Inst | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 87183.62 | 16.3 | 4.9 | 13.7 | 3.2 | 38.1 | 5 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -85743.62
WO-00097 | Replacement – Pressure Vessel VSL-0009 | VSL-0009 | Vsl | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 105372.64 | 38.3 | 9.4 | 13.3 | 2.9 | 63.9 | 8 | 0.23421 | 1546.4951 | 5 | 3 | 5 | 15 | HIGH | 50941.13 | -54431.51
WO-00100 | Replacement – Centrifugal Pump PMP-0061 | PMP-0061 | Pmp | Utilities | Replacement | High | FALSE | FALSE | DEFER | 73482.47 | 19.6 | 5 | 13.4 | 4.2 | 42.2 | 5 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | MEDIUM | 5761.08 | -67721.39
WO-00101 | Replacement – Centrifugal Pump PMP-0019 | PMP-0019 | Pmp | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 81236.69 | 47.9 | 5 | 4.9 | 5 | 62.8 | 8 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | MEDIUM | 2786.64 | -78450.05
WO-00102 | Cleaning – Electrical Equipment ELEC-0035 | ELEC-0035 | Elec | Offsites | Cleaning | Medium | FALSE | FALSE | DEFER | 17845.16 | 13.7 | 0.5 | 1.1 | 3.6 | 18.9 | 2 | 0.3627 | 1082.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 3264.29 | -14580.87
WO-00105 | Cleaning – Instrument/Analyser INST-0112 | INST-0112 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 1612.76 | 4.2 | 1.7 | 0.1 | 6.2 | 12.2 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -172.76
WO-00107 | Replacement – Instrument/Analyser INST-0065 | INST-0065 | Inst | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 50764.32 | 20.8 | 20 | 8.6 | 8.5 | 57.9 | 7 | 0.94806 | 730 | 2 | 5 | 2 | 10 | HIGH | 1365.21 | -49399.11 | WO-00038
WO-00111 | Replacement – Pressure Vessel VSL-0028 | VSL-0028 | Vsl | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 44519.28 | 31.5 | 11.1 | 23.7 | 3 | 69.3 | 9 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | HIGH | 58882.1 | 14362.82
WO-00113 | Testing – Control Valve VLV-0098 | VLV-0098 | Vlv | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 6497.25 | 16.1 | 12.3 | 22.7 | 0.6 | 51.7 | 6 | 0.64153 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3442.61 | -3054.64
WO-00115 | Repair – Control Valve VLV-0038 | VLV-0038 | Vlv | Tank-Farm | Repair | Low | FALSE | FALSE | DEFER | 69222.36 | 59.8 | 11.7 | 2.4 | 6.5 | 80.4 | 10 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3387.34 | -65835.02
WO-00116 | Overhaul – Control Valve VLV-0050 | VLV-0050 | Vlv | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 111353.09 | 97.6 | 29.4 | 43.1 | 7.4 | 177.5 | 22 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3189.72 | -108163.37
WO-00117 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | Inst | Utilities | Calibration | Critical | FALSE | FALSE | DEFER | 2820.93 | 0.2 | 9.4 | 13.6 | 0.8 | 24 | 3 | 0.81141 | 730 | 2 | 5 | 2 | 10 | HIGH | 1168.43 | -1652.5
WO-00119 | Overhaul – Control Valve VLV-0060 | VLV-0060 | Vlv | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 140083.62 | 223.3 | 49 | 20.6 | 7.5 | 300.4 | 38 | 0.57589 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3090.38 | -136993.24
WO-00120 | Overhaul – Distillation Tower TWR-0011 | TWR-0011 | Twr | Unit-100 | Overhaul | Medium | FALSE | FALSE | DEFER | 526585.78 | 140 | 10.3 | 9.7 | 8.5 | 168.5 | 21 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | HIGH | 189640.61 | -336945.17 | WO-00098
WO-00121 | Cleaning – Instrument/Analyser INST-0044 | INST-0044 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 14510.99 | 11.7 | 1.9 | 0.7 | 8.7 | 23 | 3 | 0.9471 | 730 | 2 | 5 | 2 | 10 | HIGH | 1363.83 | -13147.16
WO-00122 | Overhaul – Electrical Equipment ELEC-0076 | ELEC-0076 | Elec | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 538159.22 | 95.4 | 35.7 | 11.7 | 13.5 | 156.3 | 20 | 0.50503 | 344.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4545.25 | -533613.97
WO-00125 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 3055.41 | 7.7 | 1.3 | 4.3 | 0 | 13.3 | 2 | 0.94369 | 730 | 2 | 5 | 2 | 10 | HIGH | 1358.91 | -1696.5
WO-00127 | Inspection – Instrument/Analyser INST-0092 | INST-0092 | Inst | Unit-300 | Inspection | Low | FALSE | FALSE | DEFER | 5586.79 | 2.4 | 1.7 | 1.1 | 0.5 | 5.7 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4146.79
WO-00129 | Overhaul – Centrifugal Pump PMP-0046 | PMP-0046 | Pmp | Unit-300 | Overhaul | Critical | FALSE | FALSE | DEFER | 216535.34 | 190.7 | 30.8 | 18.8 | 7.4 | 247.7 | 31 | 0.1139 | 2025.705 | 3 | 2 | 3 | 6 | MEDIUM | 2460.33 | -214075.01
WO-00130 | Overhaul – Instrument/Analyser INST-0126 | INST-0126 | Inst | Unit-200 | Overhaul | Critical | FALSE | FALSE | DEFER | 114522.78 | 43.9 | 10.2 | 47.1 | 5.5 | 106.7 | 13 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | HIGH | 978.78 | -113544 | WO-00048
WO-00131 | Overhaul – Heat Exchanger HX-0031 | HX-0031 | Hx | Unit-300 | Overhaul | Critical | FALSE | FALSE | DEFER | 158383.67 | 232.5 | 46.3 | 25 | 13 | 316.8 | 40 | 0.31048 | 1063.1652 | 4 | 3 | 4 | 12 | HIGH | 36326.65 | -122057.02
WO-00132 | Inspection – Instrument/Analyser INST-0005 | INST-0005 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 2767.07 | 3 | 0.2 | 3.2 | 0.1 | 6.5 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1327.07
WO-00133 | Overhaul – Centrifugal Pump PMP-0063 | PMP-0063 | Pmp | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 273735.18 | 67.5 | 8.2 | 16.1 | 8.7 | 100.5 | 13 | 0.55047 | 235.7051 | 3 | 4 | 3 | 12 | HIGH | 11890.05 | -261845.13 | WO-00065
WO-00134 | Repair – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 33663.66 | 45.3 | 22.5 | 13.3 | 2.7 | 83.8 | 10 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -32223.66
WO-00135 | Overhaul – Electrical Equipment ELEC-0004 | ELEC-0004 | Elec | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 345424.59 | 67.7 | 20.3 | 20.8 | 9.2 | 118 | 15 | 0.79103 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7119.3 | -338305.29
WO-00136 | Cleaning – Instrument/Analyser INST-0066 | INST-0066 | Inst | Offsites | Cleaning | Critical | FALSE | FALSE | DEFER | 13225.36 | 8.8 | 0.2 | 1.6 | 5.8 | 16.4 | 2 | 0.77693 | 730 | 2 | 5 | 2 | 10 | HIGH | 1118.77 | -12106.59
WO-00137 | Replacement – Electrical Equipment ELEC-0048 | ELEC-0048 | Elec | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 97463.88 | 47.1 | 17.8 | 16 | 4.8 | 85.7 | 11 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4217.99 | -93245.89 | WO-00091
WO-00141 | Testing – Control Valve VLV-0004 | VLV-0004 | Vlv | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 4888.62 | 19.8 | 11.6 | 8 | 0.2 | 39.6 | 5 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | MEDIUM | 1675.84 | -3212.78
WO-00144 | Cleaning – Control Valve VLV-0001 | VLV-0001 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 18423.08 | 12.1 | 0 | 1.3 | 10 | 23.4 | 3 | 0.63786 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3422.93 | -15000.15
WO-00145 | Inspection – Instrument/Analyser INST-0076 | INST-0076 | Inst | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 2685.08 | 5.4 | 0.5 | 2.4 | 0.6 | 8.9 | 1 | 0.79324 | 730 | 2 | 5 | 2 | 10 | HIGH | 1142.27 | -1542.81
WO-00147 | Repair – Instrument/Analyser INST-0095 | INST-0095 | Inst | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 5209.95 | 21.4 | 7.8 | 12.8 | 9.3 | 51.3 | 6 | 0.94927 | 730 | 2 | 5 | 2 | 10 | HIGH | 1366.94 | -3843.01
WO-00148 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 93071.68 | 46.6 | 6.4 | 7.2 | 4.2 | 64.4 | 8 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -90565.8
WO-00149 | Calibration – Instrument/Analyser INST-0135 | INST-0135 | Inst | Tank-Farm | Calibration | Low | FALSE | FALSE | DEFER | 2064.39 | 1.7 | 4.2 | 9.4 | 0 | 15.3 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -624.39
WO-00150 | Cleaning – Instrument/Analyser INST-0027 | INST-0027 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 8154.94 | 5.7 | 1.4 | 1.5 | 7.3 | 15.9 | 2 | 0.91997 | 730 | 2 | 5 | 2 | 10 | HIGH | 1324.76 | -6830.18
WO-00151 | Repair – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 60746.33 | 68.5 | 20.9 | 18.3 | 9.4 | 117.1 | 15 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | -19300.79
WO-00152 | Overhaul – Pressure Vessel VSL-0022 | VSL-0022 | Vsl | Offsites | Overhaul | Low | FALSE | FALSE | DEFER | 227784.38 | 203.8 | 35.1 | 11.2 | 6.8 | 256.9 | 32 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | HIGH | 58166.81 | -169617.57
WO-00153 | Repair – Control Valve VLV-0051 | VLV-0051 | Vlv | Offsites | Repair | High | FALSE | FALSE | DEFER | 76242.93 | 47.4 | 24.4 | 16.9 | 3.8 | 92.5 | 12 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2866.96 | -73375.97
WO-00154 | Testing – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Testing | Medium | FALSE | FALSE | DEFER | 938.18 | 12.8 | 17 | 17.6 | 0.5 | 47.9 | 6 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | 161.25 | WO-00025
WO-00155 | Replacement – Instrument/Analyser INST-0118 | INST-0118 | Inst | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 100339.4 | 19.4 | 14.5 | 19.7 | 2.7 | 56.3 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -98899.4 | WO-00145
WO-00157 | Testing – Instrument/Analyser INST-0056 | INST-0056 | Inst | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 7223.81 | 9.8 | 12.2 | 10.2 | 0.7 | 32.9 | 4 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | HIGH | 1103.88 | -6119.93
WO-00158 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Inspection | Medium | FALSE | FALSE | DEFER | 5645.44 | 3.6 | 0.8 | 1.6 | 0.6 | 6.6 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -4205.44
WO-00159 | Replacement – Control Valve VLV-0058 | VLV-0058 | Vlv | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 23792.91 | 19.8 | 16.7 | 9.4 | 8 | 53.9 | 7 | 0.54217 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2909.45 | -20883.46 | WO-00011
WO-00160 | Inspection – Control Valve VLV-0063 | VLV-0063 | Vlv | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 5982.08 | 5.7 | 0.1 | 4.8 | 0.1 | 10.7 | 1 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | HIGH | 2078.14 | -3903.94
WO-00161 | Replacement – Storage Tank TNK-0008 | TNK-0008 | Tnk | Offsites | Replacement | Low | FALSE | FALSE | DEFER | 61284.44 | 48.8 | 2.1 | 22.6 | 6.8 | 80.3 | 10 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | LOW | 1543.9 | -59740.54
WO-00162 | Calibration – Instrument/Analyser INST-0128 | INST-0128 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 2797.95 | 1.2 | 4.9 | 11.1 | 0.7 | 17.9 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1357.95
WO-00165 | Cleaning – Instrument/Analyser INST-0151 | INST-0151 | Inst | Unit-300 | Cleaning | Low | FALSE | FALSE | DEFER | 11694.4 | 4.1 | 1.1 | 1.5 | 3.4 | 10.1 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10254.4
WO-00167 | Inspection – Instrument/Analyser INST-0161 | INST-0161 | Inst | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 6075.58 | 2.4 | 1.6 | 4.2 | 0.1 | 8.3 | 1 | 0.65143 | 452.2559 | 2 | 5 | 2 | 10 | HIGH | 938.05 | -5137.53
WO-00168 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 5281.03 | 2.5 | 1.9 | 1.8 | 0.7 | 6.9 | 1 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -4181.6
WO-00170 | Replacement – Instrument/Analyser INST-0012 | INST-0012 | Inst | Offsites | Replacement | Medium | FALSE | FALSE | DEFER | 106641.28 | 55.5 | 17.8 | 6.9 | 4.7 | 84.9 | 11 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -105201.28
WO-00171 | Replacement – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 81272.37 | 20.3 | 7.8 | 21.2 | 3.3 | 52.6 | 7 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -79944.67 | WO-00103
WO-00172 | Replacement – Control Valve VLV-0064 | VLV-0064 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 7705.73 | 21.3 | 5.1 | 14.1 | 2 | 42.5 | 5 | 0.65112 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3494.09 | -4211.64
WO-00173 | Repair – Control Valve VLV-0068 | VLV-0068 | Vlv | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 30276.47 | 23.5 | 14.4 | 16.1 | 6.3 | 60.3 | 8 | 0.63819 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3424.67 | -26851.8
WO-00174 | Cleaning – Instrument/Analyser INST-0092 | INST-0092 | Inst | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 12234.05 | 11.9 | 0.2 | 2 | 3.4 | 17.5 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10794.05
WO-00176 | Repair – Electrical Equipment ELEC-0082 | ELEC-0082 | Elec | Utilities | Repair | Low | FALSE | FALSE | DEFER | 25895.01 | 26.2 | 28.8 | 16.6 | 4.1 | 75.7 | 9 | 0.68526 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6167.3 | -19727.71
WO-00177 | Overhaul – Electrical Equipment ELEC-0008 | ELEC-0008 | Elec | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 217850.21 | 207.9 | 39.6 | 20.5 | 16.1 | 284.1 | 36 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5958.15 | -211892.06 | WO-00015
WO-00178 | Inspection – Instrument/Analyser INST-0087 | INST-0087 | Inst | Unit-300 | Inspection | High | FALSE | FALSE | DEFER | 7717.44 | 6.4 | 1.2 | 3.4 | 0.6 | 11.6 | 1 | 0.95076 | 730 | 2 | 5 | 2 | 10 | HIGH | 1369.1 | -6348.34
WO-00179 | Testing – Instrument/Analyser INST-0019 | INST-0019 | Inst | Offsites | Testing | High | FALSE | FALSE | DEFER | 9514.19 | 14.1 | 13.1 | 9.8 | 0.1 | 37.1 | 5 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -8074.19
WO-00180 | Inspection – Control Valve VLV-0079 | VLV-0079 | Vlv | Unit-300 | Inspection | High | FALSE | FALSE | DEFER | 5499.45 | 9 | 0.6 | 2.3 | 0.7 | 12.6 | 2 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3315.02 | -2184.43 | WO-00168
WO-00181 | Testing – Electrical Equipment ELEC-0006 | ELEC-0006 | Elec | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 5775.78 | 3.8 | 7.5 | 22.7 | 0.5 | 34.5 | 4 | 0.30621 | 1330.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2755.87 | -3019.91
WO-00183 | Replacement – Control Valve VLV-0034 | VLV-0034 | Vlv | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 19738.66 | 59.1 | 14.2 | 21 | 7.8 | 102.1 | 13 | 0.54543 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2926.9 | -16811.76
WO-00184 | Replacement – Electrical Equipment ELEC-0068 | ELEC-0068 | Elec | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 42299.1 | 45.3 | 14.9 | 23 | 6.1 | 89.3 | 11 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1589.67 | -40709.43
WO-00185 | Overhaul – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 374022.58 | 125.3 | 41.2 | 32.6 | 4.2 | 203.3 | 25 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -372923.15
WO-00187 | Repair – Electrical Equipment ELEC-0067 | ELEC-0067 | Elec | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 73012.16 | 58.4 | 18.5 | 3 | 6.4 | 86.3 | 11 | 0.8538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7684.19 | -65327.97
WO-00189 | Overhaul – Control Valve VLV-0066 | VLV-0066 | Vlv | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 503845.46 | 161.1 | 10.9 | 26.6 | 10.2 | 208.8 | 26 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3450.07 | -500395.39 | WO-00126
WO-00190 | Cleaning – Instrument/Analyser INST-0032 | INST-0032 | Inst | Unit-200 | Cleaning | High | FALSE | FALSE | DEFER | 1249.55 | 18.6 | 1.5 | 1.5 | 2.5 | 24.1 | 3 | 0.93702 | 730 | 2 | 5 | 2 | 10 | HIGH | 1349.31 | 99.76
WO-00191 | Overhaul – Instrument/Analyser INST-0009 | INST-0009 | Inst | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 120166.45 | 124.1 | 11 | 12.8 | 17.4 | 165.3 | 21 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -118726.45
WO-00193 | Cleaning – Piping/Pipeline Segment PPL-0015 | PPL-0015 | Ppl | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 6461.17 | 17.9 | 0.2 | 0.9 | 3.5 | 22.5 | 3 | 0.089098 | 3787.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4292.73 | -2168.44
WO-00194 | Overhaul – Instrument/Analyser INST-0049 | INST-0049 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 360602.64 | 112.1 | 20.1 | 16.5 | 22.2 | 170.9 | 21 | 0.63084 | 512.2559 | 2 | 5 | 2 | 10 | HIGH | 908.42 | -359694.22 | WO-00142
WO-00195 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | Elec | Utilities | Inspection | High | FALSE | FALSE | DEFER | 6125.76 | 5.3 | 0 | 3.1 | 0.1 | 8.5 | 1 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4834.45 | -1291.31
WO-00197 | Replacement – Electrical Equipment ELEC-0080 | ELEC-0080 | Elec | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 68151.17 | 34.8 | 18.3 | 7.3 | 6.2 | 66.6 | 8 | 0.82033 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7382.93 | -60768.24 | WO-00164
WO-00200 | Repair – Pressure Vessel VSL-0011 | VSL-0011 | Vsl | Unit-100 | Repair | Critical | FALSE | FALSE | DEFER | 60459.26 | 34.8 | 7.2 | 18.2 | 8.7 | 68.9 | 9 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | HIGH | 36127.93 | -24331.33
WO-00201 | Repair – Piping/Pipeline Segment PPL-0043 | PPL-0043 | Ppl | Tank-Farm | Repair | Low | FALSE | FALSE | DEFER | 9582.59 | 13.8 | 23.7 | 11.7 | 4.7 | 53.9 | 7 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6265.83 | -3316.76
WO-00202 | Repair – Instrument/Analyser INST-0088 | INST-0088 | Inst | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 6494.63 | 64.7 | 24.1 | 11.9 | 9.8 | 110.5 | 14 | 0.89303 | 730 | 2 | 5 | 2 | 10 | HIGH | 1285.97 | -5208.66
WO-00207 | Calibration – Instrument/Analyser INST-0006 | INST-0006 | Inst | Utilities | Calibration | Low | FALSE | FALSE | DEFER | 2711.44 | 1.4 | 2.5 | 6.9 | 1 | 11.8 | 1 | 0.96225 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.63 | -1325.81
WO-00208 | Testing – Instrument/Analyser INST-0057 | INST-0057 | Inst | Offsites | Testing | Medium | FALSE | FALSE | DEFER | 1033.59 | 8.9 | 19.2 | 19.1 | 0.2 | 47.4 | 6 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | HIGH | 1048.11 | 14.52
WO-00209 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | Elec | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 4249.75 | 3.9 | 0.1 | 1.3 | 0.9 | 6.2 | 1 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4834.45 | 584.7
WO-00210 | Testing – Instrument/Analyser INST-0029 | INST-0029 | Inst | Unit-200 | Testing | Medium | FALSE | FALSE | DEFER | 7314.85 | 9.4 | 11.2 | 16.3 | 0.7 | 37.6 | 5 | 0.95892 | 730 | 2 | 5 | 2 | 10 | HIGH | 1380.84 | -5934.01
WO-00212 | Cleaning – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 18374.25 | 6.1 | 2 | 2 | 5.7 | 15.8 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -16934.25
WO-00213 | Replacement – Instrument/Analyser INST-0163 | INST-0163 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 89820.11 | 53.7 | 16.7 | 20.2 | 5.2 | 95.8 | 12 | 0.93183 | 730 | 2 | 5 | 2 | 10 | HIGH | 1341.83 | -88478.28
WO-00215 | Cleaning – Instrument/Analyser INST-0098 | INST-0098 | Inst | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 10507.52 | 13.9 | 1.2 | 1.5 | 6.5 | 23.1 | 3 | 0.96482 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.33 | -9118.19
WO-00218 | Overhaul – Heat Exchanger HX-0009 | HX-0009 | Hx | Utilities | Overhaul | Critical | FALSE | FALSE | DEFER | 422121.16 | 209.1 | 38.3 | 15.3 | 11.3 | 274 | 34 | 0.41447 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48492.86 | -373628.3
WO-00221 | Replacement – Instrument/Analyser INST-0025 | INST-0025 | Inst | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 43274.86 | 22.1 | 12.2 | 13.2 | 9 | 56.5 | 7 | 0.9248 | 730 | 2 | 5 | 2 | 10 | HIGH | 1331.72 | -41943.14
WO-00222 | Replacement – Control Valve VLV-0082 | VLV-0082 | Vlv | Tank-Farm | Replacement | High | FALSE | FALSE | DEFER | 16512.12 | 48.8 | 19.9 | 21.3 | 1.2 | 91.2 | 11 | 0.56312 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3021.85 | -13490.27
WO-00225 | Inspection – Instrument/Analyser INST-0021 | INST-0021 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 2044.07 | 7.1 | 0.6 | 1.5 | 0.2 | 9.4 | 1 | 0.91749 | 730 | 2 | 5 | 2 | 10 | HIGH | 1321.18 | -722.89
WO-00228 | Inspection – Instrument/Analyser INST-0180 | INST-0180 | Inst | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 7751.92 | 6.7 | 1 | 4.4 | 0 | 12.1 | 2 | 0.92781 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.05 | -6415.87
WO-00229 | Inspection – Instrument/Analyser INST-0149 | INST-0149 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 6821.76 | 6.2 | 0.1 | 4.3 | 0 | 10.6 | 1 | 0.79917 | 730 | 2 | 5 | 2 | 10 | HIGH | 1150.81 | -5670.95
WO-00231 | Testing – Electrical Equipment ELEC-0023 | ELEC-0023 | Elec | Flare-System | Testing | Medium | FALSE | FALSE | DEFER | 2019.57 | 11.5 | 9.5 | 9.3 | 1.2 | 31.5 | 4 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1554.05 | -465.52 | WO-00197
WO-00232 | Calibration – Instrument/Analyser INST-0103 | INST-0103 | Inst | Unit-300 | Calibration | High | FALSE | FALSE | DEFER | 2632.64 | 0.6 | 5.7 | 4.1 | 0.7 | 11.1 | 1 | 0.96042 | 730 | 2 | 5 | 2 | 10 | HIGH | 1383.01 | -1249.63
WO-00233 | Cleaning – Control Valve VLV-0111 | VLV-0111 | Vlv | Offsites | Cleaning | Low | FALSE | FALSE | DEFER | 5063.21 | 23.7 | 1.6 | 1.8 | 2.4 | 29.5 | 4 | 0.54298 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2913.75 | -2149.46 | WO-00167
WO-00236 | Replacement – Electrical Equipment ELEC-0023 | ELEC-0023 | Elec | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 11561.78 | 42.7 | 8.6 | 17 | 4.1 | 72.4 | 9 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1554.05 | -10007.73 | WO-00203
WO-00237 | Overhaul – Centrifugal Pump PMP-0021 | PMP-0021 | Pmp | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 41664.68 | 126 | 34.9 | 30.9 | 5.5 | 197.3 | 25 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | HIGH | 18176.25 | -23488.43
WO-00239 | Calibration – Control Valve VLV-0106 | VLV-0106 | Vlv | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1002.14 | 1.2 | 8.4 | 10.2 | 0 | 19.8 | 2 | 0.64237 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3447.09 | 2444.95 | WO-00048
WO-00240 | Testing – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 14550.38 | 6 | 19.1 | 10.9 | 0.3 | 36.3 | 5 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -13164.82
WO-00241 | Overhaul – Instrument/Analyser INST-0003 | INST-0003 | Inst | Tank-Farm | Overhaul | Critical | FALSE | FALSE | DEFER | 330449.88 | 205.5 | 22.1 | 36 | 11.3 | 274.9 | 34 | 0.80391 | 730 | 2 | 5 | 2 | 10 | HIGH | 1157.63 | -329292.25
WO-00242 | Replacement – Pressure Vessel VSL-0013 | VSL-0013 | Vsl | Unit-300 | Replacement | Low | FALSE | FALSE | DEFER | 114253.96 | 33.1 | 3.9 | 17.8 | 9.7 | 64.5 | 8 | 0.1682 | 2208.4953 | 5 | 3 | 5 | 15 | HIGH | 36583.08 | -77670.88
WO-00243 | Cleaning – Control Valve VLV-0026 | VLV-0026 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 10030.74 | 17.9 | 1.6 | 1.7 | 8.6 | 29.8 | 4 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3431.19 | -6599.55
WO-00247 | Inspection – Instrument/Analyser INST-0138 | INST-0138 | Inst | Utilities | Inspection | Low | FALSE | FALSE | DEFER | 7100.03 | 8.7 | 1.7 | 1.6 | 0.1 | 12.1 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -5660.03
WO-00248 | Inspection – Electrical Equipment ELEC-0017 | ELEC-0017 | Elec | Unit-300 | Inspection | Low | FALSE | FALSE | DEFER | 3327.8 | 5.6 | 0.2 | 1.1 | 1 | 7.9 | 1 | 0.25422 | 1541.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 2287.96 | -1039.84
WO-00252 | Cleaning – Piping/Pipeline Segment PPL-0037 | PPL-0037 | Ppl | Tank-Farm | Cleaning | High | FALSE | FALSE | DEFER | 20396.44 | 25.3 | 1.3 | 0.8 | 3.2 | 30.6 | 4 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | HIGH | 13521.8 | -6874.64
WO-00253 | Replacement – Control Valve VLV-0023 | VLV-0023 | Vlv | Flare-System | Replacement | Low | FALSE | FALSE | DEFER | 105052.98 | 33.3 | 6.1 | 9.8 | 2.2 | 51.4 | 6 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3196.58 | -101856.4
WO-00255 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | Inst | Flare-System | Inspection | Critical | FALSE | FALSE | DEFER | 6935.57 | 3.5 | 0.1 | 3.3 | 0.1 | 7 | 1 | 0.94369 | 730 | 2 | 5 | 2 | 10 | HIGH | 1358.91 | -5576.66
WO-00257 | Cleaning – Pressure Vessel VSL-0020 | VSL-0020 | Vsl | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 15567.32 | 27.3 | 0.7 | 0.1 | 6.3 | 34.4 | 4 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | MEDIUM | 6857.86 | -8709.46
WO-00258 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Inspection | Low | FALSE | FALSE | DEFER | 4691.18 | 3.6 | 1.7 | 4.3 | 0.4 | 10 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3251.18
WO-00259 | Testing – Instrument/Analyser INST-0003 | INST-0003 | Inst | Tank-Farm | Testing | High | FALSE | FALSE | DEFER | 2374.14 | 8.6 | 16 | 5.7 | 0.8 | 31.1 | 4 | 0.80391 | 730 | 2 | 5 | 2 | 10 | HIGH | 1157.63 | -1216.51
WO-00260 | Testing – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Testing | Critical | FALSE | FALSE | DEFER | 6467.99 | 15.7 | 11.7 | 6.6 | 1.7 | 35.7 | 4 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -5090.17
WO-00261 | Inspection – Instrument/Analyser INST-0069 | INST-0069 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 3296.44 | 7.5 | 0.7 | 1.3 | 0.3 | 9.8 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -1856.44
WO-00265 | Repair – Storage Tank TNK-0008 | TNK-0008 | Tnk | Offsites | Repair | High | FALSE | FALSE | DEFER | 59189.96 | 82 | 22.7 | 8.5 | 3.5 | 116.7 | 15 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | LOW | 1543.9 | -57646.06
WO-00268 | Calibration – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Calibration | Low | FALSE | FALSE | DEFER | 2946.75 | 0.8 | 5.1 | 10.8 | 0.4 | 17.1 | 2 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | -1917.89
WO-00270 | Cleaning – Control Valve VLV-0011 | VLV-0011 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 5762.1 | 21.5 | 1.4 | 0.5 | 7 | 30.4 | 4 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3379.15 | -2382.95
WO-00272 | Inspection – Instrument/Analyser INST-0122 | INST-0122 | Inst | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 4003.62 | 9.9 | 1 | 3 | 0.6 | 14.5 | 2 | 0.94066 | 730 | 2 | 5 | 2 | 10 | HIGH | 1354.54 | -2649.08
WO-00273 | Inspection – Instrument/Analyser INST-0034 | INST-0034 | Inst | Offsites | Inspection | Critical | FALSE | FALSE | DEFER | 5612.42 | 5.2 | 0.6 | 1.1 | 0.8 | 7.7 | 1 | 0.95536 | 730 | 2 | 5 | 2 | 10 | HIGH | 1375.72 | -4236.7
WO-00274 | Calibration – Instrument/Analyser INST-0105 | INST-0105 | Inst | Unit-200 | Calibration | Medium | FALSE | FALSE | DEFER | 1269.57 | 1.2 | 4 | 6.5 | 0.5 | 12.2 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 170.43
WO-00275 | Inspection – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 3829.06 | 5.6 | 0.4 | 3.3 | 0.1 | 9.4 | 1 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | -354.65
WO-00276 | Inspection – Instrument/Analyser INST-0035 | INST-0035 | Inst | Offsites | Inspection | Medium | FALSE | FALSE | DEFER | 4193.01 | 4.5 | 0.9 | 2.7 | 0.9 | 9 | 1 | 0.96694 | 730 | 2 | 5 | 2 | 10 | HIGH | 1392.4 | -2800.61
WO-00279 | Testing – Control Valve VLV-0114 | VLV-0114 | Vlv | Tank-Farm | Testing | Medium | FALSE | FALSE | DEFER | 14471.06 | 13.1 | 11.6 | 20.7 | 0.4 | 45.8 | 6 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3549.3 | -10921.76
WO-00280 | Replacement – Heat Exchanger HX-0023 | HX-0023 | Hx | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 109960.5 | 55.8 | 13.7 | 6.2 | 5.3 | 81 | 10 | 0.40204 | 127.1654 | 4 | 4 | 4 | 16 | HIGH | 47038.68 | -62921.82
WO-00283 | Inspection – Control Valve VLV-0023 | VLV-0023 | Vlv | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 5980.9 | 3.7 | 1.3 | 4 | 0.1 | 9.1 | 1 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3196.58 | -2784.32
WO-00284 | Replacement – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 49797.79 | 12.5 | 17.1 | 15.2 | 5.5 | 50.3 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -48357.79
WO-00285 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 107439.62 | 45.4 | 18.7 | 22.2 | 9.9 | 96.2 | 12 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | -88438.84
WO-00287 | Cleaning – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 4883.9 | 21.3 | 0.2 | 1.4 | 8.8 | 31.7 | 4 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | -1935.66
WO-00289 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Cleaning | Low | FALSE | FALSE | DEFER | 17955.75 | 15.7 | 1.2 | 0.5 | 5 | 22.4 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -16515.75
WO-00290 | Inspection – Instrument/Analyser INST-0106 | INST-0106 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 5022.06 | 3.5 | 1.7 | 3.3 | 0.4 | 8.9 | 1 | 0.96519 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.87 | -3632.19
WO-00291 | Overhaul – Distillation Tower TWR-0006 | TWR-0006 | Twr | Flare-System | Overhaul | High | FALSE | FALSE | DEFER | 575203.21 | 141.8 | 27.7 | 39.3 | 11.6 | 220.4 | 28 | 0.38082 | 2920 | 5 | 4 | 5 | 20 | CRITICAL | 279904.94 | -295298.27
WO-00292 | Replacement – Electrical Equipment ELEC-0078 | ELEC-0078 | Elec | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 22355.77 | 45.1 | 17.7 | 22.1 | 8.9 | 93.8 | 12 | 0.19668 | 1758.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 1770.15 | -20585.62
WO-00293 | Replacement – Piping/Pipeline Segment PPL-0022 | PPL-0022 | Ppl | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 78361.23 | 57.6 | 15.1 | 13.9 | 7.2 | 93.8 | 12 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | HIGH | 9416.04 | -68945.19
WO-00295 | Overhaul – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Overhaul | Low | FALSE | FALSE | DEFER | 291152.96 | 109.6 | 34.9 | 29.8 | 6.6 | 180.9 | 23 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -289912.59
WO-00297 | Testing – Piping/Pipeline Segment PPL-0043 | PPL-0043 | Ppl | Tank-Farm | Testing | Critical | FALSE | FALSE | DEFER | 10705.36 | 7.1 | 8.1 | 9.9 | 1.8 | 26.9 | 3 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6265.83 | -4439.53
WO-00298 | Overhaul – Control Valve VLV-0025 | VLV-0025 | Vlv | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 427856.76 | 214.4 | 35.7 | 39.6 | 7.5 | 297.2 | 37 | 0.55892 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2999.3 | -424857.46
WO-00299 | Replacement – Control Valve VLV-0051 | VLV-0051 | Vlv | Offsites | Replacement | High | FALSE | FALSE | DEFER | 19763.49 | 58.8 | 5.6 | 6.7 | 6.6 | 77.7 | 10 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2866.96 | -16896.53
WO-00300 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Inspection | Low | FALSE | FALSE | DEFER | 5048.3 | 8.1 | 1.6 | 1.6 | 0.6 | 11.9 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3608.3
WO-00302 | Replacement – Heat Exchanger HX-0001 | HX-0001 | Hx | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 79646.16 | 19 | 2.3 | 19.2 | 4.9 | 45.4 | 6 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | HIGH | 48649.09 | -30997.07
WO-00303 | Cleaning – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 4779.59 | 14.8 | 0.4 | 1.8 | 7.5 | 24.5 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -3339.59
WO-00304 | Cleaning – Control Valve VLV-0083 | VLV-0083 | Vlv | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 17067.52 | 22.8 | 0.2 | 0 | 2.9 | 25.9 | 3 | 0.57925 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3108.4 | -13959.12
WO-00305 | Overhaul – Instrument/Analyser INST-0089 | INST-0089 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 94830.05 | 122.2 | 26.5 | 12.6 | 22.3 | 183.6 | 23 | 0.939 | 730 | 2 | 5 | 2 | 10 | HIGH | 1352.17 | -93477.88
WO-00306 | Replacement – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Replacement | Low | FALSE | FALSE | DEFER | 63294.33 | 24.3 | 17.4 | 15.5 | 5.5 | 62.7 | 8 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -61854.33
WO-00307 | Repair – Piping/Pipeline Segment PPL-0037 | PPL-0037 | Ppl | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 65398.55 | 28.8 | 8 | 14.4 | 5.2 | 56.4 | 7 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | HIGH | 13521.8 | -51876.75
WO-00309 | Overhaul – Instrument/Analyser INST-0115 | INST-0115 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 438422.86 | 142.1 | 37.9 | 17.4 | 18.8 | 216.2 | 27 | 0.96766 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.43 | -437029.43 | WO-00188
WO-00310 | Replacement – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 68936.66 | 52.5 | 6.5 | 18.7 | 9.6 | 87.3 | 11 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | -67907.8
WO-00311 | Overhaul – Storage Tank TNK-0002 | TNK-0002 | Tnk | Unit-300 | Overhaul | Medium | FALSE | FALSE | DEFER | 370216.52 | 238.4 | 31.9 | 12.8 | 4.9 | 288 | 36 | 0.058188 | 3954.2322 | 4 | 2 | 4 | 8 | MEDIUM | 13615.91 | -356600.61
WO-00312 | Overhaul – Heat Exchanger HX-0035 | HX-0035 | Hx | Flare-System | Overhaul | Medium | FALSE | FALSE | DEFER | 159385.54 | 109.5 | 39.8 | 27.5 | 21.4 | 198.2 | 25 | 0.38356 | 327.1654 | 4 | 4 | 4 | 16 | HIGH | 44876.21 | -114509.33
WO-00313 | Testing – Instrument/Analyser INST-0160 | INST-0160 | Inst | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 13383.3 | 6.6 | 17.2 | 4.4 | 2 | 30.2 | 4 | 0.74551 | 109.2559 | 2 | 5 | 2 | 10 | HIGH | 1073.53 | -12309.77
WO-00314 | Cleaning – Electrical Equipment ELEC-0009 | ELEC-0009 | Elec | Utilities | Cleaning | Medium | FALSE | FALSE | DEFER | 21379.69 | 7.9 | 1.7 | 0 | 5.5 | 15.1 | 2 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1991.99 | -19387.7
WO-00315 | Replacement – Centrifugal Pump PMP-0080 | PMP-0080 | Pmp | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 72434.25 | 55.6 | 7.9 | 15.6 | 8.9 | 88 | 11 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | HIGH | 16656.59 | -55777.66
WO-00316 | Inspection – Electrical Equipment ELEC-0077 | ELEC-0077 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 7576.65 | 2.4 | 1.2 | 3.3 | 0.8 | 7.7 | 1 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7273.03 | -303.62
WO-00317 | Inspection – Instrument/Analyser INST-0143 | INST-0143 | Inst | Offsites | Inspection | High | FALSE | FALSE | DEFER | 6165.59 | 3.2 | 0.9 | 3.9 | 0.7 | 8.7 | 1 | 0.83804 | 730 | 2 | 5 | 2 | 10 | HIGH | 1206.78 | -4958.81 | WO-00231
WO-00318 | Replacement – Control Valve VLV-0084 | VLV-0084 | Vlv | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 116432.11 | 31.3 | 2.8 | 8.4 | 4.1 | 46.6 | 6 | 0.6521 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3499.35 | -112932.76
WO-00319 | Replacement – Instrument/Analyser INST-0009 | INST-0009 | Inst | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 8035.52 | 34.7 | 3.5 | 9.5 | 9.9 | 57.6 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -6595.52
WO-00320 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | Inst | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 3920.28 | 3.4 | 0.2 | 3.3 | 0.5 | 7.4 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -2480.28
WO-00322 | Cleaning – Piping/Pipeline Segment PPL-0026 | PPL-0026 | Ppl | Flare-System | Cleaning | Critical | FALSE | FALSE | DEFER | 18318.92 | 10.7 | 1.7 | 0.5 | 8.7 | 21.6 | 3 | 0.23093 | 1285.7481 | 3.65 | 3 | 4 | 12 | HIGH | 11126.23 | -7192.69
WO-00324 | Replacement – Instrument/Analyser INST-0114 | INST-0114 | Inst | Offsites | Replacement | Medium | FALSE | FALSE | DEFER | 18584.52 | 57.1 | 9.9 | 17.8 | 6.2 | 91 | 11 | 0.92825 | 730 | 2 | 5 | 2 | 10 | HIGH | 1336.68 | -17247.84
WO-00325 | Cleaning – Centrifugal Pump PMP-0065 | PMP-0065 | Pmp | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 22560.22 | 20.8 | 1.1 | 1.3 | 6.9 | 30.1 | 4 | 0.5288 | 334.705 | 3 | 4 | 3 | 12 | HIGH | 11421.98 | -11138.24
WO-00326 | Cleaning – Storage Tank TNK-0012 | TNK-0012 | Tnk | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 11645.68 | 22.2 | 1.9 | 1.9 | 8.6 | 34.6 | 4 | 0.011334 | 5499.2321 | 4 | 1 | 4 | 4 | LOW | 2652.22 | -8993.46
WO-00328 | Overhaul – Heat Exchanger HX-0024 | HX-0024 | Hx | Unit-100 | Overhaul | Critical | FALSE | FALSE | DEFER | 163679.09 | 178.6 | 26.3 | 41.7 | 24 | 270.6 | 34 | 0.45456 | 2190 | 4 | 4 | 4 | 16 | HIGH | 53183.64 | -110495.45
WO-00329 | Replacement – Centrifugal Pump PMP-0044 | PMP-0044 | Pmp | Offsites | Replacement | Critical | FALSE | FALSE | DEFER | 35748.99 | 12.9 | 9.1 | 4.3 | 2 | 28.3 | 4 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15461.89 | -20287.1 | WO-00317
WO-00331 | Calibration – Instrument/Analyser INST-0015 | INST-0015 | Inst | Offsites | Calibration | Medium | FALSE | FALSE | DEFER | 918.53 | 1 | 2.9 | 19.8 | 0.1 | 23.8 | 3 | 0.7576 | 54.2559 | 2 | 5 | 2 | 10 | HIGH | 1090.94 | 172.41
WO-00332 | Repair – Control Valve VLV-0015 | VLV-0015 | Vlv | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 21101.18 | 32.6 | 25 | 6.9 | 1 | 65.5 | 8 | 0.56546 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3034.38 | -18066.8
WO-00333 | Inspection – Centrifugal Pump PMP-0051 | PMP-0051 | Pmp | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 7332.46 | 7.1 | 1.2 | 1.8 | 0.7 | 10.8 | 1 | 0.43309 | 745.705 | 3 | 4 | 3 | 12 | HIGH | 9354.8 | 2022.34
WO-00335 | Calibration – Instrument/Analyser INST-0158 | INST-0158 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1280.89 | 0 | 8.5 | 7.3 | 0.3 | 16.1 | 2 | 0.91367 | 730 | 2 | 5 | 2 | 10 | HIGH | 1315.69 | 34.8
WO-00337 | Cleaning – Instrument/Analyser INST-0052 | INST-0052 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 13602.28 | 16.5 | 0.8 | 1.2 | 9.7 | 28.2 | 4 | 0.88183 | 730 | 2 | 5 | 2 | 10 | HIGH | 1269.84 | -12332.44
WO-00338 | Overhaul – Instrument/Analyser INST-0086 | INST-0086 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 209480.22 | 216.7 | 13.7 | 43.7 | 9.1 | 283.2 | 35 | 0.63543 | 499.2559 | 2 | 5 | 2 | 10 | HIGH | 915.02 | -208565.2
WO-00340 | Overhaul – Storage Tank TNK-0004 | TNK-0004 | Tnk | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 414585.55 | 67.4 | 26.3 | 45.5 | 4.7 | 143.9 | 18 | 0.059482 | 3925.2322 | 4 | 2 | 4 | 8 | MEDIUM | 13918.82 | -400666.73
WO-00341 | Cleaning – Control Valve VLV-0042 | VLV-0042 | Vlv | Unit-300 | Cleaning | Low | FALSE | FALSE | DEFER | 22305.07 | 18.3 | 1.6 | 0.4 | 4.8 | 25.1 | 3 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3474.41 | -18830.66
WO-00342 | Repair – Piping/Pipeline Segment PPL-0040 | PPL-0040 | Ppl | Unit-200 | Repair | Medium | FALSE | FALSE | DEFER | 45520.33 | 51.7 | 15.7 | 3.1 | 9 | 79.5 | 10 | 0.088296 | 3800.7482 | 3.65 | 2 | 4 | 8 | MEDIUM | 4254.12 | -41266.21
WO-00343 | Overhaul – Instrument/Analyser INST-0031 | INST-0031 | Inst | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 178472.38 | 108.6 | 13.2 | 38.3 | 15.1 | 175.2 | 22 | 0.92201 | 730 | 2 | 5 | 2 | 10 | HIGH | 1327.7 | -177144.68
WO-00344 | Cleaning – Piping/Pipeline Segment PPL-0002 | PPL-0002 | Ppl | Unit-100 | Cleaning | High | FALSE | FALSE | DEFER | 24501.53 | 6.9 | 0.9 | 1 | 3.3 | 12.1 | 2 | 0.10207 | 3575.748 | 3.65 | 2 | 4 | 8 | MEDIUM | 4917.64 | -19583.89
WO-00347 | Overhaul – Electrical Equipment ELEC-0079 | ELEC-0079 | Elec | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 90645.91 | 124.8 | 24.4 | 9.5 | 9.5 | 168.2 | 21 | 0.44675 | 669.4437 | 2.5 | 4 | 2 | 8 | MEDIUM | 4020.78 | -86625.13
WO-00348 | Cleaning – Instrument/Analyser INST-0127 | INST-0127 | Inst | Utilities | Cleaning | Low | FALSE | FALSE | DEFER | 20348.02 | 17 | 1.7 | 1.6 | 2.8 | 23.1 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -18908.02
WO-00352 | Repair – Instrument/Analyser INST-0133 | INST-0133 | Inst | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 34265.5 | 30.4 | 5.1 | 12.6 | 9.2 | 57.3 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -32825.5 | WO-00004
WO-00354 | Cleaning – Centrifugal Pump PMP-0044 | PMP-0044 | Pmp | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 12152.47 | 27.5 | 1 | 0.8 | 5.2 | 34.5 | 4 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15461.89 | 3309.42
WO-00355 | Replacement – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Replacement | Medium | FALSE | FALSE | DEFER | 88134.26 | 27.8 | 8.9 | 16.3 | 1.5 | 54.5 | 7 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | -82356.25
WO-00356 | Overhaul – Electrical Equipment ELEC-0055 | ELEC-0055 | Elec | Unit-200 | Overhaul | High | FALSE | FALSE | DEFER | 280020.28 | 183.9 | 39.8 | 43.5 | 11.5 | 278.7 | 35 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | MEDIUM | 5383.85 | -274636.43
WO-00358 | Inspection – Centrifugal Pump PMP-0059 | PMP-0059 | Pmp | Tank-Farm | Inspection | Medium | FALSE | FALSE | DEFER | 3613.66 | 7.3 | 1 | 2.5 | 0.9 | 11.7 | 1 | 0.6343 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13700.81 | 10087.15 | WO-00090
WO-00359 | Cleaning – Instrument/Analyser INST-0090 | INST-0090 | Inst | Offsites | Cleaning | High | FALSE | FALSE | DEFER | 23801.28 | 14.2 | 1.6 | 0.3 | 4.3 | 20.4 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -22361.28
WO-00362 | Repair – Storage Tank TNK-0013 | TNK-0013 | Tnk | Flare-System | Repair | Low | FALSE | FALSE | DEFER | 50357.71 | 76.5 | 16.8 | 13.1 | 3.3 | 109.7 | 14 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | LOW | 11354.04 | -39003.67
WO-00363 | Overhaul – Instrument/Analyser INST-0175 | INST-0175 | Inst | Unit-200 | Overhaul | Medium | FALSE | FALSE | DEFER | 109961.07 | 51.2 | 34.7 | 49.3 | 21.9 | 157.1 | 20 | 0.88589 | 730 | 2 | 5 | 2 | 10 | HIGH | 1275.68 | -108685.39
WO-00364 | Testing – Control Valve VLV-0011 | VLV-0011 | Vlv | Tank-Farm | Testing | Medium | FALSE | FALSE | DEFER | 10981.01 | 8.1 | 16 | 5.6 | 0.4 | 30.1 | 4 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3379.15 | -7601.86
WO-00366 | Replacement – Instrument/Analyser INST-0132 | INST-0132 | Inst | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 31837.75 | 25.1 | 5.9 | 6.2 | 3 | 40.2 | 5 | 0.97003 | 730 | 2 | 5 | 2 | 10 | HIGH | 1396.84 | -30440.91
WO-00368 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | Inst | Unit-100 | Cleaning | Medium | FALSE | FALSE | DEFER | 17343.19 | 17.6 | 0.9 | 0.7 | 3.8 | 23 | 3 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -15903.19
WO-00370 | Calibration – Instrument/Analyser INST-0171 | INST-0171 | Inst | Flare-System | Calibration | Medium | FALSE | FALSE | DEFER | 2824.47 | 1.9 | 5.4 | 8.2 | 0.6 | 16.1 | 2 | 0.94889 | 730 | 2 | 5 | 2 | 10 | HIGH | 1366.41 | -1458.06
WO-00372 | Inspection – Electrical Equipment ELEC-0002 | ELEC-0002 | Elec | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 5053.75 | 9.6 | 0.7 | 3.1 | 0.7 | 14.1 | 2 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6708.41 | 1654.66 | WO-00073
WO-00373 | Overhaul – Instrument/Analyser INST-0143 | INST-0143 | Inst | Offsites | Overhaul | Medium | FALSE | FALSE | DEFER | 493005.17 | 189.1 | 42 | 49.5 | 11.4 | 292 | 36 | 0.83804 | 730 | 2 | 5 | 2 | 10 | HIGH | 1206.78 | -491798.39
WO-00374 | Cleaning – Control Valve VLV-0016 | VLV-0016 | Vlv | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 16998.51 | 21.8 | 1.5 | 1.8 | 4.8 | 29.9 | 4 | 0.61237 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3286.11 | -13712.4 | WO-00257
WO-00375 | Replacement – Control Valve VLV-0090 | VLV-0090 | Vlv | Flare-System | Replacement | High | FALSE | FALSE | DEFER | 73375.4 | 47.1 | 16.2 | 12.4 | 5.6 | 81.3 | 10 | 0.65442 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3511.79 | -69863.61
WO-00378 | Replacement – Control Valve VLV-0030 | VLV-0030 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 86445.18 | 33.7 | 11.9 | 15.9 | 4.4 | 65.9 | 8 | 0.57791 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3101.23 | -83343.95
WO-00380 | Cleaning – Instrument/Analyser INST-0056 | INST-0056 | Inst | Unit-200 | Cleaning | Low | FALSE | FALSE | DEFER | 18206.24 | 15.5 | 0.6 | 1.1 | 4.9 | 22.1 | 3 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | HIGH | 1103.88 | -17102.36
WO-00381 | Replacement – Instrument/Analyser INST-0061 | INST-0061 | Inst | Unit-300 | Replacement | Medium | FALSE | FALSE | DEFER | 25206.3 | 38 | 9.1 | 5.9 | 6.1 | 59.1 | 7 | 0.97132 | 730 | 2 | 5 | 2 | 10 | HIGH | 1398.7 | -23807.6
WO-00385 | Inspection – Instrument/Analyser INST-0131 | INST-0131 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 1027.45 | 3 | 0.5 | 4.6 | 0.5 | 8.6 | 1 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | HIGH | 1028.86 | 1.41
WO-00386 | Repair – Control Valve VLV-0078 | VLV-0078 | Vlv | Utilities | Repair | Low | FALSE | FALSE | DEFER | 59325.56 | 44 | 26.5 | 15.4 | 7.7 | 93.6 | 12 | 0.50925 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2732.74 | -56592.82
WO-00390 | Overhaul – Control Valve VLV-0027 | VLV-0027 | Vlv | Unit-100 | Overhaul | Low | FALSE | FALSE | DEFER | 73766.65 | 144.4 | 33.2 | 18.5 | 16.2 | 212.3 | 27 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | HIGH | 2116.63 | -71650.02
WO-00391 | Inspection – Instrument/Analyser INST-0134 | INST-0134 | Inst | Tank-Farm | Inspection | High | FALSE | FALSE | DEFER | 2294.11 | 3.7 | 0.2 | 1.7 | 0.6 | 6.2 | 1 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -854.11
WO-00393 | Testing – Heat Exchanger HX-0034 | HX-0034 | Hx | Flare-System | Testing | Low | FALSE | FALSE | DEFER | 14454.01 | 8.9 | 10.5 | 14.2 | 0.6 | 34.2 | 4 | 0.2662 | 1472.1654 | 4 | 3 | 4 | 12 | HIGH | 31144.9 | 16690.89 | WO-00363
WO-00394 | Replacement – Control Valve VLV-0059 | VLV-0059 | Vlv | Unit-100 | Replacement | High | FALSE | FALSE | DEFER | 47451.41 | 30.3 | 4.3 | 11.7 | 8.7 | 55 | 7 | 0.52703 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2828.17 | -44623.24
WO-00396 | Calibration – Instrument/Analyser INST-0173 | INST-0173 | Inst | Offsites | Calibration | High | FALSE | FALSE | DEFER | 2215.12 | 1.9 | 5.4 | 15.3 | 0.7 | 23.3 | 3 | 0.96759 | 730 | 2 | 5 | 2 | 10 | HIGH | 1393.33 | -821.79
WO-00397 | Replacement – Control Valve VLV-0076 | VLV-0076 | Vlv | Unit-300 | Replacement | High | FALSE | FALSE | DEFER | 65930.4 | 49.4 | 10.3 | 8.6 | 9.9 | 78.2 | 10 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -63424.52
WO-00398 | Testing – Instrument/Analyser INST-0019 | INST-0019 | Inst | Offsites | Testing | Medium | FALSE | FALSE | DEFER | 12231.17 | 17.1 | 19.9 | 8.2 | 1.3 | 46.5 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10791.17
WO-00401 | Replacement – Control Valve VLV-0004 | VLV-0004 | Vlv | Unit-200 | Replacement | Medium | FALSE | FALSE | DEFER | 34453.37 | 37.7 | 3.1 | 9.4 | 1.4 | 51.6 | 6 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | MEDIUM | 1675.84 | -32777.53 | WO-00202
WO-00402 | Cleaning – Instrument/Analyser INST-0060 | INST-0060 | Inst | Unit-300 | Cleaning | Medium | FALSE | FALSE | DEFER | 9099.52 | 7.5 | 1.9 | 1.2 | 7.4 | 18 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -7659.52
WO-00404 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | Inst | Utilities | Inspection | Medium | FALSE | FALSE | DEFER | 7670.91 | 8.9 | 0.6 | 5 | 0.3 | 14.8 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -6230.91
WO-00405 | Repair – Instrument/Analyser INST-0083 | INST-0083 | Inst | Tank-Farm | Repair | High | FALSE | FALSE | DEFER | 25758.52 | 49.4 | 21.3 | 4.3 | 4.8 | 79.8 | 10 | 0.96568 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.58 | -24367.94
WO-00408 | Cleaning – Piping/Pipeline Segment PPL-0023 | PPL-0023 | Ppl | Utilities | Cleaning | Medium | FALSE | FALSE | DEFER | 14403.55 | 21.6 | 2 | 1.2 | 8.5 | 33.3 | 4 | 0.18038 | 2226.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8690.83 | -5712.72
WO-00409 | Repair – Instrument/Analyser INST-0054 | INST-0054 | Inst | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 76452.94 | 25.8 | 8.3 | 12.6 | 5 | 51.7 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -75012.94
WO-00411 | Overhaul – Control Valve VLV-0027 | VLV-0027 | Vlv | Unit-100 | Overhaul | High | FALSE | FALSE | DEFER | 334021.83 | 187.1 | 35.3 | 23.1 | 4.1 | 249.6 | 31 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | HIGH | 2116.63 | -331905.2
WO-00412 | Testing – Instrument/Analyser INST-0172 | INST-0172 | Inst | Unit-200 | Testing | High | FALSE | FALSE | DEFER | 13873.83 | 7.9 | 9.2 | 12.7 | 1.4 | 31.2 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -12433.83
WO-00414 | Replacement – Instrument/Analyser INST-0137 | INST-0137 | Inst | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 68694.19 | 33.6 | 16.3 | 23.1 | 2.2 | 75.2 | 9 | 0.96365 | 730 | 2 | 5 | 2 | 10 | HIGH | 1387.65 | -67306.54
WO-00416 | Overhaul – Distillation Tower TWR-0012 | TWR-0012 | Twr | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 333104.76 | 48.1 | 15.3 | 34.2 | 14.3 | 111.9 | 14 | 0.3587 | 94.0539 | 5 | 4 | 5 | 20 | CRITICAL | 263641.88 | -69462.88
WO-00417 | Cleaning – Instrument/Analyser INST-0164 | INST-0164 | Inst | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 15434.46 | 23.6 | 0.1 | 1.4 | 7.7 | 32.8 | 4 | 0.96529 | 730 | 2 | 5 | 2 | 10 | HIGH | 1390.01 | -14044.45
WO-00418 | Inspection – Control Valve VLV-0115 | VLV-0115 | Vlv | Tank-Farm | Inspection | High | FALSE | FALSE | DEFER | 2182.51 | 3.6 | 1 | 1.5 | 0.7 | 6.8 | 1 | 0.48494 | 162.3748 | 2.65 | 4 | 3 | 12 | HIGH | 2602.31 | 419.8
WO-00419 | Inspection – Electrical Equipment ELEC-0009 | ELEC-0009 | Elec | Utilities | Inspection | High | FALSE | FALSE | DEFER | 2962.75 | 3.5 | 2 | 2.2 | 0.2 | 7.9 | 1 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1991.99 | -970.76
WO-00420 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Replacement | Low | FALSE | FALSE | DEFER | 74672.62 | 48.7 | 8.6 | 16.5 | 5.3 | 79.1 | 10 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -73432.25
WO-00422 | Inspection – Instrument/Analyser INST-0055 | INST-0055 | Inst | Tank-Farm | Inspection | Medium | FALSE | FALSE | DEFER | 6421.99 | 6.8 | 1.1 | 3.1 | 0.9 | 11.9 | 1 | 0.90654 | 730 | 2 | 5 | 2 | 10 | HIGH | 1305.41 | -5116.58
WO-00424 | Repair – Instrument/Analyser INST-0011 | INST-0011 | Inst | Unit-100 | Repair | Medium | FALSE | FALSE | DEFER | 44641.37 | 10.1 | 18.6 | 3 | 3.9 | 35.6 | 4 | 0.79553 | 730 | 2 | 5 | 2 | 10 | HIGH | 1145.57 | -43495.8
WO-00425 | Repair – Control Valve VLV-0107 | VLV-0107 | Vlv | Utilities | Repair | Medium | FALSE | FALSE | DEFER | 29908.06 | 87.1 | 27.9 | 2.4 | 3.2 | 120.6 | 15 | 0.5966 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3201.49 | -26706.57
WO-00427 | Inspection – Electrical Equipment ELEC-0068 | ELEC-0068 | Elec | Flare-System | Inspection | Medium | FALSE | FALSE | DEFER | 1582.18 | 9.5 | 1.8 | 4.2 | 0.1 | 15.6 | 2 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | MEDIUM | 1589.67 | 7.49
WO-00430 | Overhaul – Instrument/Analyser INST-0098 | INST-0098 | Inst | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 325823.07 | 130.5 | 11 | 41.1 | 6.5 | 189.1 | 24 | 0.96482 | 730 | 2 | 5 | 2 | 10 | HIGH | 1389.33 | -324433.74 | WO-00356
WO-00431 | Replacement – Instrument/Analyser INST-0116 | INST-0116 | Inst | Unit-100 | Replacement | Low | FALSE | FALSE | DEFER | 37204.69 | 28.9 | 13.1 | 10.2 | 2.6 | 54.8 | 7 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -35764.69
WO-00432 | Testing – Instrument/Analyser INST-0103 | INST-0103 | Inst | Unit-300 | Testing | Low | FALSE | FALSE | DEFER | 7149.47 | 7.9 | 4.9 | 4.7 | 0.8 | 18.3 | 2 | 0.96042 | 730 | 2 | 5 | 2 | 10 | HIGH | 1383.01 | -5766.46
WO-00434 | Repair – Piping/Pipeline Segment PPL-0034 | PPL-0034 | Ppl | Unit-100 | Repair | High | FALSE | FALSE | DEFER | 30171.52 | 68.5 | 14.1 | 18.2 | 6.8 | 107.6 | 13 | 0.081176 | 3915.748 | 3.65 | 2 | 4 | 8 | MEDIUM | 3911.07 | -26260.45
WO-00435 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 7274.18 | 6.4 | 0.6 | 4.5 | 0.1 | 11.6 | 1 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7312.2 | 38.02
WO-00437 | Testing – Instrument/Analyser INST-0004 | INST-0004 | Inst | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 8843.35 | 10.8 | 11.7 | 18.2 | 0.3 | 41 | 5 | 0.85899 | 730 | 2 | 5 | 2 | 10 | HIGH | 1236.94 | -7606.41 | WO-00370
WO-00439 | Inspection – Instrument/Analyser INST-0024 | INST-0024 | Inst | Unit-100 | Inspection | Medium | FALSE | FALSE | DEFER | 6398.13 | 9.3 | 1.9 | 2.2 | 0.8 | 14.2 | 2 | 0.86316 | 730 | 2 | 5 | 2 | 10 | HIGH | 1242.94 | -5155.19
WO-00440 | Repair – Instrument/Analyser INST-0037 | INST-0037 | Inst | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 44772.46 | 21.4 | 6.1 | 19.2 | 4.8 | 51.5 | 6 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -43332.46
WO-00441 | Replacement – Instrument/Analyser INST-0155 | INST-0155 | Inst | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 48577.46 | 57.1 | 3.1 | 6.4 | 8.1 | 74.7 | 9 | 0.95682 | 730 | 2 | 5 | 2 | 10 | HIGH | 1377.82 | -47199.64 | WO-00164
WO-00443 | Repair – Control Valve VLV-0032 | VLV-0032 | Vlv | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 72062.39 | 43.9 | 12.3 | 20 | 7.9 | 84.1 | 11 | 0.59751 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 3206.38 | -68856.01
WO-00445 | Cleaning – Electrical Equipment ELEC-0060 | ELEC-0060 | Elec | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 6075.31 | 22.4 | 1.5 | 0.2 | 6.8 | 30.9 | 4 | 0.76691 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6902.2 | 826.89
WO-00446 | Repair – Control Valve VLV-0062 | VLV-0062 | Vlv | Unit-300 | Repair | High | FALSE | FALSE | DEFER | 18075.11 | 88.7 | 16 | 3.7 | 2 | 110.4 | 14 | 0.34935 | 1279.3751 | 2.65 | 3 | 3 | 9 | MEDIUM | 1874.71 | -16200.4
WO-00447 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | Pmp | Unit-200 | Replacement | High | FALSE | FALSE | DEFER | 62086.67 | 46.9 | 5.4 | 23.9 | 2.5 | 78.7 | 10 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | HIGH | 19000.78 | -43085.89
WO-00448 | Testing – Piping/Pipeline Segment PPL-0031 | PPL-0031 | Ppl | Unit-100 | Testing | High | FALSE | FALSE | DEFER | 12571.36 | 13.7 | 18.3 | 6.7 | 0 | 38.7 | 5 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | HIGH | 14183.6 | 1612.24
WO-00451 | Replacement – Electrical Equipment ELEC-0026 | ELEC-0026 | Elec | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 41129.16 | 29.8 | 12.9 | 23.1 | 5.8 | 71.6 | 9 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5492.41 | -35636.75
WO-00459 | Testing – Instrument/Analyser INST-0038 | INST-0038 | Inst | Unit-200 | Testing | Critical | FALSE | FALSE | DEFER | 12800 | 13.2 | 15.7 | 16.1 | 1.1 | 46.1 | 6 | 0.95252 | 730 | 2 | 5 | 2 | 10 | HIGH | 1371.63 | -11428.37
WO-00460 | Calibration – Centrifugal Pump PMP-0010 | PMP-0010 | Pmp | Tank-Farm | Calibration | Critical | FALSE | FALSE | DEFER | 2205.74 | 1 | 9 | 14.8 | 0.4 | 25.2 | 3 | 0.61598 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13305.23 | 11099.49 | WO-00148
WO-00462 | Calibration – Instrument/Analyser INST-0129 | INST-0129 | Inst | Tank-Farm | Calibration | Critical | FALSE | FALSE | DEFER | 1272.23 | 0.3 | 2.9 | 5.4 | 0.4 | 9 | 1 | 0.59502 | 607.2559 | 2 | 4 | 2 | 8 | MEDIUM | 856.83 | -415.4
WO-00463 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | Pmp | Tank-Farm | Replacement | Low | FALSE | FALSE | DEFER | 115576.32 | 34.4 | 16.8 | 6.6 | 3.4 | 61.2 | 8 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15560.77 | -100015.55
WO-00464 | Replacement – Electrical Equipment ELEC-0053 | ELEC-0053 | Elec | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 79566.7 | 58.8 | 11.9 | 10.1 | 5.8 | 86.6 | 11 | 0.79521 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 7156.92 | -72409.78
WO-00466 | Repair – Instrument/Analyser INST-0057 | INST-0057 | Inst | Offsites | Repair | High | FALSE | FALSE | DEFER | 25332.85 | 37.6 | 26.2 | 18.1 | 9.2 | 91.1 | 11 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | HIGH | 1048.11 | -24284.74
WO-00468 | Testing – Instrument/Analyser INST-0020 | INST-0020 | Inst | Utilities | Testing | Low | FALSE | FALSE | DEFER | 9926.89 | 19.1 | 5.5 | 11.2 | 0 | 35.8 | 4 | 0.7612 | 37.2559 | 2 | 5 | 2 | 10 | HIGH | 1096.12 | -8830.77
WO-00469 | Repair – Piping/Pipeline Segment PPL-0018 | PPL-0018 | Ppl | Unit-200 | Repair | Critical | FALSE | FALSE | DEFER | 4188.1 | 9.7 | 13.5 | 6.7 | 8.6 | 38.5 | 5 | 0.068723 | 4114.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 3311.1 | -877
WO-00471 | Replacement – Control Valve VLV-0041 | VLV-0041 | Vlv | Offsites | Replacement | High | FALSE | FALSE | DEFER | 109158.75 | 50.7 | 16.6 | 16.3 | 9 | 92.6 | 12 | 0.41899 | 798.375 | 2.65 | 4 | 3 | 12 | HIGH | 2248.38 | -106910.37
WO-00472 | Calibration – Instrument/Analyser INST-0069 | INST-0069 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 1332.45 | 1.2 | 10 | 19.8 | 0.5 | 31.5 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | 107.55
WO-00473 | Repair – Piping/Pipeline Segment PPL-0020 | PPL-0020 | Ppl | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 78879.59 | 79.6 | 5.7 | 7.8 | 9.1 | 102.2 | 13 | 0.12468 | 3198.7481 | 3.65 | 2 | 4 | 8 | MEDIUM | 6007.02 | -72872.57
WO-00474 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | Inst | Utilities | Calibration | Medium | FALSE | FALSE | DEFER | 2070.19 | 0.8 | 5.2 | 16.9 | 0.3 | 23.2 | 3 | 0.81141 | 730 | 2 | 5 | 2 | 10 | HIGH | 1168.43 | -901.76
WO-00477 | Repair – Control Valve VLV-0044 | VLV-0044 | Vlv | Offsites | Repair | Medium | FALSE | FALSE | DEFER | 47004.01 | 18.7 | 4.1 | 10.9 | 9.5 | 43.2 | 5 | 0.6655 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3571.26 | -43432.75
WO-00478 | Replacement – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Replacement | High | FALSE | FALSE | DEFER | 8556.03 | 55.6 | 7.9 | 18.1 | 7.2 | 88.8 | 11 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -7170.47
WO-00479 | Inspection – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Inspection | Medium | FALSE | FALSE | DEFER | 3449 | 4.5 | 1.4 | 4.3 | 0.2 | 10.4 | 1 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -1316.83
WO-00481 | Overhaul – Instrument/Analyser INST-0135 | INST-0135 | Inst | Tank-Farm | Overhaul | Medium | FALSE | FALSE | DEFER | 595019.48 | 170.8 | 47.3 | 14.1 | 13 | 245.2 | 31 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -593579.48
WO-00482 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | Inst | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 77738.48 | 34.6 | 19.9 | 7.5 | 9.4 | 71.4 | 9 | 0.86137 | 730 | 2 | 5 | 2 | 10 | HIGH | 1240.37 | -76498.11
WO-00483 | Overhaul – Instrument/Analyser INST-0026 | INST-0026 | Inst | Unit-300 | Overhaul | Low | FALSE | FALSE | DEFER | 324232.1 | 93.1 | 48.5 | 46.3 | 23.5 | 211.4 | 26 | 0.96219 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.56 | -322846.54
WO-00484 | Cleaning – Control Valve VLV-0067 | VLV-0067 | Vlv | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 11840.45 | 24.4 | 0 | 1.7 | 6 | 32.1 | 4 | 0.60745 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3259.71 | -8580.74
WO-00485 | Replacement – Pressure Vessel VSL-0011 | VSL-0011 | Vsl | Unit-100 | Replacement | Critical | FALSE | FALSE | DEFER | 47391.66 | 9.6 | 9.6 | 12.2 | 3 | 34.4 | 4 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | HIGH | 36127.93 | -11263.73
WO-00486 | Cleaning – Instrument/Analyser INST-0018 | INST-0018 | Inst | Unit-200 | Cleaning | Medium | FALSE | FALSE | DEFER | 8626.51 | 23.9 | 0.2 | 1.2 | 3.3 | 28.6 | 4 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -7186.51
WO-00487 | Cleaning – Electrical Equipment ELEC-0036 | ELEC-0036 | Elec | Unit-300 | Cleaning | High | FALSE | FALSE | DEFER | 16415.14 | 14.3 | 1 | 0.4 | 5.7 | 21.4 | 3 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2132.17 | -14282.97
WO-00489 | Cleaning – Electrical Equipment ELEC-0022 | ELEC-0022 | Elec | Unit-300 | Cleaning | Critical | FALSE | FALSE | DEFER | 20941.14 | 22.5 | 0.9 | 0.4 | 8.9 | 32.7 | 4 | 0.31845 | 1278.4434 | 2.5 | 3 | 2 | 6 | MEDIUM | 2866.08 | -18075.06 | WO-00157
WO-00490 | Replacement – Centrifugal Pump PMP-0018 | PMP-0018 | Pmp | Unit-200 | Replacement | Critical | FALSE | FALSE | DEFER | 103510.74 | 28.4 | 4.1 | 9.3 | 6.4 | 48.2 | 6 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13798.72 | -89712.02
WO-00491 | Cleaning – Instrument/Analyser INST-0179 | INST-0179 | Inst | Tank-Farm | Cleaning | Medium | FALSE | FALSE | DEFER | 11515.89 | 12 | 0.5 | 1.6 | 5.2 | 19.3 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -10075.89
WO-00492 | Overhaul – Instrument/Analyser INST-0023 | INST-0023 | Inst | Unit-100 | Overhaul | Low | FALSE | FALSE | DEFER | 68742.3 | 128.1 | 29.3 | 27.2 | 20.3 | 204.9 | 26 | 0.74528 | 110.2559 | 2 | 5 | 2 | 10 | HIGH | 1073.21 | -67669.09
WO-00494 | Replacement – Instrument/Analyser INST-0001 | INST-0001 | Inst | Offsites | Replacement | Critical | FALSE | FALSE | DEFER | 108824.09 | 52.1 | 9.6 | 22.2 | 2.1 | 86 | 11 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -107384.09
WO-00495 | Replacement – Instrument/Analyser INST-0006 | INST-0006 | Inst | Utilities | Replacement | Medium | FALSE | FALSE | DEFER | 70025.11 | 26.3 | 19 | 9.1 | 3.5 | 57.9 | 7 | 0.96225 | 730 | 2 | 5 | 2 | 10 | HIGH | 1385.63 | -68639.48
WO-00497 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | Elec | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 7649.4 | 7.5 | 0.9 | 1.8 | 0.9 | 11.1 | 1 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5778.01 | -1871.39 | WO-00445
WO-00498 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | Inst | Unit-300 | Calibration | Low | FALSE | FALSE | DEFER | 2337.31 | 0.6 | 6 | 7.6 | 0.4 | 14.6 | 2 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -897.31
WO-00502 | Replacement – Electrical Equipment ELEC-0074 | ELEC-0074 | Elec | Tank-Farm | Replacement | High | FALSE | FALSE | DEFER | 113684.13 | 9.6 | 4.4 | 15.8 | 7.3 | 37.1 | 5 | 0.48585 | 455.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4372.65 | -109311.48
WO-00504 | Cleaning – Instrument/Analyser INST-0024 | INST-0024 | Inst | Unit-100 | Cleaning | High | FALSE | FALSE | DEFER | 8621.32 | 10.1 | 2 | 0.4 | 8.3 | 20.8 | 3 | 0.86316 | 730 | 2 | 5 | 2 | 10 | HIGH | 1242.94 | -7378.38 | WO-00383
WO-00506 | Replacement – Piping/Pipeline Segment PPL-0008 | PPL-0008 | Ppl | Unit-300 | Replacement | Critical | FALSE | FALSE | DEFER | 34984.64 | 45.4 | 15.3 | 10.5 | 8.9 | 80.1 | 10 | 0.21919 | 1509.7483 | 3.65 | 3 | 4 | 12 | HIGH | 10560.48 | -24424.16
WO-00507 | Inspection – Electrical Equipment ELEC-0061 | ELEC-0061 | Elec | Offsites | Inspection | High | FALSE | FALSE | DEFER | 5039.02 | 2.9 | 0.6 | 3 | 0.3 | 6.8 | 1 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6951.19 | 1912.17 | WO-00389
WO-00509 | Inspection – Control Valve VLV-0048 | VLV-0048 | Vlv | Unit-200 | Inspection | High | FALSE | FALSE | DEFER | 2392.49 | 8.7 | 1.5 | 3.5 | 0 | 13.7 | 2 | 0.35245 | 1261.3751 | 2.65 | 4 | 3 | 12 | HIGH | 1891.34 | -501.15
WO-00510 | Overhaul – Instrument/Analyser INST-0074 | INST-0074 | Inst | Utilities | Overhaul | Medium | FALSE | FALSE | DEFER | 451608.27 | 132.8 | 8.7 | 15.7 | 15.8 | 173 | 22 | 0.92649 | 730 | 2 | 5 | 2 | 10 | HIGH | 1334.15 | -450274.12
WO-00512 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | Ppl | Unit-100 | Calibration | Medium | FALSE | FALSE | DEFER | 2917.45 | 1.9 | 4.2 | 4.5 | 0.3 | 10.9 | 1 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | HIGH | 8869.41 | 5951.96 | WO-00338
WO-00515 | Testing – Control Valve VLV-0089 | VLV-0089 | Vlv | Unit-200 | Testing | Low | FALSE | FALSE | DEFER | 4923.44 | 8.5 | 16.5 | 22.9 | 1.3 | 49.2 | 6 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3326.16 | -1597.28
WO-00517 | Overhaul – Instrument/Analyser INST-0091 | INST-0091 | Inst | Tank-Farm | Overhaul | Low | FALSE | FALSE | DEFER | 525923.65 | 220.1 | 49.2 | 45.2 | 5 | 319.5 | 40 | 0.94394 | 730 | 2 | 5 | 2 | 10 | HIGH | 1359.27 | -524564.38
WO-00518 | Overhaul – Electrical Equipment ELEC-0014 | ELEC-0014 | Elec | Tank-Farm | Overhaul | High | FALSE | FALSE | DEFER | 396197.22 | 118.9 | 42.2 | 32.2 | 20.9 | 214.2 | 27 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 5975.81 | -390221.41
WO-00522 | Overhaul – Piping/Pipeline Segment PPL-0004 | PPL-0004 | Ppl | Unit-100 | Overhaul | Critical | FALSE | FALSE | DEFER | 182873.9 | 220.9 | 35.5 | 33.8 | 21.7 | 311.9 | 39 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | HIGH | 15082.22 | -167791.68
WO-00523 | Repair – Heat Exchanger HX-0018 | HX-0018 | Hx | Unit-200 | Repair | Critical | FALSE | FALSE | DEFER | 54873.42 | 41.1 | 10.7 | 3.9 | 9.5 | 65.2 | 8 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | HIGH | 33820.42 | -21053
WO-00524 | Replacement – Storage Tank TNK-0006 | TNK-0006 | Tnk | Unit-100 | Replacement | Medium | FALSE | FALSE | DEFER | 84477.33 | 44.9 | 4.9 | 20.3 | 5.6 | 75.7 | 9 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | HIGH | 41445.54 | -43031.79
WO-00526 | Repair – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Repair | Medium | FALSE | FALSE | DEFER | 67432.86 | 96.2 | 27.5 | 10 | 4.6 | 138.3 | 17 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | -59619.83
WO-00527 | Testing – Control Valve VLV-0002 | VLV-0002 | Vlv | Utilities | Testing | Medium | FALSE | FALSE | DEFER | 14606.12 | 15.8 | 8 | 22.9 | 1.9 | 48.6 | 6 | 0.67434 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3618.69 | -10987.43
WO-00528 | Repair – Instrument/Analyser INST-0068 | INST-0068 | Inst | Flare-System | Repair | High | FALSE | FALSE | DEFER | 45771.76 | 94.9 | 6.4 | 17.6 | 1.5 | 120.4 | 15 | 1 | 730 | 2 | 5 | 2 | 10 | HIGH | 1440 | -44331.76
WO-00531 | Testing – Instrument/Analyser INST-0084 | INST-0084 | Inst | Unit-300 | Testing | Medium | FALSE | FALSE | DEFER | 10935.82 | 14.2 | 11.2 | 4 | 0.5 | 29.9 | 4 | 0.96708 | 730 | 2 | 5 | 2 | 10 | HIGH | 1392.6 | -9543.22
WO-00533 | Replacement – Centrifugal Pump PMP-0053 | PMP-0053 | Pmp | Utilities | Replacement | High | FALSE | FALSE | DEFER | 61017.45 | 28.1 | 15.1 | 23.2 | 6.3 | 72.7 | 9 | 0.71868 | 1825 | 3 | 5 | 3 | 15 | HIGH | 15523.41 | -45494.04
WO-00534 | Replacement – Control Valve VLV-0029 | VLV-0029 | Vlv | Tank-Farm | Replacement | Medium | FALSE | FALSE | DEFER | 69932.56 | 24.6 | 2 | 21.3 | 4.9 | 52.8 | 7 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | HIGH | 2505.88 | -67426.68
WO-00537 | Repair – Centrifugal Pump PMP-0047 | PMP-0047 | Pmp | Flare-System | Repair | Medium | FALSE | FALSE | DEFER | 56838.33 | 94.1 | 19.3 | 12.4 | 3.7 | 129.5 | 16 | 0.60929 | 1825 | 3 | 5 | 3 | 15 | HIGH | 13160.57 | -43677.76
WO-00538 | Repair – Electrical Equipment ELEC-0002 | ELEC-0002 | Elec | Unit-200 | Repair | High | FALSE | FALSE | DEFER | 52412.67 | 29.4 | 18.1 | 15.6 | 9.5 | 72.6 | 9 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | HIGH | 6708.41 | -45704.26 | WO-00425
WO-00539 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | Inst | Utilities | Inspection | High | FALSE | FALSE | DEFER | 3655.78 | 3 | 2 | 2.7 | 0.5 | 8.2 | 1 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | HIGH | 1099.43 | -2556.35
WO-00540 | Overhaul – Instrument/Analyser INST-0030 | INST-0030 | Inst | Flare-System | Overhaul | Low | FALSE | FALSE | DEFER | 591045.95 | 137.7 | 8.4 | 18.2 | 23.6 | 187.9 | 23 | 0.88342 | 730 | 2 | 5 | 2 | 10 | HIGH | 1272.12 | -589773.83
WO-00541 | Replacement – Electrical Equipment ELEC-0032 | ELEC-0032 | Elec | Unit-200 | Replacement | Low | FALSE | FALSE | DEFER | 75755.37 | 12 | 12.4 | 6.5 | 8.4 | 39.3 | 5 | 0.53526 | 160.4436 | 2.5 | 4 | 2 | 8 | MEDIUM | 4817.3 | -70938.07
WO-00543 | Inspection – Control Valve VLV-0119 | VLV-0119 | Vlv | Flare-System | Inspection | High | FALSE | FALSE | DEFER | 6956.37 | 2.6 | 1.1 | 2.8 | 0.9 | 7.4 | 1 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | HIGH | 2948.24 | -4008.13
WO-00548 | Overhaul – Piping/Pipeline Segment PPL-0044 | PPL-0044 | Ppl | Unit-300 | Overhaul | High | FALSE | FALSE | DEFER | 395099.09 | 220.6 | 41.6 | 42.6 | 9.2 | 314 | 39 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | HIGH | 7813.03 | -387286.06
WO-00549 | Cleaning – Instrument/Analyser INST-0040 | INST-0040 | Inst | Flare-System | Cleaning | High | FALSE | FALSE | DEFER | 2060.58 | 22.5 | 0.6 | 0.6 | 4.1 | 27.8 | 3 | 0.90208 | 730 | 2 | 5 | 2 | 10 | HIGH | 1299 | -761.58
WO-00550 | Replacement – Control Valve VLV-0054 | VLV-0054 | Vlv | Utilities | Replacement | Critical | FALSE | FALSE | DEFER | 74554.82 | 38.3 | 6.6 | 8.1 | 8.4 | 61.4 | 8 | 0.65259 | 1095 | 2.65 | 5 | 3 | 15 | HIGH | 3501.98 | -71052.84

## SummaryKPIs
Total WOs | WOs Selected | WOs Deferred | Budget ($) | Budget Used ($) | Budget Utilisation (%) | Mech Hours Capacity | Mech Hours Used | Mech Utilisation (%) | Elec Hours Capacity | Elec Hours Used | Elec Utilisation (%) | Inst Hours Capacity | Inst Hours Used | Inst Utilisation (%) | Net Value ($) | ROI (×) | Risk Score Reduced | Solver Status | Solve Time (s)
550 | 199 | 351 | 5000000 | 4999232.39 | 100 | 15000 | 3275.9 | 21.8 | 8000 | 1182.9 | 14.8 | 6000 | 1553.6 | 25.9 | 4710073.69 | 0.94 | 2742 | OPTIMAL | 0.093

## CapacityUtilization
Trade | Capacity (h) | Used (h) | Available (h) | Utilisation (%)
Mechanical | 15000 | 3275.9 | 11724.1 | 21.8
Electrical | 8000 | 1182.9 | 6817.1 | 14.8
Instrumentation | 6000 | 1553.6 | 4446.4 | 25.9
Civil | 2500 | 451.9 | 2048.1 | 18.1

## RiskMatrix
likelihood_tier | 1 | 2 | 3 | 4 | 5
1 | 0 | 0 | 0 | 8 | 4
2 | 0 | 0 | 4 | 15 | 4
3 | 0 | 18 | 7 | 46 | 17
4 | 0 | 18 | 55 | 22 | 20
5 | 0 | 210 | 89 | 0 | 13

## ByArea
area | tasks | total_cost | total_mech | avg_risk_score | risk_score_total
Flare-System | 27 | 1122122.94 | 686.3 | 15.96 | 431
Offsites | 23 | 380953.54 | 253.3 | 13.09 | 301
Tank-Farm | 27 | 248545.39 | 302.5 | 13.26 | 358
Unit-100 | 38 | 1369551.79 | 719.1 | 14.29 | 543
Unit-200 | 40 | 801112.8 | 436.6 | 13.78 | 551
Unit-300 | 24 | 834205.28 | 549.8 | 12.38 | 297
Utilities | 20 | 242740.65 | 328.3 | 13.05 | 261

## ByEquipmentClass
asset_class | tasks | total_cost | total_value | avg_failure_prob | avg_risk_score | roi
Cmp | 18 | 788336.61 | 4172970.77 | 0.789 | 23.611 | 5.29
Elec | 19 | 45932.01 | 63936.95 | 0.643 | 9.158 | 1.39
Hx | 25 | 734608.95 | 380797.87 | 0.381 | 14.72 | 0.52
Inst | 17 | 311056.15 | -288213.79 | 0.933 | 9.882 | -0.93
Pmp | 47 | 2041914.6 | -1349982.07 | 0.682 | 13.915 | -0.66
Ppl | 16 | 136882.04 | 33564.37 | 0.221 | 11.5 | 0.25
Tnk | 12 | 116444.64 | 255997.26 | 0.133 | 9 | 2.2
Twr | 6 | 68624.75 | 790895.33 | 0.195 | 14.167 | 11.52
Vlv | 16 | 214305.54 | -164551.3 | 0.579 | 13.5 | -0.77
Vsl | 23 | 541127.1 | 814658.3 | 0.271 | 15.652 | 1.51

## Dim_Asset
asset_tag | asset_class | asset_name | area | replace_usd | c_safety | c_env | c_prod | c_cost
ELEC-0024 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
VLV-0026 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
PPL-0012 | Ppl | Piping/Pipeline Segment | Utilities | 88000 | 4 | 4 | 3 | 3
VSL-0019 | Vsl | Pressure Vessel | Unit-200 | 290000 | 5 | 5 | 5 | 5
INST-0114 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
INST-0142 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
INST-0121 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
INST-0082 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
INST-0007 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
INST-0111 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
TNK-0006 | Tnk | Storage Tank | Unit-100 | 390000 | 4 | 5 | 3 | 4
VLV-0110 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
INST-0026 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
HX-0033 | Hx | Heat Exchanger | Unit-200 | 195000 | 4 | 3 | 5 | 4
VLV-0089 | Vlv | Control Valve | Unit-200 | 13500 | 3 | 2 | 3 | 2
ELEC-0008 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
INST-0106 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
CMP-0017 | Cmp | Reciprocating Compressor | Offsites | 490000 | 5 | 4 | 5 | 5
INST-0048 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
ELEC-0033 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
PMP-0078 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
PMP-0039 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
VLV-0112 | Vlv | Control Valve | Unit-200 | 13500 | 3 | 2 | 3 | 2
INST-0117 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
VLV-0063 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
ELEC-0039 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
ELEC-0055 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
INST-0039 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
VLV-0104 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
PMP-0026 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
ELEC-0085 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
VSL-0023 | Vsl | Pressure Vessel | Unit-100 | 290000 | 5 | 5 | 5 | 5
INST-0029 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0177 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
INST-0141 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
HX-0005 | Hx | Heat Exchanger | Offsites | 195000 | 4 | 3 | 5 | 4
INST-0126 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
TNK-0019 | Tnk | Storage Tank | Tank-Farm | 390000 | 4 | 5 | 3 | 4
INST-0175 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0033 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
VLV-0029 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
INST-0119 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
VLV-0018 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
VLV-0080 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
VLV-0033 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
VLV-0076 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
VLV-0096 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
PMP-0052 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
INST-0155 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
VSL-0022 | Vsl | Pressure Vessel | Offsites | 290000 | 5 | 5 | 5 | 5
PPL-0014 | Ppl | Piping/Pipeline Segment | Unit-300 | 88000 | 4 | 4 | 3 | 3
INST-0124 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
HX-0032 | Hx | Heat Exchanger | Tank-Farm | 195000 | 4 | 3 | 5 | 4
INST-0013 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
VSL-0027 | Vsl | Pressure Vessel | Unit-200 | 290000 | 5 | 5 | 5 | 5
INST-0115 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
ELEC-0043 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
VLV-0065 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
ELEC-0057 | Elec | Electrical Equipment | Unit-100 | 24000 | 3 | 1 | 3 | 3
CMP-0001 | Cmp | Reciprocating Compressor | Unit-200 | 490000 | 5 | 4 | 5 | 5
VLV-0050 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
VLV-0061 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
PPL-0016 | Ppl | Piping/Pipeline Segment | Offsites | 88000 | 4 | 4 | 3 | 3
PMP-0074 | Pmp | Centrifugal Pump | Flare-System | 48000 | 3 | 2 | 4 | 3
VLV-0114 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
VSL-0012 | Vsl | Pressure Vessel | Utilities | 290000 | 5 | 5 | 5 | 5
ELEC-0026 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
INST-0010 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
PPL-0025 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
INST-0169 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
INST-0146 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
HX-0021 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
INST-0073 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
CMP-0015 | Cmp | Reciprocating Compressor | Tank-Farm | 490000 | 5 | 4 | 5 | 5
ELEC-0019 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
VLV-0043 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
INST-0167 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
ELEC-0036 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
TNK-0009 | Tnk | Storage Tank | Unit-200 | 390000 | 4 | 5 | 3 | 4
ELEC-0077 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
ELEC-0007 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
VLV-0119 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
INST-0083 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
VSL-0009 | Vsl | Pressure Vessel | Unit-100 | 290000 | 5 | 5 | 5 | 5
PPL-0045 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
HX-0029 | Hx | Heat Exchanger | Unit-200 | 195000 | 4 | 3 | 5 | 4
PMP-0061 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
PMP-0019 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
ELEC-0035 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
VSL-0001 | Vsl | Pressure Vessel | Tank-Farm | 290000 | 5 | 5 | 5 | 5
VSL-0020 | Vsl | Pressure Vessel | Offsites | 290000 | 5 | 5 | 5 | 5
INST-0112 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
INST-0065 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
PMP-0037 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
HX-0018 | Hx | Heat Exchanger | Unit-200 | 195000 | 4 | 3 | 5 | 4
PPL-0003 | Ppl | Piping/Pipeline Segment | Utilities | 88000 | 4 | 4 | 3 | 3
VSL-0028 | Vsl | Pressure Vessel | Flare-System | 290000 | 5 | 5 | 5 | 5
HX-0025 | Hx | Heat Exchanger | Unit-200 | 195000 | 4 | 3 | 5 | 4
VLV-0098 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
VLV-0038 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
INST-0162 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PMP-0067 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
VLV-0060 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
TWR-0011 | Twr | Distillation Tower | Unit-100 | 980000 | 5 | 5 | 5 | 5
INST-0044 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
ELEC-0076 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
TNK-0018 | Tnk | Storage Tank | Tank-Farm | 390000 | 4 | 5 | 3 | 4
VLV-0053 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
INST-0043 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
PMP-0014 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
INST-0092 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
HX-0016 | Hx | Heat Exchanger | Flare-System | 195000 | 4 | 3 | 5 | 4
PMP-0046 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
HX-0031 | Hx | Heat Exchanger | Unit-300 | 195000 | 4 | 3 | 5 | 4
INST-0005 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
PMP-0063 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
INST-0172 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
ELEC-0004 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
INST-0066 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
ELEC-0048 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
CMP-0002 | Cmp | Reciprocating Compressor | Utilities | 490000 | 5 | 4 | 5 | 5
HX-0015 | Hx | Heat Exchanger | Utilities | 195000 | 4 | 3 | 5 | 4
VLV-0004 | Vlv | Control Valve | Unit-200 | 13500 | 3 | 2 | 3 | 2
CMP-0010 | Cmp | Reciprocating Compressor | Flare-System | 490000 | 5 | 4 | 5 | 5
VLV-0069 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
VLV-0001 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
INST-0076 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
HX-0013 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
INST-0095 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
INST-0135 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
INST-0027 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0051 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
INST-0075 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
INST-0118 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
VSL-0021 | Vsl | Pressure Vessel | Flare-System | 290000 | 5 | 5 | 5 | 5
INST-0056 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0001 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0058 | Vlv | Control Valve | Unit-200 | 13500 | 3 | 2 | 3 | 2
TNK-0008 | Tnk | Storage Tank | Offsites | 390000 | 4 | 5 | 3 | 4
INST-0128 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PMP-0060 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
PPL-0022 | Ppl | Piping/Pipeline Segment | Unit-200 | 88000 | 4 | 4 | 3 | 3
INST-0151 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
PMP-0032 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
INST-0161 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
TNK-0013 | Tnk | Storage Tank | Flare-System | 390000 | 4 | 5 | 3 | 4
INST-0012 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
INST-0031 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
VLV-0064 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
VLV-0068 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
ELEC-0082 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
INST-0087 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
INST-0019 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0079 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
ELEC-0006 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
VLV-0066 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
VLV-0034 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
ELEC-0068 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
VLV-0088 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
ELEC-0067 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
INST-0032 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0009 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
INST-0145 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
PPL-0015 | Ppl | Piping/Pipeline Segment | Unit-300 | 88000 | 4 | 4 | 3 | 3
INST-0049 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
ELEC-0025 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
INST-0079 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
ELEC-0080 | Elec | Electrical Equipment | Tank-Farm | 24000 | 3 | 1 | 3 | 3
VLV-0120 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
VLV-0108 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
VSL-0011 | Vsl | Pressure Vessel | Unit-100 | 290000 | 5 | 5 | 5 | 5
PPL-0043 | Ppl | Piping/Pipeline Segment | Tank-Farm | 88000 | 4 | 4 | 3 | 3
INST-0088 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
ELEC-0029 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
INST-0006 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
INST-0057 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
INST-0105 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0163 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
ELEC-0014 | Elec | Electrical Equipment | Tank-Farm | 24000 | 3 | 1 | 3 | 3
INST-0098 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
VSL-0014 | Vsl | Pressure Vessel | Unit-100 | 290000 | 5 | 5 | 5 | 5
HX-0009 | Hx | Heat Exchanger | Utilities | 195000 | 4 | 3 | 5 | 4
INST-0025 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
HX-0010 | Hx | Heat Exchanger | Unit-300 | 195000 | 4 | 3 | 5 | 4
VLV-0082 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
PMP-0013 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
INST-0021 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PMP-0050 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
ELEC-0061 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
INST-0180 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
INST-0149 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
HX-0028 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
ELEC-0023 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
INST-0103 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
VLV-0111 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
PMP-0001 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
INST-0037 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
PMP-0021 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
PMP-0033 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
VLV-0106 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
INST-0003 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
VSL-0013 | Vsl | Pressure Vessel | Unit-300 | 290000 | 5 | 5 | 5 | 5
PMP-0038 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
PMP-0020 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
PMP-0062 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
INST-0138 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
ELEC-0017 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
PMP-0049 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
VSL-0006 | Vsl | Pressure Vessel | Unit-300 | 290000 | 5 | 5 | 5 | 5
PPL-0037 | Ppl | Piping/Pipeline Segment | Tank-Farm | 88000 | 4 | 4 | 3 | 3
VLV-0023 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
VLV-0073 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
INST-0069 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PMP-0034 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
PMP-0004 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
VSL-0003 | Vsl | Pressure Vessel | Tank-Farm | 290000 | 5 | 5 | 5 | 5
PMP-0023 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
PMP-0045 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
INST-0131 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
VLV-0011 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
INST-0122 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
INST-0034 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0042 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
INST-0035 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
ELEC-0063 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
HX-0023 | Hx | Heat Exchanger | Unit-300 | 195000 | 4 | 3 | 5 | 4
INST-0152 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PPL-0039 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
VLV-0116 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
INST-0042 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
TWR-0006 | Twr | Distillation Tower | Flare-System | 980000 | 5 | 5 | 5 | 5
ELEC-0078 | Elec | Electrical Equipment | Unit-100 | 24000 | 3 | 1 | 3 | 3
INST-0148 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
VLV-0055 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
VLV-0025 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
HX-0001 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
INST-0054 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0083 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
INST-0089 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
PPL-0004 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
TNK-0002 | Tnk | Storage Tank | Unit-300 | 390000 | 4 | 5 | 3 | 4
HX-0035 | Hx | Heat Exchanger | Flare-System | 195000 | 4 | 3 | 5 | 4
INST-0160 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
ELEC-0009 | Elec | Electrical Equipment | Utilities | 24000 | 3 | 1 | 3 | 3
PMP-0080 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
INST-0143 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0084 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
TNK-0015 | Tnk | Storage Tank | Unit-300 | 390000 | 4 | 5 | 3 | 4
PPL-0026 | Ppl | Piping/Pipeline Segment | Flare-System | 88000 | 4 | 4 | 3 | 3
ELEC-0030 | Elec | Electrical Equipment | Flare-System | 24000 | 3 | 1 | 3 | 3
PMP-0065 | Pmp | Centrifugal Pump | Flare-System | 48000 | 3 | 2 | 4 | 3
TNK-0012 | Tnk | Storage Tank | Flare-System | 390000 | 4 | 5 | 3 | 4
HX-0004 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
HX-0024 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
PMP-0044 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
PPL-0013 | Ppl | Piping/Pipeline Segment | Unit-300 | 88000 | 4 | 4 | 3 | 3
INST-0015 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
VLV-0015 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
PMP-0051 | Pmp | Centrifugal Pump | Flare-System | 48000 | 3 | 2 | 4 | 3
VSL-0004 | Vsl | Pressure Vessel | Offsites | 290000 | 5 | 5 | 5 | 5
INST-0158 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PPL-0042 | Ppl | Piping/Pipeline Segment | Offsites | 88000 | 4 | 4 | 3 | 3
INST-0052 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
INST-0086 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
TNK-0004 | Tnk | Storage Tank | Tank-Farm | 390000 | 4 | 5 | 3 | 4
PPL-0040 | Ppl | Piping/Pipeline Segment | Unit-200 | 88000 | 4 | 4 | 3 | 3
PPL-0002 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
ELEC-0079 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
INST-0127 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
HX-0030 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
PMP-0064 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
INST-0133 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
CMP-0013 | Cmp | Reciprocating Compressor | Flare-System | 490000 | 5 | 4 | 5 | 5
PMP-0066 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
PMP-0059 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
INST-0090 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
PMP-0018 | Pmp | Centrifugal Pump | Unit-200 | 48000 | 3 | 2 | 4 | 3
CMP-0004 | Cmp | Reciprocating Compressor | Unit-200 | 490000 | 5 | 4 | 5 | 5
INST-0132 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
INST-0171 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
CMP-0012 | Cmp | Reciprocating Compressor | Unit-100 | 490000 | 5 | 4 | 5 | 5
ELEC-0002 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
VLV-0016 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
VLV-0090 | Vlv | Control Valve | Flare-System | 13500 | 3 | 2 | 3 | 2
PMP-0042 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
VLV-0030 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
PMP-0071 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
INST-0061 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
PMP-0054 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
VLV-0078 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
CMP-0005 | Cmp | Reciprocating Compressor | Flare-System | 490000 | 5 | 4 | 5 | 5
PPL-0030 | Ppl | Piping/Pipeline Segment | Tank-Farm | 88000 | 4 | 4 | 3 | 3
VLV-0027 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
INST-0134 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
HX-0034 | Hx | Heat Exchanger | Flare-System | 195000 | 4 | 3 | 5 | 4
VLV-0059 | Vlv | Control Valve | Unit-100 | 13500 | 3 | 2 | 3 | 2
PMP-0009 | Pmp | Centrifugal Pump | Unit-300 | 48000 | 3 | 2 | 4 | 3
INST-0173 | Inst | Instrument/Analyser | Offsites | 4800 | 2 | 1 | 3 | 2
ELEC-0041 | Elec | Electrical Equipment | Offsites | 24000 | 3 | 1 | 3 | 3
INST-0060 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
ELEC-0071 | Elec | Electrical Equipment | Unit-100 | 24000 | 3 | 1 | 3 | 3
ELEC-0081 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
PPL-0023 | Ppl | Piping/Pipeline Segment | Utilities | 88000 | 4 | 4 | 3 | 3
PPL-0031 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
INST-0137 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
TWR-0012 | Twr | Distillation Tower | Utilities | 980000 | 5 | 5 | 5 | 5
INST-0164 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
VLV-0115 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
INST-0055 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
INST-0011 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
VLV-0107 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
TWR-0007 | Twr | Distillation Tower | Flare-System | 980000 | 5 | 5 | 5 | 5
INST-0116 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
ELEC-0015 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
PPL-0034 | Ppl | Piping/Pipeline Segment | Unit-100 | 88000 | 4 | 4 | 3 | 3
INST-0004 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
INST-0024 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
VSL-0010 | Vsl | Pressure Vessel | Utilities | 290000 | 5 | 5 | 5 | 5
VLV-0032 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
TWR-0005 | Twr | Distillation Tower | Tank-Farm | 980000 | 5 | 5 | 5 | 5
ELEC-0060 | Elec | Electrical Equipment | Tank-Farm | 24000 | 3 | 1 | 3 | 3
VLV-0062 | Vlv | Control Valve | Unit-300 | 13500 | 3 | 2 | 3 | 2
CMP-0007 | Cmp | Reciprocating Compressor | Flare-System | 490000 | 5 | 4 | 5 | 5
HX-0014 | Hx | Heat Exchanger | Unit-100 | 195000 | 4 | 3 | 5 | 4
INST-0038 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
PMP-0010 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
INST-0129 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
ELEC-0053 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
TWR-0009 | Twr | Distillation Tower | Tank-Farm | 980000 | 5 | 5 | 5 | 5
INST-0020 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PPL-0018 | Ppl | Piping/Pipeline Segment | Unit-200 | 88000 | 4 | 4 | 3 | 3
TNK-0020 | Tnk | Storage Tank | Flare-System | 390000 | 4 | 5 | 3 | 4
VLV-0041 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
PPL-0020 | Ppl | Piping/Pipeline Segment | Flare-System | 88000 | 4 | 4 | 3 | 3
VSL-0018 | Vsl | Pressure Vessel | Offsites | 290000 | 5 | 5 | 5 | 5
VLV-0044 | Vlv | Control Valve | Offsites | 13500 | 3 | 2 | 3 | 2
PPL-0001 | Ppl | Piping/Pipeline Segment | Utilities | 88000 | 4 | 4 | 3 | 3
VLV-0067 | Vlv | Control Valve | Tank-Farm | 13500 | 3 | 2 | 3 | 2
INST-0018 | Inst | Instrument/Analyser | Unit-200 | 4800 | 2 | 1 | 3 | 2
INST-0053 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
ELEC-0022 | Elec | Electrical Equipment | Unit-300 | 24000 | 3 | 1 | 3 | 3
INST-0179 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
INST-0023 | Inst | Instrument/Analyser | Unit-100 | 4800 | 2 | 1 | 3 | 2
PPL-0044 | Ppl | Piping/Pipeline Segment | Unit-300 | 88000 | 4 | 4 | 3 | 3
ELEC-0065 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
PMP-0058 | Pmp | Centrifugal Pump | Unit-100 | 48000 | 3 | 2 | 4 | 3
ELEC-0074 | Elec | Electrical Equipment | Tank-Farm | 24000 | 3 | 1 | 3 | 3
PMP-0027 | Pmp | Centrifugal Pump | Flare-System | 48000 | 3 | 2 | 4 | 3
PPL-0008 | Ppl | Piping/Pipeline Segment | Unit-300 | 88000 | 4 | 4 | 3 | 3
TNK-0001 | Tnk | Storage Tank | Unit-200 | 390000 | 4 | 5 | 3 | 4
VLV-0048 | Vlv | Control Valve | Unit-200 | 13500 | 3 | 2 | 3 | 2
INST-0074 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
INST-0144 | Inst | Instrument/Analyser | Utilities | 4800 | 2 | 1 | 3 | 2
PMP-0005 | Pmp | Centrifugal Pump | Tank-Farm | 48000 | 3 | 2 | 4 | 3
INST-0091 | Inst | Instrument/Analyser | Tank-Farm | 4800 | 2 | 1 | 3 | 2
VLV-0002 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2
INST-0068 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
TNK-0005 | Tnk | Storage Tank | Flare-System | 390000 | 4 | 5 | 3 | 4
INST-0084 | Inst | Instrument/Analyser | Unit-300 | 4800 | 2 | 1 | 3 | 2
CMP-0008 | Cmp | Reciprocating Compressor | Unit-100 | 490000 | 5 | 4 | 5 | 5
PMP-0053 | Pmp | Centrifugal Pump | Utilities | 48000 | 3 | 2 | 4 | 3
PMP-0041 | Pmp | Centrifugal Pump | Offsites | 48000 | 3 | 2 | 4 | 3
PMP-0047 | Pmp | Centrifugal Pump | Flare-System | 48000 | 3 | 2 | 4 | 3
INST-0030 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
ELEC-0032 | Elec | Electrical Equipment | Unit-200 | 24000 | 3 | 1 | 3 | 3
CMP-0014 | Cmp | Reciprocating Compressor | Unit-100 | 490000 | 5 | 4 | 5 | 5
VSL-0025 | Vsl | Pressure Vessel | Unit-200 | 290000 | 5 | 5 | 5 | 5
INST-0040 | Inst | Instrument/Analyser | Flare-System | 4800 | 2 | 1 | 3 | 2
VLV-0054 | Vlv | Control Valve | Utilities | 13500 | 3 | 2 | 3 | 2

## Dim_TaskType
task_type_id | task_type_name
1 | Calibration
2 | Cleaning
3 | Inspection
4 | Overhaul
5 | Repair
6 | Replacement
7 | Testing

## Dim_Priority
priority_id | priority_name | priority_weight
1 | Critical | 4
2 | High | 3
3 | Medium | 2
4 | Low | 1

## Dim_RiskLevel
risk_level_id | risk_level_name | sort_order
1 | LOW | 1
2 | MEDIUM | 2
3 | HIGH | 3
4 | CRITICAL | 4

## FactWorkOrderDecision
wo_id | description | asset_tag | task_type_id | priority_id | risk_level_id | predecessor_wo_id | mandatory | age_days | estimated_cost_usd | mech_hours | elec_hours | inst_hours | civil_hours | total_craft_hours | duration_days | fitted_beta | fitted_eta | failure_prob | rul_days | consequence_score | likelihood_tier | consequence_tier | risk_score | deferred_cost_usd | net_value_usd | selected | decision
WO-00001 | Overhaul – Electrical Equipment ELEC-0024 | ELEC-0024 | 4 | 3 | 3 |  | FALSE | 2961 | 432608.5 | 239.5 | 22.7 | 8.5 | 6.5 | 277.2 | 35 | 2 | 1460 | 0.65923 | 1460 | 2.5 | 5 | 2 | 10 | 5933.05 | -426675.45 | FALSE | DEFER
WO-00002 | Replacement – Control Valve VLV-0026 | VLV-0026 | 6 | 4 | 3 |  | FALSE | 4375 | 113098 | 40.6 | 11.4 | 20 | 3.3 | 75.3 | 9 | 1.5 | 1095 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | 3431.19 | -109666.81 | FALSE | DEFER
WO-00003 | Inspection – Piping/Pipeline Segment PPL-0012 | PPL-0012 | 3 | 3 | 2 |  | FALSE | 1370 | 5185.61 | 9.5 | 1.6 | 4.4 | 0.4 | 15.9 | 2 | 2 | 3285 | 0.099696 | 3614.7482 | 3.65 | 2 | 4 | 8 | 4803.35 | -382.26 | FALSE | DEFER
WO-00004 | Cleaning – Pressure Vessel VSL-0019 | VSL-0019 | 2 | 3 | 4 |  | FALSE | 4641 | 15844.97 | 5.4 | 0.4 | 1.1 | 2.5 | 9.4 | 1 | 2.8 | 3650 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | 80556.21 | 64711.24 | TRUE | INCLUDE
WO-00005 | Repair – Instrument/Analyser INST-0114 | INST-0114 | 5 | 4 | 3 |  | FALSE | 2613 | 73788.26 | 17.4 | 28.4 | 3.2 | 5.3 | 54.3 | 7 | 1.8 | 730 | 0.92825 | 730 | 2 | 5 | 2 | 10 | 1336.68 | -72451.58 | FALSE | DEFER
WO-00006 | Inspection – Instrument/Analyser INST-0142 | INST-0142 | 3 | 2 | 3 |  | FALSE | 4941 | 734.91 | 2.2 | 1 | 4.2 | 0.1 | 7.5 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 705.09 | TRUE | INCLUDE
WO-00007 | Cleaning – Instrument/Analyser INST-0121 | INST-0121 | 2 | 3 | 3 |  | FALSE | 4337 | 6623.09 | 21.5 | 1.9 | 1.5 | 9 | 33.9 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -5183.09 | FALSE | DEFER
WO-00008 | Repair – Instrument/Analyser INST-0082 | INST-0082 | 5 | 3 | 3 |  | FALSE | 1610 | 16266.45 | 14.3 | 21.1 | 2.9 | 9 | 47.3 | 6 | 1.8 | 730 | 0.84213 | 730 | 2 | 5 | 2 | 10 | 1212.67 | -15053.78 | FALSE | DEFER
WO-00009 | Testing – Instrument/Analyser INST-0007 | INST-0007 | 7 | 3 | 3 |  | FALSE | 3514 | 5051.36 | 10.8 | 18.8 | 8.9 | 1.1 | 39.6 | 5 | 1.8 | 730 | 0.96291 | 730 | 2 | 5 | 2 | 10 | 1386.59 | -3664.77 | FALSE | DEFER
WO-00010 | Testing – Instrument/Analyser INST-0111 | INST-0111 | 7 | 3 | 3 |  | FALSE | 4361 | 11298.2 | 4.1 | 13.5 | 15.8 | 0.3 | 33.7 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -9858.2 | FALSE | DEFER
WO-00011 | Replacement – Storage Tank TNK-0006 | TNK-0006 | 6 | 3 | 3 |  | FALSE | 4911 | 18665.17 | 34.6 | 5 | 15.8 | 2.5 | 57.9 | 7 | 3.5 | 5475 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | 41445.54 | 22780.37 | TRUE | INCLUDE
WO-00012 | Inspection – Control Valve VLV-0110 | VLV-0110 | 3 | 3 | 3 |  | FALSE | 813 | 7232.51 | 2.2 | 1 | 2.3 | 0.2 | 5.7 | 1 | 1.5 | 1095 | 0.37878 | 1096.3751 | 2.65 | 4 | 3 | 12 | 2032.63 | -5199.88 | FALSE | DEFER
WO-00013 | Repair – Instrument/Analyser INST-0026 | INST-0026 | 5 | 2 | 3 |  | FALSE | 3487 | 73391.62 | 35.9 | 8 | 15 | 6.2 | 65.1 | 8 | 1.8 | 730 | 0.96219 | 730 | 2 | 5 | 2 | 10 | 1385.56 | -72006.06 | FALSE | DEFER
WO-00014 | Calibration – Heat Exchanger HX-0033 | HX-0033 | 1 | 3 | 3 |  | FALSE | 1985 | 1653.01 | 1.3 | 4.9 | 11 | 0.2 | 17.4 | 2 | 2 | 2190 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | 32878.24 | 31225.23 | TRUE | INCLUDE
WO-00015 | Inspection – Control Valve VLV-0089 | VLV-0089 | 3 | 3 | 3 |  | FALSE | 3915 | 6359.44 | 8.4 | 1.5 | 1.1 | 0.3 | 11.3 | 1 | 1.5 | 1095 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | 3326.16 | -3033.28 | FALSE | DEFER
WO-00016 | Cleaning – Electrical Equipment ELEC-0008 | ELEC-0008 | 2 | 1 | 3 |  | FALSE | 2985 | 23061.33 | 13 | 1.8 | 0.3 | 5 | 20.1 | 3 | 2 | 1460 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | 5958.15 | -17103.18 | FALSE | DEFER
WO-00017 | Calibration – Instrument/Analyser INST-0106 | INST-0106 | 1 | 1 | 3 |  | FALSE | 3603 | 621.83 | 0.5 | 8.2 | 12.6 | 0 | 21.3 | 3 | 1.8 | 730 | 0.96519 | 730 | 2 | 5 | 2 | 10 | 1389.87 | 768.04 | TRUE | INCLUDE
WO-00018 | Overhaul – Reciprocating Compressor CMP-0017 | CMP-0017 | 4 | 1 | 4 |  | FALSE | 4834 | 193398.98 | 76.1 | 33.8 | 17.6 | 15.8 | 143.3 | 18 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 155726.02 | TRUE | INCLUDE
WO-00019 | Inspection – Instrument/Analyser INST-0048 | INST-0048 | 3 | 4 | 3 |  | FALSE | 733 | 1621.98 | 3.9 | 0.1 | 2.2 | 0.9 | 7.1 | 1 | 1.8 | 730 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | 949.8 | -672.18 | FALSE | DEFER
WO-00020 | Replacement – Electrical Equipment ELEC-0033 | ELEC-0033 | 6 | 2 | 2 | WO-00015 | FALSE | 613 | 71220.87 | 37.5 | 16.9 | 8.7 | 3.7 | 66.8 | 8 | 2 | 1460 | 0.23847 | 1602.4435 | 2.5 | 3 | 2 | 6 | 2146.27 | -69074.6 | FALSE | DEFER
WO-00021 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | 3 | 1 | 3 |  | FALSE | 4241 | 2928.69 | 9 | 1.8 | 1.4 | 0.5 | 12.7 | 2 | 2.5 | 1825 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | 18327.69 | 15399 | TRUE | INCLUDE
WO-00022 | Overhaul – Centrifugal Pump PMP-0039 | PMP-0039 | 4 | 2 | 3 |  | FALSE | 3271 | 339510.92 | 44.1 | 43.4 | 48.9 | 17.1 | 153.5 | 19 | 2.5 | 1825 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | 15725.17 | -323785.75 | FALSE | DEFER
WO-00023 | Cleaning – Control Valve VLV-0112 | VLV-0112 | 2 | 3 | 3 |  | FALSE | 4321 | 9022.56 | 7.6 | 1.2 | 0.1 | 8.6 | 17.5 | 2 | 1.5 | 1095 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | 3419.43 | -5603.13 | FALSE | DEFER
WO-00024 | Overhaul – Instrument/Analyser INST-0117 | INST-0117 | 4 | 3 | 3 |  | FALSE | 1837 | 206394.95 | 233.9 | 15.3 | 14.4 | 7.3 | 270.9 | 34 | 1.8 | 730 | 0.86878 | 730 | 2 | 5 | 2 | 10 | 1251.04 | -205143.91 | TRUE | INCLUDE
WO-00025 | Testing – Control Valve VLV-0063 | VLV-0063 | 7 | 3 | 3 |  | FALSE | 871 | 3914.39 | 18.3 | 9.6 | 17 | 0.1 | 45 | 6 | 1.5 | 1095 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | 2078.14 | -1836.25 | FALSE | DEFER
WO-00026 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | 2 | 3 | 2 |  | FALSE | 524 | 13871.67 | 9.7 | 1.7 | 1.9 | 5.7 | 19 | 2 | 2 | 1460 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | 1934.16 | -11937.51 | FALSE | DEFER
WO-00027 | Calibration – Electrical Equipment ELEC-0055 | ELEC-0055 | 1 | 2 | 2 |  | FALSE | 2480 | 876.17 | 1.7 | 4.2 | 16.4 | 0.1 | 22.4 | 3 | 2 | 1460 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | 5383.85 | 4507.68 | TRUE | INCLUDE
WO-00028 | Cleaning – Instrument/Analyser INST-0039 | INST-0039 | 2 | 2 | 3 |  | FALSE | 3563 | 13598.13 | 24.4 | 2 | 0.2 | 4.2 | 30.8 | 4 | 1.8 | 730 | 0.96419 | 730 | 2 | 5 | 2 | 10 | 1388.43 | -12209.7 | FALSE | DEFER
WO-00029 | Overhaul – Control Valve VLV-0104 | VLV-0104 | 4 | 3 | 3 |  | FALSE | 2746 | 303937.2 | 211.2 | 40.4 | 8.8 | 13.1 | 273.5 | 34 | 1.5 | 1095 | 0.55849 | 1095 | 2.65 | 4 | 3 | 12 | 2996.99 | -300940.21 | FALSE | DEFER
WO-00030 | Overhaul – Centrifugal Pump PMP-0026 | PMP-0026 | 4 | 1 | 3 |  | FALSE | 1524 | 91427.47 | 119.5 | 25.3 | 15.9 | 19.1 | 179.8 | 22 | 2.5 | 1825 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | 7865.02 | -83562.45 | FALSE | DEFER
WO-00031 | Cleaning – Electrical Equipment ELEC-0039 | ELEC-0039 | 2 | 3 | 2 |  | FALSE | 524 | 13377.52 | 25.1 | 0.2 | 0.2 | 4.4 | 29.9 | 4 | 2 | 1460 | 0.21491 | 1691.4436 | 2.5 | 3 | 2 | 6 | 1934.16 | -11443.36 | FALSE | DEFER
WO-00032 | Replacement – Electrical Equipment ELEC-0085 | ELEC-0085 | 6 | 4 | 3 |  | FALSE | 4240 | 92766.51 | 20.8 | 3.5 | 12.3 | 8 | 44.6 | 6 | 2 | 1460 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | 7020.85 | -85745.66 | FALSE | DEFER
WO-00033 | Calibration – Pressure Vessel VSL-0023 | VSL-0023 | 1 | 3 | 4 |  | FALSE | 4948 | 1762.08 | 1.4 | 7.5 | 7.7 | 0.6 | 17.2 | 2 | 2.8 | 3650 | 0.40366 | 3650 | 5 | 4 | 5 | 20 | 87797.04 | 86034.96 | TRUE | INCLUDE
WO-00034 | Replacement – Instrument/Analyser INST-0029 | INST-0029 | 6 | 4 | 3 |  | FALSE | 3371 | 80206.91 | 33 | 11.1 | 5.8 | 7 | 56.9 | 7 | 1.8 | 730 | 0.95892 | 730 | 2 | 5 | 2 | 10 | 1380.84 | -78826.07 | FALSE | DEFER
WO-00035 | Inspection – Instrument/Analyser INST-0177 | INST-0177 | 3 | 2 | 3 |  | FALSE | 1812 | 3309.18 | 2.4 | 0.1 | 5 | 0.5 | 8 | 1 | 1.8 | 730 | 0.86611 | 730 | 2 | 5 | 2 | 10 | 1247.2 | -2061.98 | FALSE | DEFER
WO-00036 | Replacement – Instrument/Analyser INST-0141 | INST-0141 | 6 | 3 | 3 |  | FALSE | 2415 | 117701.45 | 21.1 | 15.1 | 9.7 | 1.6 | 47.5 | 6 | 1.8 | 730 | 0.9166 | 730 | 2 | 5 | 2 | 10 | 1319.9 | -116381.55 | FALSE | DEFER
WO-00037 | Inspection – Heat Exchanger HX-0005 | HX-0005 | 3 | 1 | 3 |  | FALSE | 2050 | 5600.54 | 4 | 1.5 | 4.1 | 0.7 | 10.3 | 1 | 2 | 2190 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | 33706.39 | 28105.85 | TRUE | INCLUDE
WO-00038 | Calibration – Instrument/Analyser INST-0126 | INST-0126 | 1 | 3 | 3 |  | FALSE | 798 | 2972.41 | 0.5 | 4.2 | 17 | 0.2 | 21.9 | 3 | 1.8 | 730 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | 978.78 | -1993.63 | FALSE | DEFER
WO-00039 | Calibration – Storage Tank TNK-0019 | TNK-0019 | 1 | 1 | 1 |  | FALSE | 899 | 304.05 | 1.1 | 6.6 | 8.9 | 0.9 | 17.5 | 2 | 3.5 | 5475 | 0.0041101 | 6049.2321 | 4 | 1 | 4 | 4 | 961.75 | 657.7 | TRUE | INCLUDE
WO-00040 | Replacement – Instrument/Analyser INST-0175 | INST-0175 | 6 | 1 | 3 | WO-00037 | FALSE | 2012 | 102596.9 | 17.9 | 16.8 | 5.6 | 5.4 | 45.7 | 6 | 1.8 | 730 | 0.88589 | 730 | 2 | 5 | 2 | 10 | 1275.68 | -101321.22 | FALSE | DEFER
WO-00041 | Calibration – Instrument/Analyser INST-0007 | INST-0007 | 1 | 3 | 3 |  | FALSE | 3514 | 2413.68 | 1.7 | 9.9 | 14.8 | 0.8 | 27.2 | 3 | 1.8 | 730 | 0.96291 | 730 | 2 | 5 | 2 | 10 | 1386.59 | -1027.09 | FALSE | DEFER
WO-00042 | Repair – Instrument/Analyser INST-0033 | INST-0033 | 5 | 2 | 3 |  | FALSE | 3290 | 52213.15 | 89.3 | 10.1 | 10.9 | 7.6 | 117.9 | 15 | 1.8 | 730 | 0.95645 | 730 | 2 | 5 | 2 | 10 | 1377.28 | -50835.87 | FALSE | DEFER
WO-00043 | Replacement – Control Valve VLV-0029 | VLV-0029 | 6 | 3 | 3 |  | FALSE | 1553 | 117474.92 | 30.6 | 5.3 | 10.6 | 4.6 | 51.1 | 6 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | -114969.04 | FALSE | DEFER
WO-00044 | Testing – Instrument/Analyser INST-0119 | INST-0119 | 7 | 2 | 3 |  | FALSE | 2135 | 14805.56 | 13.7 | 18 | 10.4 | 1.7 | 43.8 | 5 | 1.8 | 730 | 0.89642 | 730 | 2 | 5 | 2 | 10 | 1290.84 | -13514.72 | FALSE | DEFER
WO-00045 | Inspection – Control Valve VLV-0018 | VLV-0018 | 3 | 2 | 3 |  | FALSE | 5090 | 7802.09 | 8.9 | 0.6 | 3.7 | 0.5 | 13.7 | 2 | 1.5 | 1095 | 0.66617 | 1095 | 2.65 | 5 | 3 | 15 | 3574.81 | -4227.28 | FALSE | DEFER
WO-00046 | Replacement – Control Valve VLV-0080 | VLV-0080 | 6 | 4 | 3 |  | FALSE | 1882 | 20643.16 | 36.6 | 10 | 14.2 | 2.9 | 63.7 | 8 | 1.5 | 1095 | 0.49658 | 27.375 | 2.65 | 4 | 3 | 12 | 2664.75 | -17978.41 | FALSE | DEFER
WO-00047 | Cleaning – Control Valve VLV-0033 | VLV-0033 | 2 | 2 | 3 |  | FALSE | 2277 | 22590.42 | 6.6 | 1.2 | 1.7 | 4.6 | 14.1 | 2 | 1.5 | 1095 | 0.52725 | 1095 | 2.65 | 4 | 3 | 12 | 2829.34 | -19761.08 | FALSE | DEFER
WO-00048 | Replacement – Control Valve VLV-0076 | VLV-0076 | 6 | 1 | 3 | WO-00019 | FALSE | 1553 | 36387.38 | 31.3 | 7.9 | 9.4 | 6.8 | 55.4 | 7 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | -33881.5 | FALSE | DEFER
WO-00049 | Replacement – Control Valve VLV-0096 | VLV-0096 | 6 | 3 | 3 |  | FALSE | 4457 | 84321.48 | 17.1 | 6 | 8 | 1 | 32.1 | 4 | 1.5 | 1095 | 0.64268 | 1095 | 2.65 | 5 | 3 | 15 | 3448.8 | -80872.68 | FALSE | DEFER
WO-00050 | Inspection – Centrifugal Pump PMP-0052 | PMP-0052 | 3 | 2 | 3 |  | FALSE | 3747 | 2619.75 | 10 | 1.8 | 1.9 | 0.3 | 14 | 2 | 2.5 | 1825 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | 17151.61 | 14531.86 | TRUE | INCLUDE
WO-00051 | Repair – Instrument/Analyser INST-0155 | INST-0155 | 5 | 4 | 3 |  | FALSE | 3302 | 64606.38 | 19.6 | 7.2 | 9.5 | 8.8 | 45.1 | 6 | 1.8 | 730 | 0.95682 | 730 | 2 | 5 | 2 | 10 | 1377.82 | -63228.56 | FALSE | DEFER
WO-00052 | Inspection – Pressure Vessel VSL-0022 | VSL-0022 | 3 | 1 | 3 |  | FALSE | 3687 | 4849.8 | 3.2 | 1.4 | 4.7 | 0.5 | 9.8 | 1 | 2.8 | 3650 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | 58166.81 | 53317.01 | TRUE | INCLUDE
WO-00053 | Cleaning – Piping/Pipeline Segment PPL-0014 | PPL-0014 | 2 | 1 | 2 |  | FALSE | 1034 | 10804.4 | 23.5 | 0.7 | 1.7 | 4.2 | 30.1 | 4 | 2 | 3285 | 0.078998 | 3950.7481 | 3.65 | 2 | 4 | 8 | 3806.13 | -6998.27 | TRUE | INCLUDE
WO-00054 | Replacement – Heat Exchanger HX-0033 | HX-0033 | 6 | 1 | 3 |  | FALSE | 1985 | 9015.32 | 22.6 | 13.9 | 6.8 | 2 | 45.3 | 6 | 2 | 2190 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | 32878.24 | 23862.92 | TRUE | INCLUDE
WO-00055 | Inspection – Instrument/Analyser INST-0124 | INST-0124 | 3 | 4 | 3 |  | FALSE | 5362 | 7072.3 | 9.6 | 0.1 | 4 | 0.7 | 14.4 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -5632.3 | FALSE | DEFER
WO-00056 | Replacement – Heat Exchanger HX-0032 | HX-0032 | 6 | 1 | 3 |  | FALSE | 4495 | 37833.53 | 31.6 | 17.4 | 18.6 | 5.2 | 72.8 | 9 | 2 | 2190 | 0.50931 | 2190 | 4 | 4 | 4 | 16 | 59589.59 | 21756.06 | TRUE | INCLUDE
WO-00057 | Calibration – Instrument/Analyser INST-0048 | INST-0048 | 1 | 3 | 3 |  | FALSE | 733 | 2592.68 | 0.8 | 7.3 | 10.4 | 0.5 | 19 | 2 | 1.8 | 730 | 0.65958 | 427.2558 | 2 | 5 | 2 | 10 | 949.8 | -1642.88 | FALSE | DEFER
WO-00058 | Calibration – Instrument/Analyser INST-0013 | INST-0013 | 1 | 2 | 3 |  | FALSE | 4371 | 2937.02 | 0.9 | 4.7 | 10 | 0.1 | 15.7 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -1497.02 | FALSE | DEFER
WO-00059 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | 3 | 2 | 4 |  | FALSE | 5018 | 3766.42 | 3.3 | 0.7 | 4.2 | 0.2 | 8.4 | 1 | 2.8 | 3650 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | 89441.64 | 85675.22 | TRUE | INCLUDE
WO-00060 | Repair – Instrument/Analyser INST-0115 | INST-0115 | 5 | 2 | 3 |  | FALSE | 3707 | 46220.48 | 25.8 | 13 | 12.6 | 5.6 | 57 | 7 | 1.8 | 730 | 0.96766 | 730 | 2 | 5 | 2 | 10 | 1393.43 | -44827.05 | FALSE | DEFER
WO-00061 | Overhaul – Electrical Equipment ELEC-0043 | ELEC-0043 | 4 | 4 | 3 |  | FALSE | 4705 | 332694.02 | 93.5 | 33.7 | 10.9 | 10.7 | 148.8 | 19 | 2 | 1460 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | 7312.2 | -325381.82 | FALSE | DEFER
WO-00062 | Replacement – Control Valve VLV-0065 | VLV-0065 | 6 | 2 | 3 |  | FALSE | 5370 | 74595.34 | 29.3 | 7.7 | 22.3 | 4.1 | 63.4 | 8 | 1.5 | 1095 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | 3625.6 | -70969.74 | FALSE | DEFER
WO-00063 | Repair – Electrical Equipment ELEC-0057 | ELEC-0057 | 5 | 2 | 2 | WO-00046 | FALSE | 517 | 60183.66 | 70.7 | 5.3 | 4.4 | 6.7 | 87.1 | 11 | 2 | 1460 | 0.21302 | 1698.4436 | 2.5 | 3 | 2 | 6 | 1917.2 | -58266.46 | FALSE | DEFER
WO-00064 | Replacement – Reciprocating Compressor CMP-0001 | CMP-0001 | 6 | 2 | 4 |  | FALSE | 5148 | 94600.93 | 22.9 | 3.3 | 4.7 | 5 | 35.9 | 4 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 254524.07 | TRUE | INCLUDE
WO-00065 | Repair – Control Valve VLV-0050 | VLV-0050 | 5 | 4 | 3 |  | FALSE | 3385 | 10642.74 | 26.1 | 17.8 | 8.6 | 5.3 | 57.8 | 7 | 1.5 | 1095 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | 3189.72 | -7453.02 | FALSE | DEFER
WO-00066 | Cleaning – Control Valve VLV-0061 | VLV-0061 | 2 | 3 | 3 |  | FALSE | 4623 | 10962.89 | 27.7 | 0.1 | 1.9 | 6 | 35.7 | 4 | 1.5 | 1095 | 0.64915 | 1095 | 2.65 | 5 | 3 | 15 | 3483.48 | -7479.41 | FALSE | DEFER
WO-00067 | Testing – Piping/Pipeline Segment PPL-0016 | PPL-0016 | 7 | 1 | 2 |  | FALSE | 2099 | 7856.2 | 9.9 | 9.4 | 17.2 | 1.1 | 37.6 | 5 | 2 | 3285 | 0.14302 | 2885.7481 | 3.65 | 2 | 4 | 8 | 6890.59 | -965.61 | FALSE | DEFER
WO-00068 | Calibration – Centrifugal Pump PMP-0074 | PMP-0074 | 1 | 1 | 3 |  | FALSE | 2694 | 2003.44 | 0.8 | 2 | 11.1 | 0 | 13.9 | 2 | 2.5 | 1825 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | 13573.13 | 11569.69 | TRUE | INCLUDE
WO-00069 | Overhaul – Control Valve VLV-0114 | VLV-0114 | 4 | 4 | 3 |  | FALSE | 4955 | 62923.13 | 95.1 | 35.5 | 21 | 24 | 175.6 | 22 | 1.5 | 1095 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | 3549.3 | -59373.83 | FALSE | DEFER
WO-00070 | Cleaning – Pressure Vessel VSL-0012 | VSL-0012 | 2 | 2 | 4 | WO-00029 | FALSE | 4582 | 24206.73 | 24.8 | 0.6 | 1.5 | 3.1 | 30 | 4 | 2.8 | 3650 | 0.36396 | 334.4951 | 5 | 4 | 5 | 20 | 79161.63 | 54954.9 | FALSE | DEFER
WO-00071 | Overhaul – Electrical Equipment ELEC-0026 | ELEC-0026 | 4 | 2 | 3 |  | FALSE | 2569 | 24843.17 | 94.8 | 48.1 | 21.3 | 7.6 | 171.8 | 21 | 2 | 1460 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | 5492.41 | -19350.76 | FALSE | DEFER
WO-00072 | Overhaul – Instrument/Analyser INST-0010 | INST-0010 | 4 | 3 | 3 |  | FALSE | 1249 | 507949.81 | 191.6 | 26.3 | 16.8 | 4.9 | 239.6 | 30 | 1.8 | 730 | 0.786 | 730 | 2 | 5 | 2 | 10 | 1131.85 | -506817.96 | FALSE | DEFER
WO-00073 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | 1 | 2 | 3 | WO-00039 | FALSE | 2825 | 2243.11 | 0.8 | 6.8 | 11 | 0.6 | 19.2 | 2 | 2 | 3285 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | 8869.41 | 6626.3 | TRUE | INCLUDE
WO-00074 | Calibration – Instrument/Analyser INST-0169 | INST-0169 | 1 | 3 | 3 |  | FALSE | 1566 | 1621.58 | 1.9 | 5.4 | 4.3 | 0.2 | 11.8 | 1 | 1.8 | 730 | 0.83629 | 730 | 2 | 5 | 2 | 10 | 1204.25 | -417.33 | FALSE | DEFER
WO-00075 | Cleaning – Instrument/Analyser INST-0146 | INST-0146 | 2 | 3 | 3 |  | FALSE | 1892 | 14257.23 | 21.1 | 0.5 | 1.3 | 7.6 | 30.5 | 4 | 1.8 | 730 | 0.87445 | 730 | 2 | 5 | 2 | 10 | 1259.2 | -12998.03 | FALSE | DEFER
WO-00076 | Overhaul – Instrument/Analyser INST-0177 | INST-0177 | 4 | 2 | 3 |  | FALSE | 1812 | 119671 | 122.8 | 41 | 46.2 | 15.9 | 225.9 | 28 | 1.8 | 730 | 0.86611 | 730 | 2 | 5 | 2 | 10 | 1247.2 | -118423.8 | FALSE | DEFER
WO-00077 | Calibration – Heat Exchanger HX-0021 | HX-0021 | 1 | 1 | 3 |  | TRUE | 4587 | 2272.41 | 0.7 | 8.6 | 5.2 | 0 | 14.5 | 2 | 2 | 2190 | 0.51614 | 2190 | 4 | 4 | 4 | 16 | 60387.91 | 58115.5 | TRUE | INCLUDE
WO-00078 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | 3 | 1 | 4 |  | FALSE | 5018 | 7104.07 | 5.4 | 0.5 | 2.7 | 0.4 | 9 | 1 | 2.8 | 3650 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | 89441.64 | 82337.57 | TRUE | INCLUDE
WO-00079 | Inspection – Instrument/Analyser INST-0073 | INST-0073 | 3 | 4 | 3 | WO-00052 | FALSE | 4224 | 5453.77 | 3.1 | 1.6 | 1.8 | 0.7 | 7.2 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -4013.77 | FALSE | DEFER
WO-00080 | Inspection – Reciprocating Compressor CMP-0015 | CMP-0015 | 3 | 1 | 4 |  | TRUE | 1148 | 1241.92 | 9.6 | 0.9 | 3.5 | 0 | 14 | 2 | 3 | 1460 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | 162580.25 | 161338.33 | TRUE | INCLUDE
WO-00081 | Overhaul – Centrifugal Pump PMP-0074 | PMP-0074 | 4 | 1 | 3 |  | TRUE | 2694 | 533437.71 | 94.3 | 40.6 | 35.8 | 6.3 | 177 | 22 | 2.5 | 1825 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | 13573.13 | -519864.58 | TRUE | INCLUDE
WO-00082 | Replacement – Heat Exchanger HX-0005 | HX-0005 | 6 | 2 | 3 |  | FALSE | 2050 | 55890.67 | 41 | 9.8 | 8.9 | 7.3 | 67 | 8 | 2 | 2190 | 0.28809 | 1273.1654 | 4 | 3 | 4 | 12 | 33706.39 | -22184.28 | FALSE | DEFER
WO-00083 | Overhaul – Electrical Equipment ELEC-0019 | ELEC-0019 | 4 | 2 | 2 |  | FALSE | 1908 | 339335.46 | 84.4 | 36.6 | 24.3 | 11.3 | 156.6 | 20 | 2 | 1460 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | 4601.34 | -334734.12 | FALSE | DEFER
WO-00084 | Cleaning – Instrument/Analyser INST-0117 | INST-0117 | 2 | 3 | 3 |  | FALSE | 1837 | 15463.95 | 12.2 | 1.7 | 1.7 | 2.9 | 18.5 | 2 | 1.8 | 730 | 0.86878 | 730 | 2 | 5 | 2 | 10 | 1251.04 | -14212.91 | FALSE | DEFER
WO-00085 | Replacement – Control Valve VLV-0043 | VLV-0043 | 6 | 3 | 3 |  | FALSE | 1100 | 119967.21 | 19.7 | 7 | 12.8 | 3.4 | 42.9 | 5 | 1.5 | 1095 | 0.41764 | 809.375 | 2.65 | 4 | 3 | 12 | 2241.14 | -117726.07 | FALSE | DEFER
WO-00086 | Overhaul – Instrument/Analyser INST-0167 | INST-0167 | 4 | 2 | 3 |  | FALSE | 3128 | 144214.12 | 141.3 | 45.3 | 41.3 | 14 | 241.9 | 30 | 1.8 | 730 | 0.95101 | 730 | 2 | 5 | 2 | 10 | 1369.46 | -142844.66 | FALSE | DEFER
WO-00087 | Inspection – Instrument/Analyser INST-0141 | INST-0141 | 3 | 3 | 3 |  | FALSE | 2415 | 7100.03 | 7.7 | 1.1 | 4.5 | 0.1 | 13.4 | 2 | 1.8 | 730 | 0.9166 | 730 | 2 | 5 | 2 | 10 | 1319.9 | -5780.13 | FALSE | DEFER
WO-00088 | Replacement – Electrical Equipment ELEC-0036 | ELEC-0036 | 6 | 4 | 2 |  | FALSE | 607 | 18866.41 | 32.2 | 9 | 22.8 | 3.9 | 67.9 | 8 | 2 | 1460 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | 2132.17 | -16734.24 | FALSE | DEFER
WO-00089 | Calibration – Storage Tank TNK-0009 | TNK-0009 | 1 | 1 | 3 |  | FALSE | 5278 | 2070.19 | 1.8 | 5.3 | 10.2 | 0.2 | 17.5 | 2 | 3.5 | 5475 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | 48441.95 | 46371.76 | TRUE | INCLUDE
WO-00090 | Repair – Electrical Equipment ELEC-0077 | ELEC-0077 | 5 | 2 | 3 |  | FALSE | 4638 | 39001.81 | 39.4 | 9.6 | 10.7 | 7.4 | 67.1 | 8 | 2 | 1460 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | 7273.03 | -31728.78 | FALSE | DEFER
WO-00091 | Calibration – Heat Exchanger HX-0033 | HX-0033 | 1 | 1 | 3 |  | TRUE | 1985 | 1963.41 | 1.6 | 4 | 14.1 | 0.2 | 19.9 | 2 | 2 | 2190 | 0.28101 | 1338.1654 | 4 | 3 | 4 | 12 | 32878.24 | 30914.83 | TRUE | INCLUDE
WO-00092 | Calibration – Electrical Equipment ELEC-0007 | ELEC-0007 | 1 | 4 | 3 | WO-00053 | FALSE | 5246 | 1968.67 | 0.4 | 8.9 | 4.9 | 0.6 | 14.8 | 2 | 2 | 1460 | 0.84418 | 1460 | 2.5 | 5 | 2 | 10 | 7597.65 | 5628.98 | TRUE | INCLUDE
WO-00093 | Cleaning – Control Valve VLV-0112 | VLV-0112 | 2 | 2 | 3 |  | FALSE | 4321 | 20216.12 | 18.3 | 1.6 | 1.3 | 7.5 | 28.7 | 4 | 1.5 | 1095 | 0.63721 | 1095 | 2.65 | 5 | 3 | 15 | 3419.43 | -16796.69 | FALSE | DEFER
WO-00094 | Calibration – Control Valve VLV-0119 | VLV-0119 | 1 | 2 | 3 |  | FALSE | 2602 | 866.15 | 2 | 3.8 | 7.8 | 0.9 | 14.5 | 2 | 1.5 | 1095 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | 2948.24 | 2082.09 | TRUE | INCLUDE
WO-00095 | Replacement – Instrument/Analyser INST-0111 | INST-0111 | 6 | 2 | 3 |  | FALSE | 4361 | 87183.62 | 16.3 | 4.9 | 13.7 | 3.2 | 38.1 | 5 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -85743.62 | FALSE | DEFER
WO-00096 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | 3 | 1 | 3 |  | TRUE | 3623 | 3341.33 | 4.5 | 0.1 | 3.5 | 0.6 | 8.7 | 1 | 1.8 | 730 | 0.96568 | 730 | 2 | 5 | 2 | 10 | 1390.58 | -1950.75 | TRUE | INCLUDE
WO-00097 | Replacement – Pressure Vessel VSL-0009 | VSL-0009 | 6 | 3 | 3 |  | FALSE | 3370 | 105372.64 | 38.3 | 9.4 | 13.3 | 2.9 | 63.9 | 8 | 2.8 | 3650 | 0.23421 | 1546.4951 | 5 | 3 | 5 | 15 | 50941.13 | -54431.51 | FALSE | DEFER
WO-00098 | Repair – Piping/Pipeline Segment PPL-0045 | PPL-0045 | 5 | 1 | 3 |  | TRUE | 4248 | 73031.8 | 28.6 | 12.1 | 4.9 | 3.8 | 49.4 | 6 | 2 | 3285 | 0.25897 | 736.7481 | 3.65 | 3 | 4 | 12 | 12477.11 | -60554.69 | TRUE | INCLUDE
WO-00099 | Cleaning – Heat Exchanger HX-0029 | HX-0029 | 2 | 3 | 3 |  | FALSE | 1541 | 5551.51 | 26.1 | 0.2 | 0 | 8.8 | 35.1 | 4 | 2 | 2190 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | 26996.81 | 21445.3 | TRUE | INCLUDE
WO-00100 | Replacement – Centrifugal Pump PMP-0061 | PMP-0061 | 6 | 2 | 2 |  | FALSE | 1143 | 73482.47 | 19.6 | 5 | 13.4 | 4.2 | 42.2 | 5 | 2.5 | 1825 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | 5761.08 | -67721.39 | FALSE | DEFER
WO-00101 | Replacement – Centrifugal Pump PMP-0019 | PMP-0019 | 6 | 3 | 2 |  | FALSE | 588 | 81236.69 | 47.9 | 5 | 4.9 | 5 | 62.8 | 8 | 2.5 | 1825 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | 2786.64 | -78450.05 | FALSE | DEFER
WO-00102 | Cleaning – Electrical Equipment ELEC-0035 | ELEC-0035 | 2 | 3 | 2 |  | FALSE | 1133 | 17845.16 | 13.7 | 0.5 | 1.1 | 3.6 | 18.9 | 2 | 2 | 1460 | 0.3627 | 1082.4436 | 2.5 | 4 | 2 | 8 | 3264.29 | -14580.87 | FALSE | DEFER
WO-00103 | Inspection – Pressure Vessel VSL-0001 | VSL-0001 | 3 | 4 | 3 |  | FALSE | 3190 | 2755.35 | 6.1 | 1 | 3.4 | 0.4 | 10.9 | 1 | 2.8 | 3650 | 0.21575 | 1726.4951 | 5 | 3 | 5 | 15 | 46925.07 | 44169.72 | TRUE | INCLUDE
WO-00104 | Repair – Pressure Vessel VSL-0020 | VSL-0020 | 5 | 1 | 2 |  | TRUE | 908 | 70570.85 | 65.9 | 20.5 | 13 | 4.9 | 104.3 | 13 | 2.8 | 3650 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | 6857.86 | -63712.99 | TRUE | INCLUDE
WO-00105 | Cleaning – Instrument/Analyser INST-0112 | INST-0112 | 2 | 3 | 3 |  | FALSE | 4794 | 1612.76 | 4.2 | 1.7 | 0.1 | 6.2 | 12.2 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -172.76 | FALSE | DEFER
WO-00106 | Inspection – Pressure Vessel VSL-0019 | VSL-0019 | 3 | 1 | 4 |  | FALSE | 4641 | 7228.41 | 3.5 | 1.8 | 4.1 | 0.2 | 9.6 | 1 | 2.8 | 3650 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | 80556.21 | 73327.8 | TRUE | INCLUDE
WO-00107 | Replacement – Instrument/Analyser INST-0065 | INST-0065 | 6 | 2 | 3 | WO-00038 | FALSE | 3048 | 50764.32 | 20.8 | 20 | 8.6 | 8.5 | 57.9 | 7 | 1.8 | 730 | 0.94806 | 730 | 2 | 5 | 2 | 10 | 1365.21 | -49399.11 | FALSE | DEFER
WO-00108 | Testing – Centrifugal Pump PMP-0037 | PMP-0037 | 7 | 1 | 3 |  | TRUE | 3968 | 3770.09 | 9.6 | 15.2 | 6.4 | 1.6 | 32.8 | 4 | 2.5 | 1825 | 0.82008 | 1825 | 3 | 5 | 3 | 15 | 17713.81 | 13943.72 | TRUE | INCLUDE
WO-00109 | Cleaning – Heat Exchanger HX-0018 | HX-0018 | 2 | 1 | 3 |  | TRUE | 2059 | 14191.21 | 18.5 | 0.1 | 0.3 | 3.3 | 22.2 | 3 | 2 | 2190 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | 33820.42 | 19629.21 | TRUE | INCLUDE
WO-00110 | Inspection – Piping/Pipeline Segment PPL-0003 | PPL-0003 | 3 | 2 | 3 |  | FALSE | 4164 | 7422.22 | 6.1 | 1.2 | 2.4 | 0.3 | 10 | 1 | 2 | 3285 | 0.25475 | 820.7481 | 3.65 | 3 | 4 | 12 | 12273.66 | 4851.44 | TRUE | INCLUDE
WO-00111 | Replacement – Pressure Vessel VSL-0028 | VSL-0028 | 6 | 2 | 3 |  | FALSE | 3718 | 44519.28 | 31.5 | 11.1 | 23.7 | 3 | 69.3 | 9 | 2.8 | 3650 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | 58882.1 | 14362.82 | FALSE | DEFER
WO-00112 | Inspection – Heat Exchanger HX-0025 | HX-0025 | 3 | 1 | 3 |  | FALSE | 1802 | 3189.99 | 7.7 | 0.3 | 3.3 | 0.4 | 11.7 | 1 | 2 | 2190 | 0.2607 | 1521.1654 | 4 | 3 | 4 | 12 | 30502.19 | 27312.2 | TRUE | INCLUDE
WO-00113 | Testing – Control Valve VLV-0098 | VLV-0098 | 7 | 3 | 3 |  | FALSE | 4428 | 6497.25 | 16.1 | 12.3 | 22.7 | 0.6 | 51.7 | 6 | 1.5 | 1095 | 0.64153 | 1095 | 2.65 | 5 | 3 | 15 | 3442.61 | -3054.64 | FALSE | DEFER
WO-00114 | Calibration – Control Valve VLV-0076 | VLV-0076 | 1 | 3 | 3 |  | FALSE | 1553 | 1162.27 | 0.7 | 10 | 12.9 | 0.7 | 24.3 | 3 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | 1343.61 | TRUE | INCLUDE
WO-00115 | Repair – Control Valve VLV-0038 | VLV-0038 | 5 | 4 | 3 |  | FALSE | 4177 | 69222.36 | 59.8 | 11.7 | 2.4 | 6.5 | 80.4 | 10 | 1.5 | 1095 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | 3387.34 | -65835.02 | FALSE | DEFER
WO-00116 | Overhaul – Control Valve VLV-0050 | VLV-0050 | 4 | 3 | 3 |  | FALSE | 3385 | 111353.09 | 97.6 | 29.4 | 43.1 | 7.4 | 177.5 | 22 | 1.5 | 1095 | 0.5944 | 1095 | 2.65 | 4 | 3 | 12 | 3189.72 | -108163.37 | FALSE | DEFER
WO-00117 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | 1 | 1 | 3 |  | FALSE | 1397 | 2820.93 | 0.2 | 9.4 | 13.6 | 0.8 | 24 | 3 | 1.8 | 730 | 0.81141 | 730 | 2 | 5 | 2 | 10 | 1168.43 | -1652.5 | FALSE | DEFER
WO-00118 | Overhaul – Centrifugal Pump PMP-0067 | PMP-0067 | 4 | 1 | 3 |  | TRUE | 5280 | 379238.36 | 101.4 | 26.1 | 31.3 | 15.1 | 173.9 | 22 | 2.5 | 1825 | 0.92495 | 1825 | 3 | 5 | 3 | 15 | 19978.83 | -359259.53 | TRUE | INCLUDE
WO-00119 | Overhaul – Control Valve VLV-0060 | VLV-0060 | 4 | 2 | 3 |  | FALSE | 3041 | 140083.62 | 223.3 | 49 | 20.6 | 7.5 | 300.4 | 38 | 1.5 | 1095 | 0.57589 | 1095 | 2.65 | 4 | 3 | 12 | 3090.38 | -136993.24 | FALSE | DEFER
WO-00120 | Overhaul – Distillation Tower TWR-0011 | TWR-0011 | 4 | 3 | 3 | WO-00098 | FALSE | 2943 | 526585.78 | 140 | 10.3 | 9.7 | 8.5 | 168.5 | 21 | 2.2 | 2920 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | 189640.61 | -336945.17 | FALSE | DEFER
WO-00121 | Cleaning – Instrument/Analyser INST-0044 | INST-0044 | 2 | 4 | 3 |  | FALSE | 3023 | 14510.99 | 11.7 | 1.9 | 0.7 | 8.7 | 23 | 3 | 1.8 | 730 | 0.9471 | 730 | 2 | 5 | 2 | 10 | 1363.83 | -13147.16 | FALSE | DEFER
WO-00122 | Overhaul – Electrical Equipment ELEC-0076 | ELEC-0076 | 4 | 2 | 2 |  | FALSE | 1871 | 538159.22 | 95.4 | 35.7 | 11.7 | 13.5 | 156.3 | 20 | 2 | 1460 | 0.50503 | 344.4436 | 2.5 | 4 | 2 | 8 | 4545.25 | -533613.97 | FALSE | DEFER
WO-00123 | Inspection – Storage Tank TNK-0018 | TNK-0018 | 3 | 4 | 2 |  | FALSE | 3277 | 627.57 | 4.6 | 1.2 | 2.8 | 0.3 | 8.9 | 1 | 3.5 | 5475 | 0.071498 | 3671.2321 | 4 | 2 | 4 | 8 | 16730.59 | 16103.02 | TRUE | INCLUDE
WO-00124 | Testing – Control Valve VLV-0053 | VLV-0053 | 7 | 3 | 3 |  | FALSE | 4836 | 2321.97 | 9.5 | 17 | 18.7 | 0.7 | 45.9 | 6 | 1.5 | 1095 | 0.65711 | 1095 | 2.65 | 5 | 3 | 15 | 3526.23 | 1204.26 | TRUE | INCLUDE
WO-00125 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | 3 | 2 | 3 |  | FALSE | 2938 | 3055.41 | 7.7 | 1.3 | 4.3 | 0 | 13.3 | 2 | 1.8 | 730 | 0.94369 | 730 | 2 | 5 | 2 | 10 | 1358.91 | -1696.5 | FALSE | DEFER
WO-00126 | Inspection – Centrifugal Pump PMP-0014 | PMP-0014 | 3 | 1 | 3 |  | TRUE | 4238 | 2021.65 | 2 | 1 | 3.1 | 0.7 | 6.8 | 1 | 2.5 | 1825 | 0.84821 | 1825 | 3 | 5 | 3 | 15 | 18321.4 | 16299.75 | TRUE | INCLUDE
WO-00127 | Inspection – Instrument/Analyser INST-0092 | INST-0092 | 3 | 4 | 3 |  | FALSE | 5012 | 5586.79 | 2.4 | 1.7 | 1.1 | 0.5 | 5.7 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -4146.79 | FALSE | DEFER
WO-00128 | Cleaning – Heat Exchanger HX-0016 | HX-0016 | 2 | 4 | 3 |  | FALSE | 3286 | 15602 | 20.4 | 0.2 | 1.3 | 9 | 30.9 | 4 | 2 | 2190 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | 47990.52 | 32388.52 | TRUE | INCLUDE
WO-00129 | Overhaul – Centrifugal Pump PMP-0046 | PMP-0046 | 4 | 1 | 2 |  | FALSE | 522 | 216535.34 | 190.7 | 30.8 | 18.8 | 7.4 | 247.7 | 31 | 2.5 | 1825 | 0.1139 | 2025.705 | 3 | 2 | 3 | 6 | 2460.33 | -214075.01 | FALSE | DEFER
WO-00130 | Overhaul – Instrument/Analyser INST-0126 | INST-0126 | 4 | 1 | 3 | WO-00048 | FALSE | 798 | 114522.78 | 43.9 | 10.2 | 47.1 | 5.5 | 106.7 | 13 | 1.8 | 730 | 0.67971 | 362.256 | 2 | 5 | 2 | 10 | 978.78 | -113544 | FALSE | DEFER
WO-00131 | Overhaul – Heat Exchanger HX-0031 | HX-0031 | 4 | 1 | 3 |  | FALSE | 2260 | 158383.67 | 232.5 | 46.3 | 25 | 13 | 316.8 | 40 | 2 | 2190 | 0.31048 | 1063.1652 | 4 | 3 | 4 | 12 | 36326.65 | -122057.02 | FALSE | DEFER
WO-00132 | Inspection – Instrument/Analyser INST-0005 | INST-0005 | 3 | 2 | 3 |  | FALSE | 5373 | 2767.07 | 3 | 0.2 | 3.2 | 0.1 | 6.5 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -1327.07 | FALSE | DEFER
WO-00133 | Overhaul – Centrifugal Pump PMP-0063 | PMP-0063 | 4 | 3 | 3 | WO-00065 | FALSE | 2312 | 273735.18 | 67.5 | 8.2 | 16.1 | 8.7 | 100.5 | 13 | 2.5 | 1825 | 0.55047 | 235.7051 | 3 | 4 | 3 | 12 | 11890.05 | -261845.13 | FALSE | DEFER
WO-00134 | Repair – Instrument/Analyser INST-0172 | INST-0172 | 5 | 2 | 3 |  | FALSE | 4158 | 33663.66 | 45.3 | 22.5 | 13.3 | 2.7 | 83.8 | 10 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -32223.66 | FALSE | DEFER
WO-00135 | Overhaul – Electrical Equipment ELEC-0004 | ELEC-0004 | 4 | 3 | 3 |  | FALSE | 4389 | 345424.59 | 67.7 | 20.3 | 20.8 | 9.2 | 118 | 15 | 2 | 1460 | 0.79103 | 1460 | 2.5 | 5 | 2 | 10 | 7119.3 | -338305.29 | FALSE | DEFER
WO-00136 | Cleaning – Instrument/Analyser INST-0066 | INST-0066 | 2 | 1 | 3 |  | FALSE | 1201 | 13225.36 | 8.8 | 0.2 | 1.6 | 5.8 | 16.4 | 2 | 1.8 | 730 | 0.77693 | 730 | 2 | 5 | 2 | 10 | 1118.77 | -12106.59 | FALSE | DEFER
WO-00137 | Replacement – Electrical Equipment ELEC-0048 | ELEC-0048 | 6 | 3 | 2 | WO-00091 | FALSE | 1664 | 97463.88 | 47.1 | 17.8 | 16 | 4.8 | 85.7 | 11 | 2 | 1460 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | 4217.99 | -93245.89 | FALSE | DEFER
WO-00138 | Inspection – Pressure Vessel VSL-0020 | VSL-0020 | 3 | 1 | 2 |  | TRUE | 908 | 5415.91 | 6.7 | 0.3 | 4.5 | 0.4 | 11.9 | 1 | 2.8 | 3650 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | 6857.86 | 1441.95 | TRUE | INCLUDE
WO-00139 | Replacement – Reciprocating Compressor CMP-0002 | CMP-0002 | 6 | 3 | 4 |  | FALSE | 1206 | 105033.52 | 55.7 | 10.8 | 23.1 | 8.9 | 98.5 | 12 | 3 | 1460 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | 172649.17 | 67615.65 | TRUE | INCLUDE
WO-00140 | Repair – Heat Exchanger HX-0015 | HX-0015 | 5 | 3 | 3 |  | FALSE | 2872 | 31786.28 | 77.6 | 19 | 15 | 2.6 | 114.2 | 14 | 2 | 2190 | 0.37181 | 451.1654 | 4 | 4 | 4 | 16 | 43502.04 | 11715.76 | TRUE | INCLUDE
WO-00141 | Testing – Control Valve VLV-0004 | VLV-0004 | 7 | 3 | 2 |  | FALSE | 436 | 4888.62 | 19.8 | 11.6 | 8 | 0.2 | 39.6 | 5 | 1.5 | 1095 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | 1675.84 | -3212.78 | FALSE | DEFER
WO-00142 | Cleaning – Reciprocating Compressor CMP-0010 | CMP-0010 | 2 | 2 | 4 |  | FALSE | 2274 | 8371.15 | 18.6 | 0.7 | 0.9 | 8.9 | 29.1 | 4 | 3 | 1460 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | 307515.33 | 299144.18 | TRUE | INCLUDE
WO-00143 | Calibration – Control Valve VLV-0069 | VLV-0069 | 1 | 3 | 3 |  | FALSE | 3104 | 1833.78 | 2 | 3.9 | 8.2 | 0.1 | 14.2 | 2 | 1.5 | 1095 | 0.57942 | 1095 | 2.65 | 4 | 3 | 12 | 3109.29 | 1275.51 | TRUE | INCLUDE
WO-00144 | Cleaning – Control Valve VLV-0001 | VLV-0001 | 2 | 2 | 3 |  | FALSE | 4337 | 18423.08 | 12.1 | 0 | 1.3 | 10 | 23.4 | 3 | 1.5 | 1095 | 0.63786 | 1095 | 2.65 | 5 | 3 | 15 | 3422.93 | -15000.15 | FALSE | DEFER
WO-00145 | Inspection – Instrument/Analyser INST-0076 | INST-0076 | 3 | 2 | 3 |  | FALSE | 1289 | 2685.08 | 5.4 | 0.5 | 2.4 | 0.6 | 8.9 | 1 | 1.8 | 730 | 0.79324 | 730 | 2 | 5 | 2 | 10 | 1142.27 | -1542.81 | FALSE | DEFER
WO-00146 | Replacement – Heat Exchanger HX-0013 | HX-0013 | 6 | 2 | 3 |  | FALSE | 4364 | 9603.6 | 55.7 | 9.3 | 10.6 | 1.8 | 77.4 | 10 | 2 | 2190 | 0.49943 | 2190 | 4 | 4 | 4 | 16 | 58433.39 | 48829.79 | TRUE | INCLUDE
WO-00147 | Repair – Instrument/Analyser INST-0095 | INST-0095 | 5 | 3 | 3 |  | FALSE | 3080 | 5209.95 | 21.4 | 7.8 | 12.8 | 9.3 | 51.3 | 6 | 1.8 | 730 | 0.94927 | 730 | 2 | 5 | 2 | 10 | 1366.94 | -3843.01 | FALSE | DEFER
WO-00148 | Replacement – Control Valve VLV-0076 | VLV-0076 | 6 | 3 | 3 |  | FALSE | 1553 | 93071.68 | 46.6 | 6.4 | 7.2 | 4.2 | 64.4 | 8 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | -90565.8 | FALSE | DEFER
WO-00149 | Calibration – Instrument/Analyser INST-0135 | INST-0135 | 1 | 4 | 3 |  | FALSE | 4457 | 2064.39 | 1.7 | 4.2 | 9.4 | 0 | 15.3 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -624.39 | FALSE | DEFER
WO-00150 | Cleaning – Instrument/Analyser INST-0027 | INST-0027 | 2 | 2 | 3 |  | FALSE | 2469 | 8154.94 | 5.7 | 1.4 | 1.5 | 7.3 | 15.9 | 2 | 1.8 | 730 | 0.91997 | 730 | 2 | 5 | 2 | 10 | 1324.76 | -6830.18 | FALSE | DEFER
WO-00151 | Repair – Storage Tank TNK-0006 | TNK-0006 | 5 | 2 | 3 |  | FALSE | 4911 | 60746.33 | 68.5 | 20.9 | 18.3 | 9.4 | 117.1 | 15 | 3.5 | 5475 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | 41445.54 | -19300.79 | FALSE | DEFER
WO-00152 | Overhaul – Pressure Vessel VSL-0022 | VSL-0022 | 4 | 4 | 3 |  | FALSE | 3687 | 227784.38 | 203.8 | 35.1 | 11.2 | 6.8 | 256.9 | 32 | 2.8 | 3650 | 0.26743 | 1229.4951 | 5 | 3 | 5 | 15 | 58166.81 | -169617.57 | FALSE | DEFER
WO-00153 | Repair – Control Valve VLV-0051 | VLV-0051 | 5 | 2 | 3 |  | FALSE | 2376 | 76242.93 | 47.4 | 24.4 | 16.9 | 3.8 | 92.5 | 12 | 1.5 | 1095 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | 2866.96 | -73375.97 | FALSE | DEFER
WO-00154 | Testing – Instrument/Analyser INST-0075 | INST-0075 | 7 | 3 | 3 | WO-00025 | FALSE | 1134 | 938.18 | 12.8 | 17 | 17.6 | 0.5 | 47.9 | 6 | 1.8 | 730 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | 1099.43 | 161.25 | FALSE | DEFER
WO-00155 | Replacement – Instrument/Analyser INST-0118 | INST-0118 | 6 | 2 | 3 | WO-00145 | FALSE | 4114 | 100339.4 | 19.4 | 14.5 | 19.7 | 2.7 | 56.3 | 7 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -98899.4 | FALSE | DEFER
WO-00156 | Calibration – Pressure Vessel VSL-0021 | VSL-0021 | 1 | 1 | 3 |  | TRUE | 3766 | 440.8 | 0.4 | 5.6 | 18.9 | 0.6 | 25.5 | 3 | 2.8 | 3650 | 0.27583 | 1150.4951 | 5 | 3 | 5 | 15 | 59992.23 | 59551.43 | TRUE | INCLUDE
WO-00157 | Testing – Instrument/Analyser INST-0056 | INST-0056 | 7 | 3 | 3 |  | FALSE | 1149 | 7223.81 | 9.8 | 12.2 | 10.2 | 0.7 | 32.9 | 4 | 1.8 | 730 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | 1103.88 | -6119.93 | FALSE | DEFER
WO-00158 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | 3 | 3 | 3 |  | FALSE | 4714 | 5645.44 | 3.6 | 0.8 | 1.6 | 0.6 | 6.6 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -4205.44 | FALSE | DEFER
WO-00159 | Replacement – Control Valve VLV-0058 | VLV-0058 | 6 | 2 | 3 | WO-00011 | FALSE | 2492 | 23792.91 | 19.8 | 16.7 | 9.4 | 8 | 53.9 | 7 | 1.5 | 1095 | 0.54217 | 1095 | 2.65 | 4 | 3 | 12 | 2909.45 | -20883.46 | FALSE | DEFER
WO-00160 | Inspection – Control Valve VLV-0063 | VLV-0063 | 3 | 2 | 3 |  | FALSE | 871 | 5982.08 | 5.7 | 0.1 | 4.8 | 0.1 | 10.7 | 1 | 1.5 | 1095 | 0.38726 | 1038.3751 | 2.65 | 4 | 3 | 12 | 2078.14 | -3903.94 | FALSE | DEFER
WO-00161 | Replacement – Storage Tank TNK-0008 | TNK-0008 | 6 | 4 | 1 |  | FALSE | 1128 | 61284.44 | 48.8 | 2.1 | 22.6 | 6.8 | 80.3 | 10 | 3.5 | 5475 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | 1543.9 | -59740.54 | FALSE | DEFER
WO-00162 | Calibration – Instrument/Analyser INST-0128 | INST-0128 | 1 | 3 | 3 |  | FALSE | 5090 | 2797.95 | 1.2 | 4.9 | 11.1 | 0.7 | 17.9 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -1357.95 | FALSE | DEFER
WO-00163 | Calibration – Centrifugal Pump PMP-0060 | PMP-0060 | 1 | 1 | 3 |  | TRUE | 2925 | 457.17 | 1.7 | 3.6 | 19.1 | 0.2 | 24.6 | 3 | 2.5 | 1825 | 0.67091 | 1825 | 3 | 5 | 3 | 15 | 14491.65 | 14034.48 | TRUE | INCLUDE
WO-00164 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | 1 | 1 | 3 |  | TRUE | 3032 | 2492.37 | 1.5 | 9.7 | 8.3 | 0.8 | 20.3 | 3 | 2 | 3285 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | 9416.04 | 6923.67 | TRUE | INCLUDE
WO-00165 | Cleaning – Instrument/Analyser INST-0151 | INST-0151 | 2 | 4 | 3 |  | FALSE | 4032 | 11694.4 | 4.1 | 1.1 | 1.5 | 3.4 | 10.1 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -10254.4 | FALSE | DEFER
WO-00166 | Cleaning – Centrifugal Pump PMP-0032 | PMP-0032 | 2 | 1 | 3 |  | TRUE | 1838 | 5277.9 | 19.5 | 0.4 | 0.1 | 7.5 | 27.5 | 3 | 2.5 | 1825 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | 9543.04 | 4265.14 | TRUE | INCLUDE
WO-00167 | Inspection – Instrument/Analyser INST-0161 | INST-0161 | 3 | 3 | 3 |  | FALSE | 708 | 6075.58 | 2.4 | 1.6 | 4.2 | 0.1 | 8.3 | 1 | 1.8 | 730 | 0.65143 | 452.2559 | 2 | 5 | 2 | 10 | 938.05 | -5137.53 | FALSE | DEFER
WO-00168 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | 3 | 2 | 3 |  | FALSE | 1134 | 5281.03 | 2.5 | 1.9 | 1.8 | 0.7 | 6.9 | 1 | 1.8 | 730 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | 1099.43 | -4181.6 | FALSE | DEFER
WO-00169 | Replacement – Storage Tank TNK-0013 | TNK-0013 | 6 | 1 | 1 |  | TRUE | 2765 | 56859.21 | 37.8 | 20 | 4.5 | 1 | 63.3 | 8 | 3.5 | 5475 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | 11354.04 | -45505.17 | TRUE | INCLUDE
WO-00170 | Replacement – Instrument/Analyser INST-0012 | INST-0012 | 6 | 3 | 3 |  | FALSE | 5372 | 106641.28 | 55.5 | 17.8 | 6.9 | 4.7 | 84.9 | 11 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -105201.28 | FALSE | DEFER
WO-00171 | Replacement – Instrument/Analyser INST-0031 | INST-0031 | 6 | 4 | 3 | WO-00103 | FALSE | 2503 | 81272.37 | 20.3 | 7.8 | 21.2 | 3.3 | 52.6 | 7 | 1.8 | 730 | 0.92201 | 730 | 2 | 5 | 2 | 10 | 1327.7 | -79944.67 | FALSE | DEFER
WO-00172 | Replacement – Control Valve VLV-0064 | VLV-0064 | 6 | 3 | 3 |  | FALSE | 4675 | 7705.73 | 21.3 | 5.1 | 14.1 | 2 | 42.5 | 5 | 1.5 | 1095 | 0.65112 | 1095 | 2.65 | 5 | 3 | 15 | 3494.09 | -4211.64 | FALSE | DEFER
WO-00173 | Repair – Control Valve VLV-0068 | VLV-0068 | 5 | 2 | 3 |  | FALSE | 4345 | 30276.47 | 23.5 | 14.4 | 16.1 | 6.3 | 60.3 | 8 | 1.5 | 1095 | 0.63819 | 1095 | 2.65 | 5 | 3 | 15 | 3424.67 | -26851.8 | FALSE | DEFER
WO-00174 | Cleaning – Instrument/Analyser INST-0092 | INST-0092 | 2 | 2 | 3 |  | FALSE | 5012 | 12234.05 | 11.9 | 0.2 | 2 | 3.4 | 17.5 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -10794.05 | FALSE | DEFER
WO-00175 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | 3 | 2 | 3 |  | FALSE | 4705 | 4819.43 | 5.5 | 0.5 | 2.7 | 0.7 | 9.4 | 1 | 2 | 1460 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | 7312.2 | 2492.77 | TRUE | INCLUDE
WO-00176 | Repair – Electrical Equipment ELEC-0082 | ELEC-0082 | 5 | 4 | 3 |  | FALSE | 3193 | 25895.01 | 26.2 | 28.8 | 16.6 | 4.1 | 75.7 | 9 | 2 | 1460 | 0.68526 | 1460 | 2.5 | 5 | 2 | 10 | 6167.3 | -19727.71 | FALSE | DEFER
WO-00177 | Overhaul – Electrical Equipment ELEC-0008 | ELEC-0008 | 4 | 2 | 3 | WO-00015 | FALSE | 2985 | 217850.21 | 207.9 | 39.6 | 20.5 | 16.1 | 284.1 | 36 | 2 | 1460 | 0.66202 | 1460 | 2.5 | 5 | 2 | 10 | 5958.15 | -211892.06 | FALSE | DEFER
WO-00178 | Inspection – Instrument/Analyser INST-0087 | INST-0087 | 3 | 2 | 3 |  | FALSE | 3121 | 7717.44 | 6.4 | 1.2 | 3.4 | 0.6 | 11.6 | 1 | 1.8 | 730 | 0.95076 | 730 | 2 | 5 | 2 | 10 | 1369.1 | -6348.34 | FALSE | DEFER
WO-00179 | Testing – Instrument/Analyser INST-0019 | INST-0019 | 7 | 2 | 3 |  | FALSE | 5171 | 9514.19 | 14.1 | 13.1 | 9.8 | 0.1 | 37.1 | 5 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -8074.19 | FALSE | DEFER
WO-00180 | Inspection – Control Valve VLV-0079 | VLV-0079 | 3 | 2 | 3 | WO-00168 | FALSE | 3869 | 5499.45 | 9 | 0.6 | 2.3 | 0.7 | 12.6 | 2 | 1.5 | 1095 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | 3315.02 | -2184.43 | FALSE | DEFER
WO-00181 | Testing – Electrical Equipment ELEC-0006 | ELEC-0006 | 7 | 3 | 2 |  | FALSE | 885 | 5775.78 | 3.8 | 7.5 | 22.7 | 0.5 | 34.5 | 4 | 2 | 1460 | 0.30621 | 1330.4436 | 2.5 | 3 | 2 | 6 | 2755.87 | -3019.91 | FALSE | DEFER
WO-00182 | Inspection – Control Valve VLV-0066 | VLV-0066 | 3 | 4 | 3 |  | FALSE | 4463 | 2036.35 | 9 | 0.3 | 1.1 | 0.5 | 10.9 | 1 | 1.5 | 1095 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | 3450.07 | 1413.72 | TRUE | INCLUDE
WO-00183 | Replacement – Control Valve VLV-0034 | VLV-0034 | 6 | 3 | 3 |  | FALSE | 2541 | 19738.66 | 59.1 | 14.2 | 21 | 7.8 | 102.1 | 13 | 1.5 | 1095 | 0.54543 | 1095 | 2.65 | 4 | 3 | 12 | 2926.9 | -16811.76 | FALSE | DEFER
WO-00184 | Replacement – Electrical Equipment ELEC-0068 | ELEC-0068 | 6 | 2 | 2 |  | FALSE | 385 | 42299.1 | 45.3 | 14.9 | 23 | 6.1 | 89.3 | 11 | 2 | 1460 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | 1589.67 | -40709.43 | FALSE | DEFER
WO-00185 | Overhaul – Instrument/Analyser INST-0075 | INST-0075 | 4 | 3 | 3 |  | FALSE | 1134 | 374022.58 | 125.3 | 41.2 | 32.6 | 4.2 | 203.3 | 25 | 1.8 | 730 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | 1099.43 | -372923.15 | FALSE | DEFER
WO-00186 | Cleaning – Control Valve VLV-0088 | VLV-0088 | 2 | 1 | 3 |  | TRUE | 4120 | 22966.27 | 13.9 | 1.1 | 0.9 | 6.3 | 22.2 | 3 | 1.5 | 1095 | 0.62881 | 1095 | 2.65 | 5 | 3 | 15 | 3374.35 | -19591.92 | TRUE | INCLUDE
WO-00187 | Repair – Electrical Equipment ELEC-0067 | ELEC-0067 | 5 | 3 | 3 |  | FALSE | 5432 | 73012.16 | 58.4 | 18.5 | 3 | 6.4 | 86.3 | 11 | 2 | 1460 | 0.8538 | 1460 | 2.5 | 5 | 2 | 10 | 7684.19 | -65327.97 | FALSE | DEFER
WO-00188 | Calibration – Piping/Pipeline Segment PPL-0022 | PPL-0022 | 1 | 1 | 3 |  | TRUE | 3032 | 331.95 | 1.4 | 4.3 | 14.4 | 0.6 | 20.7 | 3 | 2 | 3285 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | 9416.04 | 9084.09 | TRUE | INCLUDE
WO-00189 | Overhaul – Control Valve VLV-0066 | VLV-0066 | 4 | 3 | 3 | WO-00126 | FALSE | 4463 | 503845.46 | 161.1 | 10.9 | 26.6 | 10.2 | 208.8 | 26 | 1.5 | 1095 | 0.64292 | 1095 | 2.65 | 5 | 3 | 15 | 3450.07 | -500395.39 | FALSE | DEFER
WO-00190 | Cleaning – Instrument/Analyser INST-0032 | INST-0032 | 2 | 2 | 3 |  | FALSE | 2787 | 1249.55 | 18.6 | 1.5 | 1.5 | 2.5 | 24.1 | 3 | 1.8 | 730 | 0.93702 | 730 | 2 | 5 | 2 | 10 | 1349.31 | 99.76 | FALSE | DEFER
WO-00191 | Overhaul – Instrument/Analyser INST-0009 | INST-0009 | 4 | 2 | 3 |  | FALSE | 3990 | 120166.45 | 124.1 | 11 | 12.8 | 17.4 | 165.3 | 21 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -118726.45 | FALSE | DEFER
WO-00192 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | 1 | 2 | 3 |  | FALSE | 4725 | 334.7 | 1.1 | 5.1 | 16.8 | 0.8 | 23.8 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 1105.3 | TRUE | INCLUDE
WO-00193 | Cleaning – Piping/Pipeline Segment PPL-0015 | PPL-0015 | 2 | 3 | 2 |  | FALSE | 1197 | 6461.17 | 17.9 | 0.2 | 0.9 | 3.5 | 22.5 | 3 | 2 | 3285 | 0.089098 | 3787.7482 | 3.65 | 2 | 4 | 8 | 4292.73 | -2168.44 | FALSE | DEFER
WO-00194 | Overhaul – Instrument/Analyser INST-0049 | INST-0049 | 4 | 3 | 3 | WO-00142 | FALSE | 648 | 360602.64 | 112.1 | 20.1 | 16.5 | 22.2 | 170.9 | 21 | 1.8 | 730 | 0.63084 | 512.2559 | 2 | 5 | 2 | 10 | 908.42 | -359694.22 | FALSE | DEFER
WO-00195 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | 3 | 2 | 2 |  | FALSE | 2067 | 6125.76 | 5.3 | 0 | 3.1 | 0.1 | 8.5 | 1 | 2 | 1460 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | 4834.45 | -1291.31 | FALSE | DEFER
WO-00196 | Calibration – Instrument/Analyser INST-0079 | INST-0079 | 1 | 4 | 3 |  | FALSE | 2869 | 920 | 1.8 | 7.3 | 17.3 | 0.6 | 27 | 3 | 1.8 | 730 | 0.94074 | 730 | 2 | 5 | 2 | 10 | 1354.67 | 434.67 | TRUE | INCLUDE
WO-00197 | Replacement – Electrical Equipment ELEC-0080 | ELEC-0080 | 6 | 3 | 3 | WO-00164 | FALSE | 4830 | 68151.17 | 34.8 | 18.3 | 7.3 | 6.2 | 66.6 | 8 | 2 | 1460 | 0.82033 | 1460 | 2.5 | 5 | 2 | 10 | 7382.93 | -60768.24 | FALSE | DEFER
WO-00198 | Replacement – Control Valve VLV-0120 | VLV-0120 | 6 | 1 | 3 |  | TRUE | 2323 | 104771.88 | 27.4 | 5.1 | 15.7 | 4.8 | 53 | 7 | 1.5 | 1095 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | 2846.98 | -101924.9 | TRUE | INCLUDE
WO-00199 | Inspection – Control Valve VLV-0108 | VLV-0108 | 3 | 3 | 3 |  | FALSE | 5123 | 2045.05 | 8.2 | 1.8 | 3.2 | 0.1 | 13.3 | 2 | 1.5 | 1095 | 0.66731 | 1095 | 2.65 | 5 | 3 | 15 | 3580.94 | 1535.89 | TRUE | INCLUDE
WO-00200 | Repair – Pressure Vessel VSL-0011 | VSL-0011 | 5 | 1 | 3 |  | FALSE | 2686 | 60459.26 | 34.8 | 7.2 | 18.2 | 8.7 | 68.9 | 9 | 2.8 | 3650 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | 36127.93 | -24331.33 | FALSE | DEFER
WO-00201 | Repair – Piping/Pipeline Segment PPL-0043 | PPL-0043 | 5 | 4 | 2 |  | FALSE | 1877 | 9582.59 | 13.8 | 23.7 | 11.7 | 4.7 | 53.9 | 7 | 2 | 3285 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | 6265.83 | -3316.76 | FALSE | DEFER
WO-00202 | Repair – Instrument/Analyser INST-0088 | INST-0088 | 5 | 3 | 3 |  | FALSE | 2094 | 6494.63 | 64.7 | 24.1 | 11.9 | 9.8 | 110.5 | 14 | 1.8 | 730 | 0.89303 | 730 | 2 | 5 | 2 | 10 | 1285.97 | -5208.66 | FALSE | DEFER
WO-00203 | Inspection – Heat Exchanger HX-0016 | HX-0016 | 3 | 3 | 3 |  | FALSE | 3286 | 2067.41 | 8.6 | 2 | 1.4 | 0.1 | 12.1 | 2 | 2 | 2190 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | 47990.52 | 45923.11 | TRUE | INCLUDE
WO-00204 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | 3 | 1 | 3 |  | FALSE | 1524 | 1107.34 | 9.1 | 1.6 | 4.5 | 0.7 | 15.9 | 2 | 2.5 | 1825 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | 7865.02 | 6757.68 | TRUE | INCLUDE
WO-00205 | Repair – Instrument/Analyser INST-0031 | INST-0031 | 5 | 2 | 3 |  | FALSE | 2503 | 25300.43 | 33.3 | 27 | 14.3 | 9.1 | 83.7 | 10 | 1.8 | 730 | 0.92201 | 730 | 2 | 5 | 2 | 10 | 1327.7 | -23972.73 | TRUE | INCLUDE
WO-00206 | Testing – Electrical Equipment ELEC-0029 | ELEC-0029 | 7 | 3 | 2 |  | FALSE | 1604 | 9384.76 | 14 | 22.3 | 11.6 | 1.4 | 49.3 | 6 | 2 | 1460 | 0.45763 | 611.4436 | 2.5 | 4 | 2 | 8 | 4118.71 | -5266.05 | TRUE | INCLUDE
WO-00207 | Calibration – Instrument/Analyser INST-0006 | INST-0006 | 1 | 4 | 3 |  | FALSE | 3489 | 2711.44 | 1.4 | 2.5 | 6.9 | 1 | 11.8 | 1 | 1.8 | 730 | 0.96225 | 730 | 2 | 5 | 2 | 10 | 1385.63 | -1325.81 | FALSE | DEFER
WO-00208 | Testing – Instrument/Analyser INST-0057 | INST-0057 | 7 | 3 | 3 |  | FALSE | 976 | 1033.59 | 8.9 | 19.2 | 19.1 | 0.2 | 47.4 | 6 | 1.8 | 730 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | 1048.11 | 14.52 | FALSE | DEFER
WO-00209 | Inspection – Electrical Equipment ELEC-0025 | ELEC-0025 | 3 | 3 | 2 |  | FALSE | 2067 | 4249.75 | 3.9 | 0.1 | 1.3 | 0.9 | 6.2 | 1 | 2 | 1460 | 0.53716 | 148.4436 | 2.5 | 4 | 2 | 8 | 4834.45 | 584.7 | FALSE | DEFER
WO-00210 | Testing – Instrument/Analyser INST-0029 | INST-0029 | 7 | 3 | 3 |  | FALSE | 3371 | 7314.85 | 9.4 | 11.2 | 16.3 | 0.7 | 37.6 | 5 | 1.8 | 730 | 0.95892 | 730 | 2 | 5 | 2 | 10 | 1380.84 | -5934.01 | FALSE | DEFER
WO-00211 | Calibration – Storage Tank TNK-0009 | TNK-0009 | 1 | 3 | 3 | WO-00206 | FALSE | 5278 | 2652.36 | 0.5 | 6.2 | 7.6 | 0 | 14.3 | 2 | 3.5 | 5475 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | 48441.95 | 45789.59 | TRUE | INCLUDE
WO-00212 | Cleaning – Instrument/Analyser INST-0105 | INST-0105 | 2 | 4 | 3 |  | FALSE | 3957 | 18374.25 | 6.1 | 2 | 2 | 5.7 | 15.8 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -16934.25 | FALSE | DEFER
WO-00213 | Replacement – Instrument/Analyser INST-0163 | INST-0163 | 6 | 4 | 3 |  | FALSE | 2681 | 89820.11 | 53.7 | 16.7 | 20.2 | 5.2 | 95.8 | 12 | 1.8 | 730 | 0.93183 | 730 | 2 | 5 | 2 | 10 | 1341.83 | -88478.28 | FALSE | DEFER
WO-00214 | Calibration – Electrical Equipment ELEC-0014 | ELEC-0014 | 1 | 4 | 3 |  | FALSE | 3002 | 570.86 | 0.2 | 8.2 | 14 | 0.5 | 22.9 | 3 | 2 | 1460 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | 5975.81 | 5404.95 | TRUE | INCLUDE
WO-00215 | Cleaning – Instrument/Analyser INST-0098 | INST-0098 | 2 | 3 | 3 |  | FALSE | 3588 | 10507.52 | 13.9 | 1.2 | 1.5 | 6.5 | 23.1 | 3 | 1.8 | 730 | 0.96482 | 730 | 2 | 5 | 2 | 10 | 1389.33 | -9118.19 | FALSE | DEFER
WO-00216 | Calibration – Centrifugal Pump PMP-0032 | PMP-0032 | 1 | 1 | 3 |  | FALSE | 1838 | 2174.74 | 1.7 | 2.5 | 16.1 | 0.5 | 20.8 | 3 | 2.5 | 1825 | 0.44181 | 709.705 | 3 | 4 | 3 | 12 | 9543.04 | 7368.3 | TRUE | INCLUDE
WO-00217 | Calibration – Pressure Vessel VSL-0014 | VSL-0014 | 1 | 1 | 3 |  | TRUE | 2625 | 2206.31 | 1 | 8.4 | 8.8 | 0.2 | 18.4 | 2 | 2.8 | 3650 | 0.16034 | 2291.4951 | 5 | 3 | 5 | 15 | 34874.61 | 32668.3 | TRUE | INCLUDE
WO-00218 | Overhaul – Heat Exchanger HX-0009 | HX-0009 | 4 | 1 | 3 |  | FALSE | 3334 | 422121.16 | 209.1 | 38.3 | 15.3 | 11.3 | 274 | 34 | 2 | 2190 | 0.41447 | 2190 | 4 | 4 | 4 | 16 | 48492.86 | -373628.3 | FALSE | DEFER
WO-00219 | Calibration – Instrument/Analyser INST-0025 | INST-0025 | 1 | 2 | 3 |  | FALSE | 2551 | 894.88 | 1.1 | 8.3 | 14.7 | 0.3 | 24.4 | 3 | 1.8 | 730 | 0.9248 | 730 | 2 | 5 | 2 | 10 | 1331.72 | 436.84 | TRUE | INCLUDE
WO-00220 | Cleaning – Heat Exchanger HX-0010 | HX-0010 | 2 | 1 | 3 |  | TRUE | 3384 | 14187.23 | 6.3 | 1.7 | 1 | 5.8 | 14.8 | 2 | 2 | 2190 | 0.41891 | 2190 | 4 | 4 | 4 | 16 | 49012.24 | 34825.01 | TRUE | INCLUDE
WO-00221 | Replacement – Instrument/Analyser INST-0025 | INST-0025 | 6 | 4 | 3 |  | FALSE | 2551 | 43274.86 | 22.1 | 12.2 | 13.2 | 9 | 56.5 | 7 | 1.8 | 730 | 0.9248 | 730 | 2 | 5 | 2 | 10 | 1331.72 | -41943.14 | FALSE | DEFER
WO-00222 | Replacement – Control Valve VLV-0082 | VLV-0082 | 6 | 2 | 3 |  | FALSE | 2822 | 16512.12 | 48.8 | 19.9 | 21.3 | 1.2 | 91.2 | 11 | 1.5 | 1095 | 0.56312 | 1095 | 2.65 | 4 | 3 | 12 | 3021.85 | -13490.27 | FALSE | DEFER
WO-00223 | Inspection – Centrifugal Pump PMP-0013 | PMP-0013 | 3 | 2 | 3 |  | FALSE | 4594 | 6673.77 | 6.7 | 1 | 3.2 | 0.3 | 11.2 | 1 | 2.5 | 1825 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | 19000.78 | 12327.01 | TRUE | INCLUDE
WO-00224 | Inspection – Centrifugal Pump PMP-0078 | PMP-0078 | 3 | 3 | 3 |  | FALSE | 4241 | 5380.49 | 7.9 | 1.3 | 2.3 | 0.8 | 12.3 | 2 | 2.5 | 1825 | 0.8485 | 1825 | 3 | 5 | 3 | 15 | 18327.69 | 12947.2 | TRUE | INCLUDE
WO-00225 | Inspection – Instrument/Analyser INST-0021 | INST-0021 | 3 | 2 | 3 |  | FALSE | 2429 | 2044.07 | 7.1 | 0.6 | 1.5 | 0.2 | 9.4 | 1 | 1.8 | 730 | 0.91749 | 730 | 2 | 5 | 2 | 10 | 1321.18 | -722.89 | FALSE | DEFER
WO-00226 | Overhaul – Centrifugal Pump PMP-0050 | PMP-0050 | 4 | 1 | 2 |  | TRUE | 662 | 370320.49 | 75.3 | 37.9 | 19.8 | 10.2 | 143.2 | 18 | 2.5 | 1825 | 0.14641 | 1885.705 | 3 | 2 | 3 | 6 | 3162.56 | -367157.93 | TRUE | INCLUDE
WO-00227 | Calibration – Electrical Equipment ELEC-0061 | ELEC-0061 | 1 | 4 | 3 |  | FALSE | 4139 | 2887.48 | 1 | 2.3 | 8.2 | 0.2 | 11.7 | 1 | 2 | 1460 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | 6951.19 | 4063.71 | TRUE | INCLUDE
WO-00228 | Inspection – Instrument/Analyser INST-0180 | INST-0180 | 3 | 3 | 3 |  | FALSE | 2605 | 7751.92 | 6.7 | 1 | 4.4 | 0 | 12.1 | 2 | 1.8 | 730 | 0.92781 | 730 | 2 | 5 | 2 | 10 | 1336.05 | -6415.87 | FALSE | DEFER
WO-00229 | Inspection – Instrument/Analyser INST-0149 | INST-0149 | 3 | 2 | 3 |  | FALSE | 1323 | 6821.76 | 6.2 | 0.1 | 4.3 | 0 | 10.6 | 1 | 1.8 | 730 | 0.79917 | 730 | 2 | 5 | 2 | 10 | 1150.81 | -5670.95 | FALSE | DEFER
WO-00230 | Calibration – Heat Exchanger HX-0028 | HX-0028 | 1 | 1 | 3 |  | TRUE | 5045 | 1501.64 | 1.8 | 7.1 | 14 | 0.3 | 23.2 | 3 | 2 | 2190 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | 64199.97 | 62698.33 | TRUE | INCLUDE
WO-00231 | Testing – Electrical Equipment ELEC-0023 | ELEC-0023 | 7 | 3 | 2 | WO-00197 | FALSE | 371 | 2019.57 | 11.5 | 9.5 | 9.3 | 1.2 | 31.5 | 4 | 2 | 1460 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | 1554.05 | -465.52 | FALSE | DEFER
WO-00232 | Calibration – Instrument/Analyser INST-0103 | INST-0103 | 1 | 2 | 3 |  | FALSE | 3423 | 2632.64 | 0.6 | 5.7 | 4.1 | 0.7 | 11.1 | 1 | 1.8 | 730 | 0.96042 | 730 | 2 | 5 | 2 | 10 | 1383.01 | -1249.63 | FALSE | DEFER
WO-00233 | Cleaning – Control Valve VLV-0111 | VLV-0111 | 2 | 4 | 3 | WO-00167 | FALSE | 2504 | 5063.21 | 23.7 | 1.6 | 1.8 | 2.4 | 29.5 | 4 | 1.5 | 1095 | 0.54298 | 1095 | 2.65 | 4 | 3 | 12 | 2913.75 | -2149.46 | FALSE | DEFER
WO-00234 | Replacement – Centrifugal Pump PMP-0001 | PMP-0001 | 6 | 1 | 3 |  | TRUE | 4319 | 40584.87 | 21 | 6.8 | 15.1 | 3.2 | 46.1 | 6 | 2.5 | 1825 | 0.85591 | 1825 | 3 | 5 | 3 | 15 | 18487.66 | -22097.21 | TRUE | INCLUDE
WO-00235 | Cleaning – Instrument/Analyser INST-0037 | INST-0037 | 2 | 1 | 3 |  | TRUE | 4388 | 21064.63 | 20.6 | 1.2 | 0.3 | 8.5 | 30.6 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -19624.63 | TRUE | INCLUDE
WO-00236 | Replacement – Electrical Equipment ELEC-0023 | ELEC-0023 | 6 | 3 | 2 | WO-00203 | FALSE | 371 | 11561.78 | 42.7 | 8.6 | 17 | 4.1 | 72.4 | 9 | 2 | 1460 | 0.17267 | 1844.4436 | 2.5 | 3 | 2 | 6 | 1554.05 | -10007.73 | FALSE | DEFER
WO-00237 | Overhaul – Centrifugal Pump PMP-0021 | PMP-0021 | 4 | 2 | 3 |  | FALSE | 4170 | 41664.68 | 126 | 34.9 | 30.9 | 5.5 | 197.3 | 25 | 2.5 | 1825 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | 18176.25 | -23488.43 | FALSE | DEFER
WO-00238 | Replacement – Centrifugal Pump PMP-0033 | PMP-0033 | 6 | 1 | 3 |  | FALSE | 3852 | 6660 | 16.1 | 11 | 10.2 | 7.2 | 44.5 | 6 | 2.5 | 1825 | 0.80677 | 1825 | 3 | 5 | 3 | 15 | 17426.28 | 10766.28 | TRUE | INCLUDE
WO-00239 | Calibration – Control Valve VLV-0106 | VLV-0106 | 1 | 3 | 3 | WO-00048 | FALSE | 4449 | 1002.14 | 1.2 | 8.4 | 10.2 | 0 | 19.8 | 2 | 1.5 | 1095 | 0.64237 | 1095 | 2.65 | 5 | 3 | 15 | 3447.09 | 2444.95 | FALSE | DEFER
WO-00240 | Testing – Instrument/Analyser INST-0026 | INST-0026 | 7 | 3 | 3 |  | FALSE | 3487 | 14550.38 | 6 | 19.1 | 10.9 | 0.3 | 36.3 | 5 | 1.8 | 730 | 0.96219 | 730 | 2 | 5 | 2 | 10 | 1385.56 | -13164.82 | FALSE | DEFER
WO-00241 | Overhaul – Instrument/Analyser INST-0003 | INST-0003 | 4 | 1 | 3 |  | FALSE | 1351 | 330449.88 | 205.5 | 22.1 | 36 | 11.3 | 274.9 | 34 | 1.8 | 730 | 0.80391 | 730 | 2 | 5 | 2 | 10 | 1157.63 | -329292.25 | FALSE | DEFER
WO-00242 | Replacement – Pressure Vessel VSL-0013 | VSL-0013 | 6 | 4 | 3 |  | FALSE | 2708 | 114253.96 | 33.1 | 3.9 | 17.8 | 9.7 | 64.5 | 8 | 2.8 | 3650 | 0.1682 | 2208.4953 | 5 | 3 | 5 | 15 | 36583.08 | -77670.88 | FALSE | DEFER
WO-00243 | Cleaning – Control Valve VLV-0026 | VLV-0026 | 2 | 3 | 3 |  | FALSE | 4375 | 10030.74 | 17.9 | 1.6 | 1.7 | 8.6 | 29.8 | 4 | 1.5 | 1095 | 0.6394 | 1095 | 2.65 | 5 | 3 | 15 | 3431.19 | -6599.55 | FALSE | DEFER
WO-00244 | Inspection – Centrifugal Pump PMP-0038 | PMP-0038 | 3 | 3 | 3 |  | FALSE | 2710 | 4811.88 | 3.3 | 0.1 | 3 | 0.7 | 7.1 | 1 | 2.5 | 1825 | 0.63144 | 1825 | 3 | 5 | 3 | 15 | 13639.2 | 8827.32 | TRUE | INCLUDE
WO-00245 | Calibration – Centrifugal Pump PMP-0020 | PMP-0020 | 1 | 1 | 3 |  | FALSE | 3855 | 2600.27 | 1.5 | 7.6 | 4.2 | 0.6 | 13.9 | 2 | 2.5 | 1825 | 0.80713 | 1825 | 3 | 5 | 3 | 15 | 17433.92 | 14833.65 | TRUE | INCLUDE
WO-00246 | Inspection – Centrifugal Pump PMP-0062 | PMP-0062 | 3 | 3 | 3 |  | FALSE | 2644 | 1757.45 | 8.6 | 1.5 | 4.8 | 1 | 15.9 | 2 | 2.5 | 1825 | 0.61872 | 1825 | 3 | 5 | 3 | 15 | 13364.33 | 11606.88 | TRUE | INCLUDE
WO-00247 | Inspection – Instrument/Analyser INST-0138 | INST-0138 | 3 | 4 | 3 |  | FALSE | 4750 | 7100.03 | 8.7 | 1.7 | 1.6 | 0.1 | 12.1 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -5660.03 | FALSE | DEFER
WO-00248 | Inspection – Electrical Equipment ELEC-0017 | ELEC-0017 | 3 | 4 | 2 |  | FALSE | 674 | 3327.8 | 5.6 | 0.2 | 1.1 | 1 | 7.9 | 1 | 2 | 1460 | 0.25422 | 1541.4436 | 2.5 | 3 | 2 | 6 | 2287.96 | -1039.84 | FALSE | DEFER
WO-00249 | Repair – Pressure Vessel VSL-0019 | VSL-0019 | 5 | 3 | 4 |  | FALSE | 4641 | 24195.92 | 28.2 | 15.1 | 10.2 | 1.1 | 54.6 | 7 | 2.8 | 3650 | 0.37037 | 275.4953 | 5 | 4 | 5 | 20 | 80556.21 | 56360.29 | TRUE | INCLUDE
WO-00250 | Testing – Centrifugal Pump PMP-0049 | PMP-0049 | 7 | 2 | 3 |  | FALSE | 4725 | 8166.02 | 9 | 11.9 | 5.9 | 0.5 | 27.3 | 3 | 2.5 | 1825 | 0.88977 | 1825 | 3 | 5 | 3 | 15 | 19218.98 | 11052.96 | TRUE | INCLUDE
WO-00251 | Overhaul – Pressure Vessel VSL-0006 | VSL-0006 | 4 | 1 | 4 |  | TRUE | 5225 | 333845.33 | 209.8 | 17.5 | 9.2 | 4.8 | 241.3 | 30 | 2.8 | 3650 | 0.43349 | 3650 | 5 | 4 | 5 | 20 | 94283.4 | -239561.93 | TRUE | INCLUDE
WO-00252 | Cleaning – Piping/Pipeline Segment PPL-0037 | PPL-0037 | 2 | 2 | 3 |  | FALSE | 4687 | 20396.44 | 25.3 | 1.3 | 0.8 | 3.2 | 30.6 | 4 | 2 | 3285 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | 13521.8 | -6874.64 | FALSE | DEFER
WO-00253 | Replacement – Control Valve VLV-0023 | VLV-0023 | 6 | 4 | 3 |  | FALSE | 3410 | 105052.98 | 33.3 | 6.1 | 9.8 | 2.2 | 51.4 | 6 | 1.5 | 1095 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | 3196.58 | -101856.4 | FALSE | DEFER
WO-00254 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | 3 | 2 | 3 |  | FALSE | 4371 | 695.06 | 3.5 | 1.6 | 3.1 | 0.6 | 8.8 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 744.94 | TRUE | INCLUDE
WO-00255 | Inspection – Instrument/Analyser INST-0043 | INST-0043 | 3 | 1 | 3 |  | FALSE | 2938 | 6935.57 | 3.5 | 0.1 | 3.3 | 0.1 | 7 | 1 | 1.8 | 730 | 0.94369 | 730 | 2 | 5 | 2 | 10 | 1358.91 | -5576.66 | FALSE | DEFER
WO-00256 | Calibration – Control Valve VLV-0073 | VLV-0073 | 1 | 2 | 3 |  | FALSE | 1726 | 1576.51 | 0.5 | 4.8 | 15.7 | 0.1 | 21.1 | 3 | 1.5 | 1095 | 0.48307 | 183.3751 | 2.65 | 4 | 3 | 12 | 2592.27 | 1015.76 | TRUE | INCLUDE
WO-00257 | Cleaning – Pressure Vessel VSL-0020 | VSL-0020 | 2 | 2 | 2 |  | FALSE | 908 | 15567.32 | 27.3 | 0.7 | 0.1 | 6.3 | 34.4 | 4 | 2.8 | 3650 | 0.03153 | 4008.4951 | 5 | 1 | 5 | 5 | 6857.86 | -8709.46 | FALSE | DEFER
WO-00258 | Inspection – Instrument/Analyser INST-0001 | INST-0001 | 3 | 4 | 3 |  | FALSE | 4714 | 4691.18 | 3.6 | 1.7 | 4.3 | 0.4 | 10 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -3251.18 | FALSE | DEFER
WO-00259 | Testing – Instrument/Analyser INST-0003 | INST-0003 | 7 | 2 | 3 |  | FALSE | 1351 | 2374.14 | 8.6 | 16 | 5.7 | 0.8 | 31.1 | 4 | 1.8 | 730 | 0.80391 | 730 | 2 | 5 | 2 | 10 | 1157.63 | -1216.51 | FALSE | DEFER
WO-00260 | Testing – Instrument/Analyser INST-0155 | INST-0155 | 7 | 1 | 3 |  | FALSE | 3302 | 6467.99 | 15.7 | 11.7 | 6.6 | 1.7 | 35.7 | 4 | 1.8 | 730 | 0.95682 | 730 | 2 | 5 | 2 | 10 | 1377.82 | -5090.17 | FALSE | DEFER
WO-00261 | Inspection – Instrument/Analyser INST-0069 | INST-0069 | 3 | 2 | 3 |  | FALSE | 4652 | 3296.44 | 7.5 | 0.7 | 1.3 | 0.3 | 9.8 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -1856.44 | FALSE | DEFER
WO-00262 | Inspection – Centrifugal Pump PMP-0034 | PMP-0034 | 3 | 1 | 2 |  | FALSE | 1386 | 4557.53 | 2.9 | 0.6 | 3.6 | 0.7 | 7.8 | 1 | 2.5 | 1825 | 0.32905 | 1161.7051 | 3 | 3 | 3 | 9 | 7107.46 | 2549.93 | TRUE | INCLUDE
WO-00263 | Replacement – Centrifugal Pump PMP-0004 | PMP-0004 | 6 | 1 | 3 |  | TRUE | 5350 | 33394.56 | 57.8 | 5.4 | 7.7 | 5 | 75.9 | 9 | 2.5 | 1825 | 0.9286 | 1825 | 3 | 5 | 3 | 15 | 20057.78 | -13336.78 | TRUE | INCLUDE
WO-00264 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | 3 | 1 | 3 |  | FALSE | 2814 | 1309.51 | 7.1 | 1.2 | 3.6 | 0.8 | 12.7 | 2 | 2.8 | 3650 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | 38798.52 | 37489.01 | TRUE | INCLUDE
WO-00265 | Repair – Storage Tank TNK-0008 | TNK-0008 | 5 | 2 | 1 |  | FALSE | 1128 | 59189.96 | 82 | 22.7 | 8.5 | 3.5 | 116.7 | 15 | 3.5 | 5475 | 0.0065979 | 5820.2324 | 4 | 1 | 4 | 4 | 1543.9 | -57646.06 | FALSE | DEFER
WO-00266 | Inspection – Centrifugal Pump PMP-0023 | PMP-0023 | 3 | 2 | 3 |  | FALSE | 2258 | 3939.48 | 2.3 | 0 | 4.7 | 0.7 | 7.7 | 1 | 2.5 | 1825 | 0.53872 | 289.705 | 3 | 4 | 3 | 12 | 11636.29 | 7696.81 | TRUE | INCLUDE
WO-00267 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | 6 | 1 | 3 |  | TRUE | 3222 | 70611.87 | 54.4 | 13.7 | 16 | 5.1 | 89.2 | 11 | 2.5 | 1825 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | 15560.77 | -55051.1 | TRUE | INCLUDE
WO-00268 | Calibration – Instrument/Analyser INST-0131 | INST-0131 | 1 | 4 | 3 |  | FALSE | 923 | 2946.75 | 0.8 | 5.1 | 10.8 | 0.4 | 17.1 | 2 | 1.8 | 730 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | 1028.86 | -1917.89 | FALSE | DEFER
WO-00269 | Calibration – Pressure Vessel VSL-0028 | VSL-0028 | 1 | 3 | 3 |  | FALSE | 3718 | 1205.72 | 0.7 | 5.4 | 4.6 | 0.5 | 11.2 | 1 | 2.8 | 3650 | 0.27072 | 1198.4951 | 5 | 3 | 5 | 15 | 58882.1 | 57676.38 | TRUE | INCLUDE
WO-00270 | Cleaning – Control Valve VLV-0011 | VLV-0011 | 2 | 3 | 3 |  | FALSE | 4141 | 5762.1 | 21.5 | 1.4 | 0.5 | 7 | 30.4 | 4 | 1.5 | 1095 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | 3379.15 | -2382.95 | FALSE | DEFER
WO-00271 | Repair – Reciprocating Compressor CMP-0015 | CMP-0015 | 5 | 3 | 4 |  | FALSE | 1148 | 12613.64 | 25.9 | 16.6 | 2.8 | 4.7 | 50 | 6 | 3 | 1460 | 0.46568 | 779.9307 | 4.75 | 4 | 5 | 20 | 162580.25 | 149966.61 | TRUE | INCLUDE
WO-00272 | Inspection – Instrument/Analyser INST-0122 | INST-0122 | 3 | 2 | 3 |  | FALSE | 2867 | 4003.62 | 9.9 | 1 | 3 | 0.6 | 14.5 | 2 | 1.8 | 730 | 0.94066 | 730 | 2 | 5 | 2 | 10 | 1354.54 | -2649.08 | FALSE | DEFER
WO-00273 | Inspection – Instrument/Analyser INST-0034 | INST-0034 | 3 | 1 | 3 |  | FALSE | 3256 | 5612.42 | 5.2 | 0.6 | 1.1 | 0.8 | 7.7 | 1 | 1.8 | 730 | 0.95536 | 730 | 2 | 5 | 2 | 10 | 1375.72 | -4236.7 | FALSE | DEFER
WO-00274 | Calibration – Instrument/Analyser INST-0105 | INST-0105 | 1 | 3 | 3 |  | FALSE | 3957 | 1269.57 | 1.2 | 4 | 6.5 | 0.5 | 12.2 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 170.43 | FALSE | DEFER
WO-00275 | Inspection – Control Valve VLV-0042 | VLV-0042 | 3 | 3 | 3 |  | FALSE | 4579 | 3829.06 | 5.6 | 0.4 | 3.3 | 0.1 | 9.4 | 1 | 1.5 | 1095 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | 3474.41 | -354.65 | FALSE | DEFER
WO-00276 | Inspection – Instrument/Analyser INST-0035 | INST-0035 | 3 | 3 | 3 |  | FALSE | 3676 | 4193.01 | 4.5 | 0.9 | 2.7 | 0.9 | 9 | 1 | 1.8 | 730 | 0.96694 | 730 | 2 | 5 | 2 | 10 | 1392.4 | -2800.61 | FALSE | DEFER
WO-00277 | Calibration – Electrical Equipment ELEC-0063 | ELEC-0063 | 1 | 4 | 3 |  | FALSE | 3399 | 831.83 | 0.7 | 2.6 | 10.7 | 0.7 | 14.7 | 2 | 2 | 1460 | 0.70669 | 1460 | 2.5 | 5 | 2 | 10 | 6360.25 | 5528.42 | TRUE | INCLUDE
WO-00278 | Cleaning – Control Valve VLV-0065 | VLV-0065 | 2 | 1 | 3 |  | TRUE | 5370 | 16361.74 | 8.3 | 0.1 | 1.6 | 3.3 | 13.3 | 2 | 1.5 | 1095 | 0.67563 | 1095 | 2.65 | 5 | 3 | 15 | 3625.6 | -12736.14 | TRUE | INCLUDE
WO-00279 | Testing – Control Valve VLV-0114 | VLV-0114 | 7 | 3 | 3 |  | FALSE | 4955 | 14471.06 | 13.1 | 11.6 | 20.7 | 0.4 | 45.8 | 6 | 1.5 | 1095 | 0.66141 | 1095 | 2.65 | 5 | 3 | 15 | 3549.3 | -10921.76 | FALSE | DEFER
WO-00280 | Replacement – Heat Exchanger HX-0023 | HX-0023 | 6 | 1 | 3 |  | FALSE | 3196 | 109960.5 | 55.8 | 13.7 | 6.2 | 5.3 | 81 | 10 | 2 | 2190 | 0.40204 | 127.1654 | 4 | 4 | 4 | 16 | 47038.68 | -62921.82 | FALSE | DEFER
WO-00281 | Repair – Instrument/Analyser INST-0105 | INST-0105 | 5 | 1 | 3 |  | TRUE | 3957 | 12795.42 | 13 | 22.3 | 10.2 | 8.5 | 54 | 7 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -11355.42 | TRUE | INCLUDE
WO-00282 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | 1 | 1 | 3 |  | TRUE | 4170 | 304.54 | 0.1 | 5.7 | 7.5 | 0.6 | 13.9 | 2 | 2.5 | 1825 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | 18176.25 | 17871.71 | TRUE | INCLUDE
WO-00283 | Inspection – Control Valve VLV-0023 | VLV-0023 | 3 | 3 | 3 |  | FALSE | 3410 | 5980.9 | 3.7 | 1.3 | 4 | 0.1 | 9.1 | 1 | 1.5 | 1095 | 0.59568 | 1095 | 2.65 | 4 | 3 | 12 | 3196.58 | -2784.32 | FALSE | DEFER
WO-00284 | Replacement – Instrument/Analyser INST-0152 | INST-0152 | 6 | 4 | 3 |  | FALSE | 4490 | 49797.79 | 12.5 | 17.1 | 15.2 | 5.5 | 50.3 | 6 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -48357.79 | FALSE | DEFER
WO-00285 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | 6 | 1 | 3 |  | FALSE | 4594 | 107439.62 | 45.4 | 18.7 | 22.2 | 9.9 | 96.2 | 12 | 2.5 | 1825 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | 19000.78 | -88438.84 | FALSE | DEFER
WO-00286 | Calibration – Piping/Pipeline Segment PPL-0039 | PPL-0039 | 1 | 2 | 2 |  | FALSE | 1209 | 2452.58 | 1.3 | 4.2 | 19.4 | 0.2 | 25.1 | 3 | 2 | 3285 | 0.089837 | 3775.7481 | 3.65 | 2 | 4 | 8 | 4328.35 | 1875.77 | TRUE | INCLUDE
WO-00287 | Cleaning – Control Valve VLV-0119 | VLV-0119 | 2 | 2 | 3 |  | FALSE | 2602 | 4883.9 | 21.3 | 0.2 | 1.4 | 8.8 | 31.7 | 4 | 1.5 | 1095 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | 2948.24 | -1935.66 | FALSE | DEFER
WO-00288 | Calibration – Control Valve VLV-0116 | VLV-0116 | 1 | 3 | 3 |  | FALSE | 2226 | 638.97 | 1.7 | 9.6 | 6.4 | 0.7 | 18.4 | 2 | 1.5 | 1095 | 0.52354 | 1095 | 2.65 | 4 | 3 | 12 | 2809.43 | 2170.46 | TRUE | INCLUDE
WO-00289 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | 2 | 4 | 3 |  | FALSE | 4894 | 17955.75 | 15.7 | 1.2 | 0.5 | 5 | 22.4 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -16515.75 | FALSE | DEFER
WO-00290 | Inspection – Instrument/Analyser INST-0106 | INST-0106 | 3 | 2 | 3 |  | FALSE | 3603 | 5022.06 | 3.5 | 1.7 | 3.3 | 0.4 | 8.9 | 1 | 1.8 | 730 | 0.96519 | 730 | 2 | 5 | 2 | 10 | 1389.87 | -3632.19 | FALSE | DEFER
WO-00291 | Overhaul – Distillation Tower TWR-0006 | TWR-0006 | 4 | 2 | 4 |  | FALSE | 4457 | 575203.21 | 141.8 | 27.7 | 39.3 | 11.6 | 220.4 | 28 | 2.2 | 2920 | 0.38082 | 2920 | 5 | 4 | 5 | 20 | 279904.94 | -295298.27 | FALSE | DEFER
WO-00292 | Replacement – Electrical Equipment ELEC-0078 | ELEC-0078 | 6 | 3 | 2 |  | FALSE | 457 | 22355.77 | 45.1 | 17.7 | 22.1 | 8.9 | 93.8 | 12 | 2 | 1460 | 0.19668 | 1758.4434 | 2.5 | 3 | 2 | 6 | 1770.15 | -20585.62 | FALSE | DEFER
WO-00293 | Replacement – Piping/Pipeline Segment PPL-0022 | PPL-0022 | 6 | 3 | 3 |  | FALSE | 3032 | 78361.23 | 57.6 | 15.1 | 13.9 | 7.2 | 93.8 | 12 | 2 | 3285 | 0.19543 | 1952.7481 | 3.65 | 3 | 4 | 12 | 9416.04 | -68945.19 | FALSE | DEFER
WO-00294 | Repair – Reciprocating Compressor CMP-0010 | CMP-0010 | 5 | 4 | 4 |  | FALSE | 2274 | 61530.83 | 47.9 | 11.1 | 11 | 4 | 74 | 9 | 3 | 1460 | 0.88082 | 1460 | 4.75 | 5 | 5 | 25 | 307515.33 | 245984.5 | TRUE | INCLUDE
WO-00295 | Overhaul – Instrument/Analyser INST-0148 | INST-0148 | 4 | 4 | 3 |  | FALSE | 1769 | 291152.96 | 109.6 | 34.9 | 29.8 | 6.6 | 180.9 | 23 | 1.8 | 730 | 0.86137 | 730 | 2 | 5 | 2 | 10 | 1240.37 | -289912.59 | FALSE | DEFER
WO-00296 | Replacement – Control Valve VLV-0055 | VLV-0055 | 6 | 1 | 3 |  | TRUE | 1292 | 54746.52 | 18.7 | 12 | 18 | 8.9 | 57.6 | 7 | 1.5 | 1095 | 0.44001 | 617.3751 | 2.65 | 4 | 3 | 12 | 2361.21 | -52385.31 | TRUE | INCLUDE
WO-00297 | Testing – Piping/Pipeline Segment PPL-0043 | PPL-0043 | 7 | 1 | 2 |  | FALSE | 1877 | 10705.36 | 7.1 | 8.1 | 9.9 | 1.8 | 26.9 | 3 | 2 | 3285 | 0.13005 | 3107.7481 | 3.65 | 2 | 4 | 8 | 6265.83 | -4439.53 | FALSE | DEFER
WO-00298 | Overhaul – Control Valve VLV-0025 | VLV-0025 | 4 | 4 | 3 |  | FALSE | 2753 | 427856.76 | 214.4 | 35.7 | 39.6 | 7.5 | 297.2 | 37 | 1.5 | 1095 | 0.55892 | 1095 | 2.65 | 4 | 3 | 12 | 2999.3 | -424857.46 | FALSE | DEFER
WO-00299 | Replacement – Control Valve VLV-0051 | VLV-0051 | 6 | 2 | 3 |  | FALSE | 2376 | 19763.49 | 58.8 | 5.6 | 6.7 | 6.6 | 77.7 | 10 | 1.5 | 1095 | 0.53426 | 1095 | 2.65 | 4 | 3 | 12 | 2866.96 | -16896.53 | FALSE | DEFER
WO-00300 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | 3 | 4 | 3 |  | FALSE | 4490 | 5048.3 | 8.1 | 1.6 | 1.6 | 0.6 | 11.9 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -3608.3 | FALSE | DEFER
WO-00301 | Inspection – Electrical Equipment ELEC-0019 | ELEC-0019 | 3 | 4 | 2 |  | FALSE | 1908 | 2136.85 | 2 | 1 | 1.8 | 0.7 | 5.5 | 1 | 2 | 1460 | 0.51126 | 307.4436 | 2.5 | 4 | 2 | 8 | 4601.34 | 2464.49 | TRUE | INCLUDE
WO-00302 | Replacement – Heat Exchanger HX-0001 | HX-0001 | 6 | 4 | 3 |  | FALSE | 3349 | 79646.16 | 19 | 2.3 | 19.2 | 4.9 | 45.4 | 6 | 2 | 2190 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | 48649.09 | -30997.07 | FALSE | DEFER
WO-00303 | Cleaning – Instrument/Analyser INST-0054 | INST-0054 | 2 | 2 | 3 |  | FALSE | 4591 | 4779.59 | 14.8 | 0.4 | 1.8 | 7.5 | 24.5 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -3339.59 | FALSE | DEFER
WO-00304 | Cleaning – Control Valve VLV-0083 | VLV-0083 | 2 | 2 | 3 |  | FALSE | 3101 | 17067.52 | 22.8 | 0.2 | 0 | 2.9 | 25.9 | 3 | 1.5 | 1095 | 0.57925 | 1095 | 2.65 | 4 | 3 | 12 | 3108.4 | -13959.12 | FALSE | DEFER
WO-00305 | Overhaul – Instrument/Analyser INST-0089 | INST-0089 | 4 | 3 | 3 |  | FALSE | 2830 | 94830.05 | 122.2 | 26.5 | 12.6 | 22.3 | 183.6 | 23 | 1.8 | 730 | 0.939 | 730 | 2 | 5 | 2 | 10 | 1352.17 | -93477.88 | FALSE | DEFER
WO-00306 | Replacement – Instrument/Analyser INST-0054 | INST-0054 | 6 | 4 | 3 |  | FALSE | 4591 | 63294.33 | 24.3 | 17.4 | 15.5 | 5.5 | 62.7 | 8 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -61854.33 | FALSE | DEFER
WO-00307 | Repair – Piping/Pipeline Segment PPL-0037 | PPL-0037 | 5 | 2 | 3 |  | FALSE | 4687 | 65398.55 | 28.8 | 8 | 14.4 | 5.2 | 56.4 | 7 | 2 | 3285 | 0.28065 | 297.7481 | 3.65 | 3 | 4 | 12 | 13521.8 | -51876.75 | FALSE | DEFER
WO-00308 | Calibration – Piping/Pipeline Segment PPL-0004 | PPL-0004 | 1 | 3 | 3 |  | FALSE | 5368 | 1026.88 | 0.6 | 5.9 | 8.4 | 0.7 | 15.6 | 2 | 2 | 3285 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | 15082.22 | 14055.34 | TRUE | INCLUDE
WO-00309 | Overhaul – Instrument/Analyser INST-0115 | INST-0115 | 4 | 3 | 3 | WO-00188 | FALSE | 3707 | 438422.86 | 142.1 | 37.9 | 17.4 | 18.8 | 216.2 | 27 | 1.8 | 730 | 0.96766 | 730 | 2 | 5 | 2 | 10 | 1393.43 | -437029.43 | FALSE | DEFER
WO-00310 | Replacement – Instrument/Analyser INST-0131 | INST-0131 | 6 | 4 | 3 |  | FALSE | 923 | 68936.66 | 52.5 | 6.5 | 18.7 | 9.6 | 87.3 | 11 | 1.8 | 730 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | 1028.86 | -67907.8 | FALSE | DEFER
WO-00311 | Overhaul – Storage Tank TNK-0002 | TNK-0002 | 4 | 3 | 2 |  | FALSE | 2994 | 370216.52 | 238.4 | 31.9 | 12.8 | 4.9 | 288 | 36 | 3.5 | 5475 | 0.058188 | 3954.2322 | 4 | 2 | 4 | 8 | 13615.91 | -356600.61 | FALSE | DEFER
WO-00312 | Overhaul – Heat Exchanger HX-0035 | HX-0035 | 4 | 3 | 3 |  | FALSE | 2996 | 159385.54 | 109.5 | 39.8 | 27.5 | 21.4 | 198.2 | 25 | 2 | 2190 | 0.38356 | 327.1654 | 4 | 4 | 4 | 16 | 44876.21 | -114509.33 | FALSE | DEFER
WO-00313 | Testing – Instrument/Analyser INST-0160 | INST-0160 | 7 | 2 | 3 |  | FALSE | 1051 | 13383.3 | 6.6 | 17.2 | 4.4 | 2 | 30.2 | 4 | 1.8 | 730 | 0.74551 | 109.2559 | 2 | 5 | 2 | 10 | 1073.53 | -12309.77 | FALSE | DEFER
WO-00314 | Cleaning – Electrical Equipment ELEC-0009 | ELEC-0009 | 2 | 3 | 2 |  | FALSE | 548 | 21379.69 | 7.9 | 1.7 | 0 | 5.5 | 15.1 | 2 | 2 | 1460 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | 1991.99 | -19387.7 | FALSE | DEFER
WO-00315 | Replacement – Centrifugal Pump PMP-0080 | PMP-0080 | 6 | 3 | 3 |  | FALSE | 3570 | 72434.25 | 55.6 | 7.9 | 15.6 | 8.9 | 88 | 11 | 2.5 | 1825 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | 16656.59 | -55777.66 | FALSE | DEFER
WO-00316 | Inspection – Electrical Equipment ELEC-0077 | ELEC-0077 | 3 | 2 | 3 |  | FALSE | 4638 | 7576.65 | 2.4 | 1.2 | 3.3 | 0.8 | 7.7 | 1 | 2 | 1460 | 0.80811 | 1460 | 2.5 | 5 | 2 | 10 | 7273.03 | -303.62 | FALSE | DEFER
WO-00317 | Inspection – Instrument/Analyser INST-0143 | INST-0143 | 3 | 2 | 3 | WO-00231 | FALSE | 1579 | 6165.59 | 3.2 | 0.9 | 3.9 | 0.7 | 8.7 | 1 | 1.8 | 730 | 0.83804 | 730 | 2 | 5 | 2 | 10 | 1206.78 | -4958.81 | FALSE | DEFER
WO-00318 | Replacement – Control Valve VLV-0084 | VLV-0084 | 6 | 4 | 3 |  | FALSE | 4701 | 116432.11 | 31.3 | 2.8 | 8.4 | 4.1 | 46.6 | 6 | 1.5 | 1095 | 0.6521 | 1095 | 2.65 | 5 | 3 | 15 | 3499.35 | -112932.76 | FALSE | DEFER
WO-00319 | Replacement – Instrument/Analyser INST-0009 | INST-0009 | 6 | 3 | 3 |  | FALSE | 3990 | 8035.52 | 34.7 | 3.5 | 9.5 | 9.9 | 57.6 | 7 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -6595.52 | FALSE | DEFER
WO-00320 | Inspection – Instrument/Analyser INST-0013 | INST-0013 | 3 | 3 | 3 |  | FALSE | 4371 | 3920.28 | 3.4 | 0.2 | 3.3 | 0.5 | 7.4 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -2480.28 | FALSE | DEFER
WO-00321 | Repair – Storage Tank TNK-0015 | TNK-0015 | 5 | 1 | 1 |  | TRUE | 2301 | 21241.18 | 92.9 | 17.5 | 6.7 | 8.6 | 125.7 | 16 | 3.5 | 5475 | 0.031924 | 4647.2321 | 4 | 1 | 4 | 4 | 7470.16 | -13771.02 | TRUE | INCLUDE
WO-00322 | Cleaning – Piping/Pipeline Segment PPL-0026 | PPL-0026 | 2 | 1 | 3 |  | FALSE | 3699 | 18318.92 | 10.7 | 1.7 | 0.5 | 8.7 | 21.6 | 3 | 2 | 3285 | 0.23093 | 1285.7481 | 3.65 | 3 | 4 | 12 | 11126.23 | -7192.69 | FALSE | DEFER
WO-00323 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | 3 | 3 | 3 |  | FALSE | 2817 | 3419.29 | 8.8 | 0.3 | 4.5 | 0.2 | 13.8 | 2 | 2 | 1460 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | 5778.01 | 2358.72 | TRUE | INCLUDE
WO-00324 | Replacement – Instrument/Analyser INST-0114 | INST-0114 | 6 | 3 | 3 |  | FALSE | 2613 | 18584.52 | 57.1 | 9.9 | 17.8 | 6.2 | 91 | 11 | 1.8 | 730 | 0.92825 | 730 | 2 | 5 | 2 | 10 | 1336.68 | -17247.84 | FALSE | DEFER
WO-00325 | Cleaning – Centrifugal Pump PMP-0065 | PMP-0065 | 2 | 2 | 3 |  | FALSE | 2213 | 22560.22 | 20.8 | 1.1 | 1.3 | 6.9 | 30.1 | 4 | 2.5 | 1825 | 0.5288 | 334.705 | 3 | 4 | 3 | 12 | 11421.98 | -11138.24 | FALSE | DEFER
WO-00326 | Cleaning – Storage Tank TNK-0012 | TNK-0012 | 2 | 2 | 1 |  | FALSE | 1449 | 11645.68 | 22.2 | 1.9 | 1.9 | 8.6 | 34.6 | 4 | 3.5 | 5475 | 0.011334 | 5499.2321 | 4 | 1 | 4 | 4 | 2652.22 | -8993.46 | FALSE | DEFER
WO-00327 | Calibration – Heat Exchanger HX-0004 | HX-0004 | 1 | 3 | 3 |  | FALSE | 2889 | 698.54 | 1 | 4.1 | 4.1 | 1 | 10.2 | 1 | 2 | 2190 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | 43691.97 | 42993.43 | TRUE | INCLUDE
WO-00328 | Overhaul – Heat Exchanger HX-0024 | HX-0024 | 4 | 1 | 3 |  | FALSE | 3800 | 163679.09 | 178.6 | 26.3 | 41.7 | 24 | 270.6 | 34 | 2 | 2190 | 0.45456 | 2190 | 4 | 4 | 4 | 16 | 53183.64 | -110495.45 | FALSE | DEFER
WO-00329 | Replacement – Centrifugal Pump PMP-0044 | PMP-0044 | 6 | 1 | 3 | WO-00317 | FALSE | 3193 | 35748.99 | 12.9 | 9.1 | 4.3 | 2 | 28.3 | 4 | 2.5 | 1825 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | 15461.89 | -20287.1 | FALSE | DEFER
WO-00330 | Inspection – Piping/Pipeline Segment PPL-0013 | PPL-0013 | 3 | 1 | 3 |  | FALSE | 2292 | 6017.98 | 2.8 | 1.7 | 1.9 | 0.1 | 6.5 | 1 | 2 | 3285 | 0.15413 | 2692.7481 | 3.65 | 3 | 4 | 12 | 7426.16 | 1408.18 | TRUE | INCLUDE
WO-00331 | Calibration – Instrument/Analyser INST-0015 | INST-0015 | 1 | 3 | 3 |  | FALSE | 1106 | 918.53 | 1 | 2.9 | 19.8 | 0.1 | 23.8 | 3 | 1.8 | 730 | 0.7576 | 54.2559 | 2 | 5 | 2 | 10 | 1090.94 | 172.41 | FALSE | DEFER
WO-00332 | Repair – Control Valve VLV-0015 | VLV-0015 | 5 | 3 | 3 |  | FALSE | 2861 | 21101.18 | 32.6 | 25 | 6.9 | 1 | 65.5 | 8 | 1.5 | 1095 | 0.56546 | 1095 | 2.65 | 4 | 3 | 12 | 3034.38 | -18066.8 | FALSE | DEFER
WO-00333 | Inspection – Centrifugal Pump PMP-0051 | PMP-0051 | 3 | 2 | 3 |  | FALSE | 1802 | 7332.46 | 7.1 | 1.2 | 1.8 | 0.7 | 10.8 | 1 | 2.5 | 1825 | 0.43309 | 745.705 | 3 | 4 | 3 | 12 | 9354.8 | 2022.34 | FALSE | DEFER
WO-00334 | Inspection – Pressure Vessel VSL-0004 | VSL-0004 | 3 | 3 | 3 |  | FALSE | 2288 | 7118.26 | 6.6 | 1.6 | 2.1 | 0.1 | 10.4 | 1 | 2.8 | 3650 | 0.12966 | 2628.4951 | 5 | 2 | 5 | 10 | 28201.02 | 21082.76 | TRUE | INCLUDE
WO-00335 | Calibration – Instrument/Analyser INST-0158 | INST-0158 | 1 | 3 | 3 |  | FALSE | 2370 | 1280.89 | 0 | 8.5 | 7.3 | 0.3 | 16.1 | 2 | 1.8 | 730 | 0.91367 | 730 | 2 | 5 | 2 | 10 | 1315.69 | 34.8 | FALSE | DEFER
WO-00336 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | 3 | 4 | 3 | WO-00205 | FALSE | 4121 | 1132.77 | 2.2 | 1.8 | 2.2 | 0.7 | 6.9 | 1 | 2 | 3285 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | 12169.06 | 11036.29 | TRUE | INCLUDE
WO-00337 | Cleaning – Instrument/Analyser INST-0052 | INST-0052 | 2 | 3 | 3 |  | FALSE | 1968 | 13602.28 | 16.5 | 0.8 | 1.2 | 9.7 | 28.2 | 4 | 1.8 | 730 | 0.88183 | 730 | 2 | 5 | 2 | 10 | 1269.84 | -12332.44 | FALSE | DEFER
WO-00338 | Overhaul – Instrument/Analyser INST-0086 | INST-0086 | 4 | 3 | 3 |  | FALSE | 661 | 209480.22 | 216.7 | 13.7 | 43.7 | 9.1 | 283.2 | 35 | 1.8 | 730 | 0.63543 | 499.2559 | 2 | 5 | 2 | 10 | 915.02 | -208565.2 | FALSE | DEFER
WO-00339 | Calibration – Electrical Equipment ELEC-0048 | ELEC-0048 | 1 | 3 | 2 |  | FALSE | 1664 | 1535.59 | 0.4 | 8.8 | 9.9 | 0.3 | 19.4 | 2 | 2 | 1460 | 0.46867 | 551.4437 | 2.5 | 4 | 2 | 8 | 4217.99 | 2682.4 | TRUE | INCLUDE
WO-00340 | Overhaul – Storage Tank TNK-0004 | TNK-0004 | 4 | 2 | 2 |  | FALSE | 3023 | 414585.55 | 67.4 | 26.3 | 45.5 | 4.7 | 143.9 | 18 | 3.5 | 5475 | 0.059482 | 3925.2322 | 4 | 2 | 4 | 8 | 13918.82 | -400666.73 | FALSE | DEFER
WO-00341 | Cleaning – Control Valve VLV-0042 | VLV-0042 | 2 | 4 | 3 |  | FALSE | 4579 | 22305.07 | 18.3 | 1.6 | 0.4 | 4.8 | 25.1 | 3 | 1.5 | 1095 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | 3474.41 | -18830.66 | FALSE | DEFER
WO-00342 | Repair – Piping/Pipeline Segment PPL-0040 | PPL-0040 | 5 | 3 | 2 |  | FALSE | 1184 | 45520.33 | 51.7 | 15.7 | 3.1 | 9 | 79.5 | 10 | 2 | 3285 | 0.088296 | 3800.7482 | 3.65 | 2 | 4 | 8 | 4254.12 | -41266.21 | FALSE | DEFER
WO-00343 | Overhaul – Instrument/Analyser INST-0031 | INST-0031 | 4 | 2 | 3 |  | FALSE | 2503 | 178472.38 | 108.6 | 13.2 | 38.3 | 15.1 | 175.2 | 22 | 1.8 | 730 | 0.92201 | 730 | 2 | 5 | 2 | 10 | 1327.7 | -177144.68 | FALSE | DEFER
WO-00344 | Cleaning – Piping/Pipeline Segment PPL-0002 | PPL-0002 | 2 | 2 | 2 |  | FALSE | 1409 | 24501.53 | 6.9 | 0.9 | 1 | 3.3 | 12.1 | 2 | 2 | 3285 | 0.10207 | 3575.748 | 3.65 | 2 | 4 | 8 | 4917.64 | -19583.89 | FALSE | DEFER
WO-00345 | Cleaning – Centrifugal Pump PMP-0074 | PMP-0074 | 2 | 2 | 3 |  | FALSE | 2694 | 4776.27 | 7.7 | 1.7 | 0.6 | 7 | 17 | 2 | 2.5 | 1825 | 0.62839 | 1825 | 3 | 5 | 3 | 15 | 13573.13 | 8796.86 | TRUE | INCLUDE
WO-00346 | Repair – Centrifugal Pump PMP-0061 | PMP-0061 | 5 | 1 | 2 |  | TRUE | 1143 | 59711.78 | 85.3 | 20.3 | 10.1 | 4.5 | 120.2 | 15 | 2.5 | 1825 | 0.26672 | 1404.705 | 3 | 3 | 3 | 9 | 5761.08 | -53950.7 | TRUE | INCLUDE
WO-00347 | Overhaul – Electrical Equipment ELEC-0079 | ELEC-0079 | 4 | 3 | 2 |  | FALSE | 1546 | 90645.91 | 124.8 | 24.4 | 9.5 | 9.5 | 168.2 | 21 | 2 | 1460 | 0.44675 | 669.4437 | 2.5 | 4 | 2 | 8 | 4020.78 | -86625.13 | FALSE | DEFER
WO-00348 | Cleaning – Instrument/Analyser INST-0127 | INST-0127 | 2 | 4 | 3 |  | FALSE | 4463 | 20348.02 | 17 | 1.7 | 1.6 | 2.8 | 23.1 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -18908.02 | FALSE | DEFER
WO-00349 | Inspection – Heat Exchanger HX-0030 | HX-0030 | 3 | 1 | 3 |  | TRUE | 3200 | 5016.6 | 8.3 | 0.7 | 3.4 | 0.4 | 12.8 | 2 | 2 | 2190 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | 47081.26 | 42064.66 | TRUE | INCLUDE
WO-00350 | Inspection – Electrical Equipment ELEC-0085 | ELEC-0085 | 3 | 3 | 3 |  | FALSE | 4240 | 1301.98 | 2.8 | 1.2 | 3.1 | 0.5 | 7.6 | 1 | 2 | 1460 | 0.78009 | 1460 | 2.5 | 5 | 2 | 10 | 7020.85 | 5718.87 | TRUE | INCLUDE
WO-00351 | Inspection – Centrifugal Pump PMP-0064 | PMP-0064 | 3 | 3 | 3 |  | FALSE | 3585 | 2605.28 | 8.2 | 1.8 | 2.8 | 0.1 | 12.9 | 2 | 2.5 | 1825 | 0.77315 | 1825 | 3 | 5 | 3 | 15 | 16700.13 | 14094.85 | TRUE | INCLUDE
WO-00352 | Repair – Instrument/Analyser INST-0133 | INST-0133 | 5 | 3 | 3 | WO-00004 | FALSE | 4318 | 34265.5 | 30.4 | 5.1 | 12.6 | 9.2 | 57.3 | 7 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -32825.5 | FALSE | DEFER
WO-00353 | Replacement – Reciprocating Compressor CMP-0013 | CMP-0013 | 6 | 1 | 4 |  | FALSE | 1596 | 78932.16 | 51.3 | 10.6 | 20.4 | 4.5 | 86.8 | 11 | 3 | 1460 | 0.67268 | 331.9307 | 4.75 | 5 | 5 | 25 | 234850.27 | 155918.11 | TRUE | INCLUDE
WO-00354 | Cleaning – Centrifugal Pump PMP-0044 | PMP-0044 | 2 | 2 | 3 |  | FALSE | 3193 | 12152.47 | 27.5 | 1 | 0.8 | 5.2 | 34.5 | 4 | 2.5 | 1825 | 0.71583 | 1825 | 3 | 5 | 3 | 15 | 15461.89 | 3309.42 | FALSE | DEFER
WO-00355 | Replacement – Electrical Equipment ELEC-0030 | ELEC-0030 | 6 | 3 | 3 |  | FALSE | 2817 | 88134.26 | 27.8 | 8.9 | 16.3 | 1.5 | 54.5 | 7 | 2 | 1460 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | 5778.01 | -82356.25 | FALSE | DEFER
WO-00356 | Overhaul – Electrical Equipment ELEC-0055 | ELEC-0055 | 4 | 2 | 2 |  | FALSE | 2480 | 280020.28 | 183.9 | 39.8 | 43.5 | 11.5 | 278.7 | 35 | 2 | 1460 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | 5383.85 | -274636.43 | FALSE | DEFER
WO-00357 | Calibration – Centrifugal Pump PMP-0066 | PMP-0066 | 1 | 2 | 2 |  | FALSE | 968 | 1829.05 | 1.3 | 6.4 | 16.4 | 0.2 | 24.3 | 3 | 2.5 | 1825 | 0.22202 | 1579.705 | 3 | 3 | 3 | 9 | 4795.66 | 2966.61 | TRUE | INCLUDE
WO-00358 | Inspection – Centrifugal Pump PMP-0059 | PMP-0059 | 3 | 3 | 3 | WO-00090 | FALSE | 2725 | 3613.66 | 7.3 | 1 | 2.5 | 0.9 | 11.7 | 1 | 2.5 | 1825 | 0.6343 | 1825 | 3 | 5 | 3 | 15 | 13700.81 | 10087.15 | FALSE | DEFER
WO-00359 | Cleaning – Instrument/Analyser INST-0090 | INST-0090 | 2 | 2 | 3 |  | FALSE | 4292 | 23801.28 | 14.2 | 1.6 | 0.3 | 4.3 | 20.4 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -22361.28 | FALSE | DEFER
WO-00360 | Inspection – Centrifugal Pump PMP-0018 | PMP-0018 | 3 | 4 | 3 | WO-00096 | FALSE | 2749 | 4313.36 | 3.5 | 1.3 | 1.8 | 0.1 | 6.7 | 1 | 2.5 | 1825 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | 13798.72 | 9485.36 | TRUE | INCLUDE
WO-00361 | Cleaning – Instrument/Analyser INST-0172 | INST-0172 | 2 | 1 | 3 |  | TRUE | 4158 | 23474.82 | 15.8 | 0.1 | 1.1 | 6.5 | 23.5 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -22034.82 | TRUE | INCLUDE
WO-00362 | Repair – Storage Tank TNK-0013 | TNK-0013 | 5 | 4 | 1 |  | FALSE | 2765 | 50357.71 | 76.5 | 16.8 | 13.1 | 3.3 | 109.7 | 14 | 3.5 | 5475 | 0.048522 | 4183.2324 | 4 | 1 | 4 | 4 | 11354.04 | -39003.67 | FALSE | DEFER
WO-00363 | Overhaul – Instrument/Analyser INST-0175 | INST-0175 | 4 | 3 | 3 |  | FALSE | 2012 | 109961.07 | 51.2 | 34.7 | 49.3 | 21.9 | 157.1 | 20 | 1.8 | 730 | 0.88589 | 730 | 2 | 5 | 2 | 10 | 1275.68 | -108685.39 | FALSE | DEFER
WO-00364 | Testing – Control Valve VLV-0011 | VLV-0011 | 7 | 3 | 3 |  | FALSE | 4141 | 10981.01 | 8.1 | 16 | 5.6 | 0.4 | 30.1 | 4 | 1.5 | 1095 | 0.62971 | 1095 | 2.65 | 5 | 3 | 15 | 3379.15 | -7601.86 | FALSE | DEFER
WO-00365 | Replacement – Reciprocating Compressor CMP-0004 | CMP-0004 | 6 | 1 | 4 |  | FALSE | 5436 | 114652.62 | 59.8 | 8.7 | 18.2 | 4.7 | 91.4 | 11 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 234472.38 | TRUE | INCLUDE
WO-00366 | Replacement – Instrument/Analyser INST-0132 | INST-0132 | 6 | 4 | 3 |  | FALSE | 3815 | 31837.75 | 25.1 | 5.9 | 6.2 | 3 | 40.2 | 5 | 1.8 | 730 | 0.97003 | 730 | 2 | 5 | 2 | 10 | 1396.84 | -30440.91 | FALSE | DEFER
WO-00367 | Inspection – Centrifugal Pump PMP-0039 | PMP-0039 | 3 | 2 | 3 |  | FALSE | 3271 | 3003.2 | 6.2 | 0.7 | 3.1 | 0 | 10 | 1 | 2.5 | 1825 | 0.72802 | 1825 | 3 | 5 | 3 | 15 | 15725.17 | 12721.97 | TRUE | INCLUDE
WO-00368 | Cleaning – Instrument/Analyser INST-0042 | INST-0042 | 2 | 3 | 3 |  | FALSE | 4894 | 17343.19 | 17.6 | 0.9 | 0.7 | 3.8 | 23 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -15903.19 | FALSE | DEFER
WO-00369 | Inspection – Pressure Vessel VSL-0027 | VSL-0027 | 3 | 1 | 4 |  | FALSE | 5018 | 3028.98 | 7.4 | 0.2 | 1.3 | 0.7 | 9.6 | 1 | 2.8 | 3650 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | 89441.64 | 86412.66 | TRUE | INCLUDE
WO-00370 | Calibration – Instrument/Analyser INST-0171 | INST-0171 | 1 | 3 | 3 |  | FALSE | 3070 | 2824.47 | 1.9 | 5.4 | 8.2 | 0.6 | 16.1 | 2 | 1.8 | 730 | 0.94889 | 730 | 2 | 5 | 2 | 10 | 1366.41 | -1458.06 | FALSE | DEFER
WO-00371 | Cleaning – Reciprocating Compressor CMP-0012 | CMP-0012 | 2 | 4 | 4 |  | FALSE | 1706 | 8722.69 | 5.5 | 0.4 | 0.3 | 3 | 9.2 | 1 | 3 | 1460 | 0.71599 | 221.9307 | 4.75 | 5 | 5 | 25 | 249970.39 | 241247.7 | TRUE | INCLUDE
WO-00372 | Inspection – Electrical Equipment ELEC-0002 | ELEC-0002 | 3 | 2 | 3 | WO-00073 | FALSE | 3812 | 5053.75 | 9.6 | 0.7 | 3.1 | 0.7 | 14.1 | 2 | 2 | 1460 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | 6708.41 | 1654.66 | FALSE | DEFER
WO-00373 | Overhaul – Instrument/Analyser INST-0143 | INST-0143 | 4 | 3 | 3 |  | FALSE | 1579 | 493005.17 | 189.1 | 42 | 49.5 | 11.4 | 292 | 36 | 1.8 | 730 | 0.83804 | 730 | 2 | 5 | 2 | 10 | 1206.78 | -491798.39 | FALSE | DEFER
WO-00374 | Cleaning – Control Valve VLV-0016 | VLV-0016 | 2 | 3 | 3 | WO-00257 | FALSE | 3752 | 16998.51 | 21.8 | 1.5 | 1.8 | 4.8 | 29.9 | 4 | 1.5 | 1095 | 0.61237 | 1095 | 2.65 | 5 | 3 | 15 | 3286.11 | -13712.4 | FALSE | DEFER
WO-00375 | Replacement – Control Valve VLV-0090 | VLV-0090 | 6 | 2 | 3 |  | FALSE | 4763 | 73375.4 | 47.1 | 16.2 | 12.4 | 5.6 | 81.3 | 10 | 1.5 | 1095 | 0.65442 | 1095 | 2.65 | 5 | 3 | 15 | 3511.79 | -69863.61 | FALSE | DEFER
WO-00376 | Inspection – Centrifugal Pump PMP-0042 | PMP-0042 | 3 | 3 | 3 |  | FALSE | 3253 | 2527.83 | 9.3 | 0.6 | 4.9 | 0.2 | 15 | 2 | 2.5 | 1825 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | 15665.17 | 13137.34 | TRUE | INCLUDE
WO-00377 | Cleaning – Pressure Vessel VSL-0027 | VSL-0027 | 2 | 1 | 4 |  | FALSE | 5018 | 17724.88 | 19.5 | 1.4 | 1.8 | 6.5 | 29.2 | 4 | 2.8 | 3650 | 0.41123 | 3650 | 5 | 4 | 5 | 20 | 89441.64 | 71716.76 | TRUE | INCLUDE
WO-00378 | Replacement – Control Valve VLV-0030 | VLV-0030 | 6 | 3 | 3 |  | FALSE | 3077 | 86445.18 | 33.7 | 11.9 | 15.9 | 4.4 | 65.9 | 8 | 1.5 | 1095 | 0.57791 | 1095 | 2.65 | 4 | 3 | 12 | 3101.23 | -83343.95 | FALSE | DEFER
WO-00379 | Calibration – Centrifugal Pump PMP-0071 | PMP-0071 | 1 | 1 | 3 |  | FALSE | 4028 | 2200.04 | 1.4 | 9.1 | 13.5 | 1 | 25 | 3 | 2.5 | 1825 | 0.82667 | 1825 | 3 | 5 | 3 | 15 | 17856.16 | 15656.12 | TRUE | INCLUDE
WO-00380 | Cleaning – Instrument/Analyser INST-0056 | INST-0056 | 2 | 4 | 3 |  | FALSE | 1149 | 18206.24 | 15.5 | 0.6 | 1.1 | 4.9 | 22.1 | 3 | 1.8 | 730 | 0.76658 | 11.2559 | 2 | 5 | 2 | 10 | 1103.88 | -17102.36 | FALSE | DEFER
WO-00381 | Replacement – Instrument/Analyser INST-0061 | INST-0061 | 6 | 3 | 3 |  | FALSE | 3878 | 25206.3 | 38 | 9.1 | 5.9 | 6.1 | 59.1 | 7 | 1.8 | 730 | 0.97132 | 730 | 2 | 5 | 2 | 10 | 1398.7 | -23807.6 | FALSE | DEFER
WO-00382 | Inspection – Centrifugal Pump PMP-0054 | PMP-0054 | 3 | 4 | 3 |  | FALSE | 3759 | 5022.52 | 6.5 | 1.5 | 2.4 | 0.2 | 10.6 | 1 | 2.5 | 1825 | 0.79554 | 1825 | 3 | 5 | 3 | 15 | 17183.71 | 12161.19 | TRUE | INCLUDE
WO-00383 | Cleaning – Reciprocating Compressor CMP-0001 | CMP-0001 | 2 | 4 | 4 |  | FALSE | 5148 | 1651.36 | 23.7 | 0.4 | 1.6 | 7.6 | 33.3 | 4 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 347473.64 | TRUE | INCLUDE
WO-00384 | Testing – Centrifugal Pump PMP-0052 | PMP-0052 | 7 | 1 | 3 |  | FALSE | 3747 | 4478.95 | 15.8 | 10.3 | 16.6 | 1.2 | 43.9 | 5 | 2.5 | 1825 | 0.79406 | 1825 | 3 | 5 | 3 | 15 | 17151.61 | 12672.66 | TRUE | INCLUDE
WO-00385 | Inspection – Instrument/Analyser INST-0131 | INST-0131 | 3 | 3 | 3 |  | FALSE | 923 | 1027.45 | 3 | 0.5 | 4.6 | 0.5 | 8.6 | 1 | 1.8 | 730 | 0.71449 | 237.2558 | 2 | 5 | 2 | 10 | 1028.86 | 1.41 | FALSE | DEFER
WO-00386 | Repair – Control Valve VLV-0078 | VLV-0078 | 5 | 4 | 3 |  | FALSE | 2038 | 59325.56 | 44 | 26.5 | 15.4 | 7.7 | 93.6 | 12 | 1.5 | 1095 | 0.50925 | 1095 | 2.65 | 4 | 3 | 12 | 2732.74 | -56592.82 | FALSE | DEFER
WO-00387 | Cleaning – Centrifugal Pump PMP-0045 | PMP-0045 | 2 | 1 | 3 |  | TRUE | 3222 | 13685.79 | 25.4 | 0.9 | 1.6 | 2.4 | 30.3 | 4 | 2.5 | 1825 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | 15560.77 | 1874.98 | TRUE | INCLUDE
WO-00388 | Cleaning – Reciprocating Compressor CMP-0005 | CMP-0005 | 2 | 4 | 4 |  | FALSE | 4190 | 2766.69 | 27.4 | 0 | 1.4 | 3.9 | 32.7 | 4 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 346358.31 | TRUE | INCLUDE
WO-00389 | Replacement – Piping/Pipeline Segment PPL-0030 | PPL-0030 | 6 | 1 | 3 |  | FALSE | 4844 | 8137.59 | 9.4 | 12 | 23.7 | 9.8 | 54.9 | 7 | 2 | 3285 | 0.28825 | 140.7483 | 3.65 | 3 | 4 | 12 | 13887.95 | 5750.36 | TRUE | INCLUDE
WO-00390 | Overhaul – Control Valve VLV-0027 | VLV-0027 | 4 | 4 | 3 |  | FALSE | 922 | 73766.65 | 144.4 | 33.2 | 18.5 | 16.2 | 212.3 | 27 | 1.5 | 1095 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | 2116.63 | -71650.02 | FALSE | DEFER
WO-00391 | Inspection – Instrument/Analyser INST-0134 | INST-0134 | 3 | 2 | 3 |  | FALSE | 4787 | 2294.11 | 3.7 | 0.2 | 1.7 | 0.6 | 6.2 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -854.11 | FALSE | DEFER
WO-00392 | Calibration – Distillation Tower TWR-0011 | TWR-0011 | 1 | 1 | 3 |  | FALSE | 2943 | 2683.66 | 1.9 | 7.3 | 7.2 | 0.1 | 16.5 | 2 | 2.2 | 2920 | 0.25801 | 1323.054 | 5 | 3 | 5 | 15 | 189640.61 | 186956.95 | TRUE | INCLUDE
WO-00393 | Testing – Heat Exchanger HX-0034 | HX-0034 | 7 | 4 | 3 | WO-00363 | FALSE | 1851 | 14454.01 | 8.9 | 10.5 | 14.2 | 0.6 | 34.2 | 4 | 2 | 2190 | 0.2662 | 1472.1654 | 4 | 3 | 4 | 12 | 31144.9 | 16690.89 | FALSE | DEFER
WO-00394 | Replacement – Control Valve VLV-0059 | VLV-0059 | 6 | 2 | 3 |  | FALSE | 2274 | 47451.41 | 30.3 | 4.3 | 11.7 | 8.7 | 55 | 7 | 1.5 | 1095 | 0.52703 | 1095 | 2.65 | 4 | 3 | 12 | 2828.17 | -44623.24 | FALSE | DEFER
WO-00395 | Cleaning – Centrifugal Pump PMP-0009 | PMP-0009 | 2 | 1 | 3 |  | FALSE | 3655 | 10759.29 | 8.1 | 0 | 0.5 | 2.5 | 11.1 | 1 | 2.5 | 1825 | 0.78238 | 1825 | 3 | 5 | 3 | 15 | 16899.41 | 6140.12 | TRUE | INCLUDE
WO-00396 | Calibration – Instrument/Analyser INST-0173 | INST-0173 | 1 | 2 | 3 |  | FALSE | 3704 | 2215.12 | 1.9 | 5.4 | 15.3 | 0.7 | 23.3 | 3 | 1.8 | 730 | 0.96759 | 730 | 2 | 5 | 2 | 10 | 1393.33 | -821.79 | FALSE | DEFER
WO-00397 | Replacement – Control Valve VLV-0076 | VLV-0076 | 6 | 2 | 3 |  | FALSE | 1553 | 65930.4 | 49.4 | 10.3 | 8.6 | 9.9 | 78.2 | 10 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | -63424.52 | FALSE | DEFER
WO-00398 | Testing – Instrument/Analyser INST-0019 | INST-0019 | 7 | 3 | 3 |  | FALSE | 5171 | 12231.17 | 17.1 | 19.9 | 8.2 | 1.3 | 46.5 | 6 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -10791.17 | FALSE | DEFER
WO-00399 | Calibration – Heat Exchanger HX-0016 | HX-0016 | 1 | 3 | 3 |  | FALSE | 3286 | 960.38 | 0.4 | 4.6 | 11.7 | 0.6 | 17.3 | 2 | 2 | 2190 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | 47990.52 | 47030.14 | TRUE | INCLUDE
WO-00400 | Calibration – Electrical Equipment ELEC-0041 | ELEC-0041 | 1 | 1 | 2 |  | TRUE | 1599 | 2093.22 | 0.5 | 5.8 | 9.4 | 0.2 | 15.9 | 2 | 2 | 1460 | 0.4567 | 616.4436 | 2.5 | 4 | 2 | 8 | 4110.34 | 2017.12 | TRUE | INCLUDE
WO-00401 | Replacement – Control Valve VLV-0004 | VLV-0004 | 6 | 3 | 2 | WO-00202 | FALSE | 436 | 34453.37 | 37.7 | 3.1 | 9.4 | 1.4 | 51.6 | 6 | 1.5 | 1095 | 0.31229 | 1473.375 | 2.65 | 3 | 3 | 9 | 1675.84 | -32777.53 | FALSE | DEFER
WO-00402 | Cleaning – Instrument/Analyser INST-0060 | INST-0060 | 2 | 3 | 3 |  | FALSE | 4310 | 9099.52 | 7.5 | 1.9 | 1.2 | 7.4 | 18 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -7659.52 | FALSE | DEFER
WO-00403 | Calibration – Electrical Equipment ELEC-0071 | ELEC-0071 | 1 | 2 | 3 |  | FALSE | 4950 | 2709.86 | 0.8 | 7.5 | 7.7 | 0.7 | 16.7 | 2 | 2 | 1460 | 0.82756 | 1460 | 2.5 | 5 | 2 | 10 | 7448.04 | 4738.18 | TRUE | INCLUDE
WO-00404 | Inspection – Instrument/Analyser INST-0152 | INST-0152 | 3 | 3 | 3 |  | FALSE | 4490 | 7670.91 | 8.9 | 0.6 | 5 | 0.3 | 14.8 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -6230.91 | FALSE | DEFER
WO-00405 | Repair – Instrument/Analyser INST-0083 | INST-0083 | 5 | 2 | 3 |  | FALSE | 3623 | 25758.52 | 49.4 | 21.3 | 4.3 | 4.8 | 79.8 | 10 | 1.8 | 730 | 0.96568 | 730 | 2 | 5 | 2 | 10 | 1390.58 | -24367.94 | FALSE | DEFER
WO-00406 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | 1 | 3 | 3 |  | FALSE | 3486 | 580.71 | 0.5 | 7.7 | 6.5 | 0.4 | 15.1 | 2 | 2 | 1460 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | 6437.74 | 5857.03 | TRUE | INCLUDE
WO-00407 | Calibration – Heat Exchanger HX-0030 | HX-0030 | 1 | 3 | 3 |  | FALSE | 3200 | 465.67 | 1.7 | 7.8 | 9.4 | 0.8 | 19.7 | 2 | 2 | 2190 | 0.4024 | 123.1654 | 4 | 4 | 4 | 16 | 47081.26 | 46615.59 | TRUE | INCLUDE
WO-00408 | Cleaning – Piping/Pipeline Segment PPL-0023 | PPL-0023 | 2 | 3 | 3 |  | FALSE | 2758 | 14403.55 | 21.6 | 2 | 1.2 | 8.5 | 33.3 | 4 | 2 | 3285 | 0.18038 | 2226.7481 | 3.65 | 3 | 4 | 12 | 8690.83 | -5712.72 | FALSE | DEFER
WO-00409 | Repair – Instrument/Analyser INST-0054 | INST-0054 | 5 | 3 | 3 |  | FALSE | 4591 | 76452.94 | 25.8 | 8.3 | 12.6 | 5 | 51.7 | 6 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -75012.94 | FALSE | DEFER
WO-00410 | Calibration – Pressure Vessel VSL-0003 | VSL-0003 | 1 | 1 | 3 |  | TRUE | 2814 | 2808.8 | 0.8 | 7.7 | 7.1 | 0.5 | 16.1 | 2 | 2.8 | 3650 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | 38798.52 | 35989.72 | TRUE | INCLUDE
WO-00411 | Overhaul – Control Valve VLV-0027 | VLV-0027 | 4 | 2 | 3 |  | FALSE | 922 | 334021.83 | 187.1 | 35.3 | 23.1 | 4.1 | 249.6 | 31 | 1.5 | 1095 | 0.39443 | 987.3752 | 2.65 | 4 | 3 | 12 | 2116.63 | -331905.2 | FALSE | DEFER
WO-00412 | Testing – Instrument/Analyser INST-0172 | INST-0172 | 7 | 2 | 3 |  | FALSE | 4158 | 13873.83 | 7.9 | 9.2 | 12.7 | 1.4 | 31.2 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -12433.83 | FALSE | DEFER
WO-00413 | Inspection – Piping/Pipeline Segment PPL-0031 | PPL-0031 | 3 | 2 | 3 |  | FALSE | 4972 | 3580.68 | 4.1 | 0.6 | 1.7 | 0.7 | 7.1 | 1 | 2 | 3285 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | 14183.6 | 10602.92 | TRUE | INCLUDE
WO-00414 | Replacement – Instrument/Analyser INST-0137 | INST-0137 | 6 | 4 | 3 |  | FALSE | 3542 | 68694.19 | 33.6 | 16.3 | 23.1 | 2.2 | 75.2 | 9 | 1.8 | 730 | 0.96365 | 730 | 2 | 5 | 2 | 10 | 1387.65 | -67306.54 | FALSE | DEFER
WO-00415 | Calibration – Centrifugal Pump PMP-0021 | PMP-0021 | 1 | 2 | 3 |  | FALSE | 4170 | 2139.15 | 0.7 | 4.8 | 4.1 | 1 | 10.6 | 1 | 2.5 | 1825 | 0.84149 | 1825 | 3 | 5 | 3 | 15 | 18176.25 | 16037.1 | TRUE | INCLUDE
WO-00416 | Overhaul – Distillation Tower TWR-0012 | TWR-0012 | 4 | 3 | 4 |  | FALSE | 4172 | 333104.76 | 48.1 | 15.3 | 34.2 | 14.3 | 111.9 | 14 | 2.2 | 2920 | 0.3587 | 94.0539 | 5 | 4 | 5 | 20 | 263641.88 | -69462.88 | FALSE | DEFER
WO-00417 | Cleaning – Instrument/Analyser INST-0164 | INST-0164 | 2 | 2 | 3 |  | FALSE | 3607 | 15434.46 | 23.6 | 0.1 | 1.4 | 7.7 | 32.8 | 4 | 1.8 | 730 | 0.96529 | 730 | 2 | 5 | 2 | 10 | 1390.01 | -14044.45 | FALSE | DEFER
WO-00418 | Inspection – Control Valve VLV-0115 | VLV-0115 | 3 | 2 | 3 |  | FALSE | 1747 | 2182.51 | 3.6 | 1 | 1.5 | 0.7 | 6.8 | 1 | 1.5 | 1095 | 0.48494 | 162.3748 | 2.65 | 4 | 3 | 12 | 2602.31 | 419.8 | FALSE | DEFER
WO-00419 | Inspection – Electrical Equipment ELEC-0009 | ELEC-0009 | 3 | 2 | 2 |  | FALSE | 548 | 2962.75 | 3.5 | 2 | 2.2 | 0.2 | 7.9 | 1 | 2 | 1460 | 0.22133 | 1667.4436 | 2.5 | 3 | 2 | 6 | 1991.99 | -970.76 | FALSE | DEFER
WO-00420 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | 6 | 4 | 3 |  | FALSE | 1769 | 74672.62 | 48.7 | 8.6 | 16.5 | 5.3 | 79.1 | 10 | 1.8 | 730 | 0.86137 | 730 | 2 | 5 | 2 | 10 | 1240.37 | -73432.25 | FALSE | DEFER
WO-00421 | Cleaning – Centrifugal Pump PMP-0042 | PMP-0042 | 2 | 3 | 3 |  | FALSE | 3253 | 7957.4 | 20.9 | 1.6 | 0.9 | 9.9 | 33.3 | 4 | 2.5 | 1825 | 0.72524 | 1825 | 3 | 5 | 3 | 15 | 15665.17 | 7707.77 | TRUE | INCLUDE
WO-00422 | Inspection – Instrument/Analyser INST-0055 | INST-0055 | 3 | 3 | 3 |  | FALSE | 2267 | 6421.99 | 6.8 | 1.1 | 3.1 | 0.9 | 11.9 | 1 | 1.8 | 730 | 0.90654 | 730 | 2 | 5 | 2 | 10 | 1305.41 | -5116.58 | FALSE | DEFER
WO-00423 | Cleaning – Heat Exchanger HX-0028 | HX-0028 | 2 | 3 | 3 |  | FALSE | 5045 | 2172.64 | 14.8 | 1.8 | 1.4 | 2.4 | 20.4 | 3 | 2 | 2190 | 0.54872 | 2190 | 4 | 4 | 4 | 16 | 64199.97 | 62027.33 | TRUE | INCLUDE
WO-00424 | Repair – Instrument/Analyser INST-0011 | INST-0011 | 5 | 3 | 3 |  | FALSE | 1302 | 44641.37 | 10.1 | 18.6 | 3 | 3.9 | 35.6 | 4 | 1.8 | 730 | 0.79553 | 730 | 2 | 5 | 2 | 10 | 1145.57 | -43495.8 | FALSE | DEFER
WO-00425 | Repair – Control Valve VLV-0107 | VLV-0107 | 5 | 3 | 3 |  | FALSE | 3428 | 29908.06 | 87.1 | 27.9 | 2.4 | 3.2 | 120.6 | 15 | 1.5 | 1095 | 0.5966 | 1095 | 2.65 | 4 | 3 | 12 | 3201.49 | -26706.57 | FALSE | DEFER
WO-00426 | Calibration – Electrical Equipment ELEC-0030 | ELEC-0030 | 1 | 1 | 3 |  | FALSE | 2817 | 1298.77 | 1.3 | 6.9 | 15.8 | 0.7 | 24.7 | 3 | 2 | 1460 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | 5778.01 | 4479.24 | TRUE | INCLUDE
WO-00427 | Inspection – Electrical Equipment ELEC-0068 | ELEC-0068 | 3 | 3 | 2 |  | FALSE | 385 | 1582.18 | 9.5 | 1.8 | 4.2 | 0.1 | 15.6 | 2 | 2 | 1460 | 0.17663 | 1830.4436 | 2.5 | 3 | 2 | 6 | 1589.67 | 7.49 | FALSE | DEFER
WO-00428 | Inspection – Distillation Tower TWR-0007 | TWR-0007 | 3 | 4 | 4 | WO-00330 | FALSE | 4310 | 3326.04 | 4.1 | 1.7 | 1.6 | 0.6 | 8 | 1 | 2.2 | 2920 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | 271562.17 | 268236.13 | TRUE | INCLUDE
WO-00429 | Calibration – Instrument/Analyser INST-0042 | INST-0042 | 1 | 4 | 3 | WO-00323 | FALSE | 4894 | 421.85 | 1.8 | 7.1 | 11.3 | 0.7 | 20.9 | 3 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 1018.15 | TRUE | INCLUDE
WO-00430 | Overhaul – Instrument/Analyser INST-0098 | INST-0098 | 4 | 2 | 3 | WO-00356 | FALSE | 3588 | 325823.07 | 130.5 | 11 | 41.1 | 6.5 | 189.1 | 24 | 1.8 | 730 | 0.96482 | 730 | 2 | 5 | 2 | 10 | 1389.33 | -324433.74 | FALSE | DEFER
WO-00431 | Replacement – Instrument/Analyser INST-0116 | INST-0116 | 6 | 4 | 3 |  | FALSE | 5320 | 37204.69 | 28.9 | 13.1 | 10.2 | 2.6 | 54.8 | 7 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -35764.69 | FALSE | DEFER
WO-00432 | Testing – Instrument/Analyser INST-0103 | INST-0103 | 7 | 4 | 3 |  | FALSE | 3423 | 7149.47 | 7.9 | 4.9 | 4.7 | 0.8 | 18.3 | 2 | 1.8 | 730 | 0.96042 | 730 | 2 | 5 | 2 | 10 | 1383.01 | -5766.46 | FALSE | DEFER
WO-00433 | Calibration – Electrical Equipment ELEC-0015 | ELEC-0015 | 1 | 2 | 2 |  | FALSE | 625 | 1177.95 | 1.9 | 5.4 | 8.4 | 0.4 | 16.1 | 2 | 2 | 1460 | 0.2416 | 1590.4436 | 2.5 | 3 | 2 | 6 | 2174.38 | 996.43 | TRUE | INCLUDE
WO-00434 | Repair – Piping/Pipeline Segment PPL-0034 | PPL-0034 | 5 | 2 | 2 |  | FALSE | 1069 | 30171.52 | 68.5 | 14.1 | 18.2 | 6.8 | 107.6 | 13 | 2 | 3285 | 0.081176 | 3915.748 | 3.65 | 2 | 4 | 8 | 3911.07 | -26260.45 | FALSE | DEFER
WO-00435 | Inspection – Electrical Equipment ELEC-0043 | ELEC-0043 | 3 | 2 | 3 |  | FALSE | 4705 | 7274.18 | 6.4 | 0.6 | 4.5 | 0.1 | 11.6 | 1 | 2 | 1460 | 0.81247 | 1460 | 2.5 | 5 | 2 | 10 | 7312.2 | 38.02 | FALSE | DEFER
WO-00436 | Cleaning – Heat Exchanger HX-0004 | HX-0004 | 2 | 1 | 3 |  | TRUE | 2889 | 9155.54 | 15.4 | 0.5 | 0.3 | 2.3 | 18.5 | 2 | 2 | 2190 | 0.37344 | 434.1652 | 4 | 4 | 4 | 16 | 43691.97 | 34536.43 | TRUE | INCLUDE
WO-00437 | Testing – Instrument/Analyser INST-0004 | INST-0004 | 7 | 2 | 3 | WO-00370 | FALSE | 1748 | 8843.35 | 10.8 | 11.7 | 18.2 | 0.3 | 41 | 5 | 1.8 | 730 | 0.85899 | 730 | 2 | 5 | 2 | 10 | 1236.94 | -7606.41 | FALSE | DEFER
WO-00438 | Cleaning – Distillation Tower TWR-0007 | TWR-0007 | 2 | 1 | 4 |  | FALSE | 4310 | 12497.54 | 22.5 | 1.8 | 1.6 | 3.5 | 29.4 | 4 | 2.2 | 2920 | 0.36947 | 2920 | 5 | 4 | 5 | 20 | 271562.17 | 259064.63 | TRUE | INCLUDE
WO-00439 | Inspection – Instrument/Analyser INST-0024 | INST-0024 | 3 | 3 | 3 |  | FALSE | 1785 | 6398.13 | 9.3 | 1.9 | 2.2 | 0.8 | 14.2 | 2 | 1.8 | 730 | 0.86316 | 730 | 2 | 5 | 2 | 10 | 1242.94 | -5155.19 | FALSE | DEFER
WO-00440 | Repair – Instrument/Analyser INST-0037 | INST-0037 | 5 | 2 | 3 |  | FALSE | 4388 | 44772.46 | 21.4 | 6.1 | 19.2 | 4.8 | 51.5 | 6 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -43332.46 | FALSE | DEFER
WO-00441 | Replacement – Instrument/Analyser INST-0155 | INST-0155 | 6 | 3 | 3 | WO-00164 | FALSE | 3302 | 48577.46 | 57.1 | 3.1 | 6.4 | 8.1 | 74.7 | 9 | 1.8 | 730 | 0.95682 | 730 | 2 | 5 | 2 | 10 | 1377.82 | -47199.64 | FALSE | DEFER
WO-00442 | Inspection – Pressure Vessel VSL-0010 | VSL-0010 | 3 | 3 | 3 |  | FALSE | 3870 | 855.01 | 3.8 | 0.5 | 1.1 | 0.2 | 5.6 | 1 | 2.8 | 3650 | 0.28693 | 1046.4952 | 5 | 3 | 5 | 15 | 62407.43 | 61552.42 | TRUE | INCLUDE
WO-00443 | Repair – Control Valve VLV-0032 | VLV-0032 | 5 | 3 | 3 |  | FALSE | 3446 | 72062.39 | 43.9 | 12.3 | 20 | 7.9 | 84.1 | 11 | 1.5 | 1095 | 0.59751 | 1095 | 2.65 | 4 | 3 | 12 | 3206.38 | -68856.01 | FALSE | DEFER
WO-00444 | Replacement – Distillation Tower TWR-0005 | TWR-0005 | 6 | 2 | 3 |  | FALSE | 657 | 41950.13 | 34.8 | 11.8 | 4.3 | 9.6 | 60.5 | 8 | 2.2 | 2920 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | 44001.97 | 2051.84 | TRUE | INCLUDE
WO-00445 | Cleaning – Electrical Equipment ELEC-0060 | ELEC-0060 | 2 | 3 | 3 |  | FALSE | 4070 | 6075.31 | 22.4 | 1.5 | 0.2 | 6.8 | 30.9 | 4 | 2 | 1460 | 0.76691 | 1460 | 2.5 | 5 | 2 | 10 | 6902.2 | 826.89 | FALSE | DEFER
WO-00446 | Repair – Control Valve VLV-0062 | VLV-0062 | 5 | 2 | 2 |  | FALSE | 630 | 18075.11 | 88.7 | 16 | 3.7 | 2 | 110.4 | 14 | 1.5 | 1095 | 0.34935 | 1279.3751 | 2.65 | 3 | 3 | 9 | 1874.71 | -16200.4 | FALSE | DEFER
WO-00447 | Replacement – Centrifugal Pump PMP-0013 | PMP-0013 | 6 | 2 | 3 |  | FALSE | 4594 | 62086.67 | 46.9 | 5.4 | 23.9 | 2.5 | 78.7 | 10 | 2.5 | 1825 | 0.87967 | 1825 | 3 | 5 | 3 | 15 | 19000.78 | -43085.89 | FALSE | DEFER
WO-00448 | Testing – Piping/Pipeline Segment PPL-0031 | PPL-0031 | 7 | 2 | 3 |  | FALSE | 4972 | 12571.36 | 13.7 | 18.3 | 6.7 | 0 | 38.7 | 5 | 2 | 3285 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | 14183.6 | 1612.24 | FALSE | DEFER
WO-00449 | Inspection – Reciprocating Compressor CMP-0007 | CMP-0007 | 3 | 3 | 4 |  | FALSE | 3016 | 3247.37 | 3.8 | 1.8 | 4.5 | 0.8 | 10.9 | 1 | 3 | 1460 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | 339618.52 | 336371.15 | TRUE | INCLUDE
WO-00450 | Inspection – Instrument/Analyser INST-0083 | INST-0083 | 3 | 3 | 3 |  | FALSE | 3623 | 957.92 | 7.2 | 1.3 | 2.5 | 0.5 | 11.5 | 1 | 1.8 | 730 | 0.96568 | 730 | 2 | 5 | 2 | 10 | 1390.58 | 432.66 | TRUE | INCLUDE
WO-00451 | Replacement – Electrical Equipment ELEC-0026 | ELEC-0026 | 6 | 3 | 3 |  | FALSE | 2569 | 41129.16 | 29.8 | 12.9 | 23.1 | 5.8 | 71.6 | 9 | 2 | 1460 | 0.61027 | 1460 | 2.5 | 5 | 2 | 10 | 5492.41 | -35636.75 | FALSE | DEFER
WO-00452 | Calibration – Control Valve VLV-0038 | VLV-0038 | 1 | 4 | 3 |  | FALSE | 4177 | 517.82 | 1.3 | 5.9 | 13.2 | 0 | 20.4 | 3 | 1.5 | 1095 | 0.63123 | 1095 | 2.65 | 5 | 3 | 15 | 3387.34 | 2869.52 | TRUE | INCLUDE
WO-00453 | Testing – Control Valve VLV-0079 | VLV-0079 | 7 | 2 | 3 |  | FALSE | 3869 | 550.49 | 5.8 | 7.6 | 19.6 | 1.2 | 34.2 | 4 | 1.5 | 1095 | 0.61775 | 1095 | 2.65 | 5 | 3 | 15 | 3315.02 | 2764.53 | TRUE | INCLUDE
WO-00454 | Calibration – Control Valve VLV-0042 | VLV-0042 | 1 | 2 | 3 |  | FALSE | 4579 | 1189.73 | 0.9 | 5.1 | 12.3 | 0.5 | 18.8 | 2 | 1.5 | 1095 | 0.64746 | 1095 | 2.65 | 5 | 3 | 15 | 3474.41 | 2284.68 | TRUE | INCLUDE
WO-00455 | Overhaul – Heat Exchanger HX-0014 | HX-0014 | 4 | 1 | 3 |  | TRUE | 2851 | 546377.23 | 140.6 | 46.5 | 31.1 | 19.4 | 237.6 | 30 | 2 | 2190 | 0.3698 | 472.1654 | 4 | 4 | 4 | 16 | 43266.74 | -503110.49 | TRUE | INCLUDE
WO-00456 | Calibration – Heat Exchanger HX-0016 | HX-0016 | 1 | 4 | 3 | WO-00444 | FALSE | 3286 | 940.1 | 0 | 3.3 | 4.3 | 0.9 | 8.5 | 1 | 2 | 2190 | 0.41018 | 37.1652 | 4 | 4 | 4 | 16 | 47990.52 | 47050.42 | TRUE | INCLUDE
WO-00457 | Calibration – Reciprocating Compressor CMP-0002 | CMP-0002 | 1 | 2 | 4 |  | FALSE | 1206 | 502.76 | 1.8 | 8 | 9.3 | 0.5 | 19.6 | 2 | 3 | 1460 | 0.49452 | 721.9307 | 4.75 | 4 | 5 | 20 | 172649.17 | 172146.41 | TRUE | INCLUDE
WO-00458 | Inspection – Distillation Tower TWR-0005 | TWR-0005 | 3 | 3 | 3 |  | FALSE | 657 | 4311.4 | 7.9 | 0.4 | 2.8 | 0.5 | 11.6 | 1 | 2.2 | 2920 | 0.059867 | 3609.054 | 5 | 2 | 5 | 10 | 44001.97 | 39690.57 | TRUE | INCLUDE
WO-00459 | Testing – Instrument/Analyser INST-0038 | INST-0038 | 7 | 1 | 3 |  | FALSE | 3171 | 12800 | 13.2 | 15.7 | 16.1 | 1.1 | 46.1 | 6 | 1.8 | 730 | 0.95252 | 730 | 2 | 5 | 2 | 10 | 1371.63 | -11428.37 | FALSE | DEFER
WO-00460 | Calibration – Centrifugal Pump PMP-0010 | PMP-0010 | 1 | 1 | 3 | WO-00148 | FALSE | 2630 | 2205.74 | 1 | 9 | 14.8 | 0.4 | 25.2 | 3 | 2.5 | 1825 | 0.61598 | 1825 | 3 | 5 | 3 | 15 | 13305.23 | 11099.49 | FALSE | DEFER
WO-00461 | Inspection – Electrical Equipment ELEC-0055 | ELEC-0055 | 3 | 3 | 2 |  | FALSE | 2480 | 3203.31 | 5.7 | 0.3 | 1.8 | 0.2 | 8 | 1 | 2 | 1460 | 0.59821 | 1460 | 2.5 | 4 | 2 | 8 | 5383.85 | 2180.54 | TRUE | INCLUDE
WO-00462 | Calibration – Instrument/Analyser INST-0129 | INST-0129 | 1 | 1 | 2 |  | FALSE | 553 | 1272.23 | 0.3 | 2.9 | 5.4 | 0.4 | 9 | 1 | 1.8 | 730 | 0.59502 | 607.2559 | 2 | 4 | 2 | 8 | 856.83 | -415.4 | FALSE | DEFER
WO-00463 | Replacement – Centrifugal Pump PMP-0045 | PMP-0045 | 6 | 4 | 3 |  | FALSE | 3222 | 115576.32 | 34.4 | 16.8 | 6.6 | 3.4 | 61.2 | 8 | 2.5 | 1825 | 0.72041 | 1825 | 3 | 5 | 3 | 15 | 15560.77 | -100015.55 | FALSE | DEFER
WO-00464 | Replacement – Electrical Equipment ELEC-0053 | ELEC-0053 | 6 | 1 | 3 |  | FALSE | 4448 | 79566.7 | 58.8 | 11.9 | 10.1 | 5.8 | 86.6 | 11 | 2 | 1460 | 0.79521 | 1460 | 2.5 | 5 | 2 | 10 | 7156.92 | -72409.78 | FALSE | DEFER
WO-00465 | Inspection – Centrifugal Pump PMP-0019 | PMP-0019 | 3 | 2 | 2 | WO-00264 | FALSE | 588 | 653.07 | 9.1 | 1.3 | 2.2 | 0.2 | 12.8 | 2 | 2.5 | 1825 | 0.12901 | 1959.7052 | 3 | 2 | 3 | 6 | 2786.64 | 2133.57 | TRUE | INCLUDE
WO-00466 | Repair – Instrument/Analyser INST-0057 | INST-0057 | 5 | 2 | 3 |  | FALSE | 976 | 25332.85 | 37.6 | 26.2 | 18.1 | 9.2 | 91.1 | 11 | 1.8 | 730 | 0.72785 | 184.2559 | 2 | 5 | 2 | 10 | 1048.11 | -24284.74 | FALSE | DEFER
WO-00467 | Inspection – Distillation Tower TWR-0009 | TWR-0009 | 3 | 4 | 3 |  | FALSE | 570 | 3855.98 | 4.4 | 1.8 | 1.1 | 0.6 | 7.9 | 1 | 2.2 | 2920 | 0.052723 | 3696.054 | 5 | 2 | 5 | 10 | 38751.19 | 34895.21 | TRUE | INCLUDE
WO-00468 | Testing – Instrument/Analyser INST-0020 | INST-0020 | 7 | 4 | 3 |  | FALSE | 1123 | 9926.89 | 19.1 | 5.5 | 11.2 | 0 | 35.8 | 4 | 1.8 | 730 | 0.7612 | 37.2559 | 2 | 5 | 2 | 10 | 1096.12 | -8830.77 | FALSE | DEFER
WO-00469 | Repair – Piping/Pipeline Segment PPL-0018 | PPL-0018 | 5 | 1 | 2 |  | FALSE | 870 | 4188.1 | 9.7 | 13.5 | 6.7 | 8.6 | 38.5 | 5 | 2 | 3285 | 0.068723 | 4114.7481 | 3.65 | 2 | 4 | 8 | 3311.1 | -877 | FALSE | DEFER
WO-00470 | Calibration – Storage Tank TNK-0020 | TNK-0020 | 1 | 2 | 3 |  | FALSE | 4788 | 1752.49 | 0.8 | 3.2 | 20 | 0.6 | 24.6 | 3 | 3.5 | 5475 | 0.16756 | 2160.2321 | 4 | 3 | 4 | 12 | 39208.79 | 37456.3 | TRUE | INCLUDE
WO-00471 | Replacement – Control Valve VLV-0041 | VLV-0041 | 6 | 2 | 3 |  | FALSE | 1111 | 109158.75 | 50.7 | 16.6 | 16.3 | 9 | 92.6 | 12 | 1.5 | 1095 | 0.41899 | 798.375 | 2.65 | 4 | 3 | 12 | 2248.38 | -106910.37 | FALSE | DEFER
WO-00472 | Calibration – Instrument/Analyser INST-0069 | INST-0069 | 1 | 3 | 3 |  | FALSE | 4652 | 1332.45 | 1.2 | 10 | 19.8 | 0.5 | 31.5 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 107.55 | FALSE | DEFER
WO-00473 | Repair – Piping/Pipeline Segment PPL-0020 | PPL-0020 | 5 | 3 | 2 |  | FALSE | 1786 | 78879.59 | 79.6 | 5.7 | 7.8 | 9.1 | 102.2 | 13 | 2 | 3285 | 0.12468 | 3198.7481 | 3.65 | 2 | 4 | 8 | 6007.02 | -72872.57 | FALSE | DEFER
WO-00474 | Calibration – Instrument/Analyser INST-0162 | INST-0162 | 1 | 3 | 3 |  | FALSE | 1397 | 2070.19 | 0.8 | 5.2 | 16.9 | 0.3 | 23.2 | 3 | 1.8 | 730 | 0.81141 | 730 | 2 | 5 | 2 | 10 | 1168.43 | -901.76 | FALSE | DEFER
WO-00475 | Calibration – Electrical Equipment ELEC-0081 | ELEC-0081 | 1 | 3 | 3 |  | FALSE | 3486 | 2564.76 | 0.6 | 7.9 | 5.7 | 0.1 | 14.3 | 2 | 2 | 1460 | 0.7153 | 1460 | 2.5 | 5 | 2 | 10 | 6437.74 | 3872.98 | TRUE | INCLUDE
WO-00476 | Inspection – Pressure Vessel VSL-0018 | VSL-0018 | 3 | 3 | 4 |  | FALSE | 4857 | 7612.97 | 9.2 | 0.1 | 4.4 | 0.5 | 14.2 | 2 | 2.8 | 3650 | 0.39382 | 59.4951 | 5 | 4 | 5 | 20 | 85654.78 | 78041.81 | TRUE | INCLUDE
WO-00477 | Repair – Control Valve VLV-0044 | VLV-0044 | 5 | 3 | 3 |  | FALSE | 5071 | 47004.01 | 18.7 | 4.1 | 10.9 | 9.5 | 43.2 | 5 | 1.5 | 1095 | 0.6655 | 1095 | 2.65 | 5 | 3 | 15 | 3571.26 | -43432.75 | FALSE | DEFER
WO-00478 | Replacement – Instrument/Analyser INST-0026 | INST-0026 | 6 | 2 | 3 |  | FALSE | 3487 | 8556.03 | 55.6 | 7.9 | 18.1 | 7.2 | 88.8 | 11 | 1.8 | 730 | 0.96219 | 730 | 2 | 5 | 2 | 10 | 1385.56 | -7170.47 | FALSE | DEFER
WO-00479 | Inspection – Electrical Equipment ELEC-0036 | ELEC-0036 | 3 | 3 | 2 |  | FALSE | 607 | 3449 | 4.5 | 1.4 | 4.3 | 0.2 | 10.4 | 1 | 2 | 1460 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | 2132.17 | -1316.83 | FALSE | DEFER
WO-00480 | Inspection – Piping/Pipeline Segment PPL-0001 | PPL-0001 | 3 | 2 | 3 |  | FALSE | 4443 | 2185.49 | 8.1 | 1.6 | 4.1 | 0.1 | 13.9 | 2 | 2 | 3285 | 0.26868 | 541.7481 | 3.65 | 3 | 4 | 12 | 12944.99 | 10759.5 | TRUE | INCLUDE
WO-00481 | Overhaul – Instrument/Analyser INST-0135 | INST-0135 | 4 | 3 | 3 |  | FALSE | 4457 | 595019.48 | 170.8 | 47.3 | 14.1 | 13 | 245.2 | 31 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -593579.48 | FALSE | DEFER
WO-00482 | Replacement – Instrument/Analyser INST-0148 | INST-0148 | 6 | 3 | 3 |  | FALSE | 1769 | 77738.48 | 34.6 | 19.9 | 7.5 | 9.4 | 71.4 | 9 | 1.8 | 730 | 0.86137 | 730 | 2 | 5 | 2 | 10 | 1240.37 | -76498.11 | FALSE | DEFER
WO-00483 | Overhaul – Instrument/Analyser INST-0026 | INST-0026 | 4 | 4 | 3 |  | FALSE | 3487 | 324232.1 | 93.1 | 48.5 | 46.3 | 23.5 | 211.4 | 26 | 1.8 | 730 | 0.96219 | 730 | 2 | 5 | 2 | 10 | 1385.56 | -322846.54 | FALSE | DEFER
WO-00484 | Cleaning – Control Valve VLV-0067 | VLV-0067 | 2 | 3 | 3 |  | FALSE | 3648 | 11840.45 | 24.4 | 0 | 1.7 | 6 | 32.1 | 4 | 1.5 | 1095 | 0.60745 | 1095 | 2.65 | 5 | 3 | 15 | 3259.71 | -8580.74 | FALSE | DEFER
WO-00485 | Replacement – Pressure Vessel VSL-0011 | VSL-0011 | 6 | 1 | 3 |  | FALSE | 2686 | 47391.66 | 9.6 | 9.6 | 12.2 | 3 | 34.4 | 4 | 2.8 | 3650 | 0.16611 | 2230.4949 | 5 | 3 | 5 | 15 | 36127.93 | -11263.73 | FALSE | DEFER
WO-00486 | Cleaning – Instrument/Analyser INST-0018 | INST-0018 | 2 | 3 | 3 |  | FALSE | 3940 | 8626.51 | 23.9 | 0.2 | 1.2 | 3.3 | 28.6 | 4 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -7186.51 | FALSE | DEFER
WO-00487 | Cleaning – Electrical Equipment ELEC-0036 | ELEC-0036 | 2 | 2 | 2 |  | FALSE | 607 | 16415.14 | 14.3 | 1 | 0.4 | 5.7 | 21.4 | 3 | 2 | 1460 | 0.23691 | 1608.4434 | 2.5 | 3 | 2 | 6 | 2132.17 | -14282.97 | FALSE | DEFER
WO-00488 | Cleaning – Instrument/Analyser INST-0053 | INST-0053 | 2 | 1 | 2 |  | TRUE | 440 | 11435.72 | 22.7 | 0.9 | 0.5 | 4.2 | 28.3 | 4 | 1.8 | 730 | 0.54637 | 720.2559 | 2 | 4 | 2 | 8 | 786.77 | -10648.95 | TRUE | INCLUDE
WO-00489 | Cleaning – Electrical Equipment ELEC-0022 | ELEC-0022 | 2 | 1 | 2 | WO-00157 | FALSE | 937 | 20941.14 | 22.5 | 0.9 | 0.4 | 8.9 | 32.7 | 4 | 2 | 1460 | 0.31845 | 1278.4434 | 2.5 | 3 | 2 | 6 | 2866.08 | -18075.06 | FALSE | DEFER
WO-00490 | Replacement – Centrifugal Pump PMP-0018 | PMP-0018 | 6 | 1 | 3 |  | FALSE | 2749 | 103510.74 | 28.4 | 4.1 | 9.3 | 6.4 | 48.2 | 6 | 2.5 | 1825 | 0.63883 | 1825 | 3 | 5 | 3 | 15 | 13798.72 | -89712.02 | FALSE | DEFER
WO-00491 | Cleaning – Instrument/Analyser INST-0179 | INST-0179 | 2 | 3 | 3 |  | FALSE | 4370 | 11515.89 | 12 | 0.5 | 1.6 | 5.2 | 19.3 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -10075.89 | FALSE | DEFER
WO-00492 | Overhaul – Instrument/Analyser INST-0023 | INST-0023 | 4 | 4 | 3 |  | FALSE | 1050 | 68742.3 | 128.1 | 29.3 | 27.2 | 20.3 | 204.9 | 26 | 1.8 | 730 | 0.74528 | 110.2559 | 2 | 5 | 2 | 10 | 1073.21 | -67669.09 | FALSE | DEFER
WO-00493 | Calibration – Piping/Pipeline Segment PPL-0044 | PPL-0044 | 1 | 3 | 3 |  | FALSE | 2433 | 1831.79 | 1.1 | 7.2 | 8.6 | 0.8 | 17.7 | 2 | 2 | 3285 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | 7813.03 | 5981.24 | TRUE | INCLUDE
WO-00494 | Replacement – Instrument/Analyser INST-0001 | INST-0001 | 6 | 1 | 3 |  | FALSE | 4714 | 108824.09 | 52.1 | 9.6 | 22.2 | 2.1 | 86 | 11 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -107384.09 | FALSE | DEFER
WO-00495 | Replacement – Instrument/Analyser INST-0006 | INST-0006 | 6 | 3 | 3 |  | FALSE | 3489 | 70025.11 | 26.3 | 19 | 9.1 | 3.5 | 57.9 | 7 | 1.8 | 730 | 0.96225 | 730 | 2 | 5 | 2 | 10 | 1385.63 | -68639.48 | FALSE | DEFER
WO-00496 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | 3 | 1 | 3 |  | TRUE | 3570 | 5983.92 | 5 | 2 | 3.8 | 0.1 | 10.9 | 1 | 2.5 | 1825 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | 16656.59 | 10672.67 | TRUE | INCLUDE
WO-00497 | Inspection – Electrical Equipment ELEC-0030 | ELEC-0030 | 3 | 2 | 3 | WO-00445 | FALSE | 2817 | 7649.4 | 7.5 | 0.9 | 1.8 | 0.9 | 11.1 | 1 | 2 | 1460 | 0.642 | 1460 | 2.5 | 5 | 2 | 10 | 5778.01 | -1871.39 | FALSE | DEFER
WO-00498 | Calibration – Instrument/Analyser INST-0145 | INST-0145 | 1 | 4 | 3 |  | FALSE | 4725 | 2337.31 | 0.6 | 6 | 7.6 | 0.4 | 14.6 | 2 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -897.31 | FALSE | DEFER
WO-00499 | Calibration – Electrical Equipment ELEC-0065 | ELEC-0065 | 1 | 2 | 3 |  | FALSE | 3906 | 2570.52 | 1.1 | 3.9 | 15.4 | 0.5 | 20.9 | 3 | 2 | 1460 | 0.75345 | 1460 | 2.5 | 5 | 2 | 10 | 6781.01 | 4210.49 | TRUE | INCLUDE
WO-00500 | Overhaul – Centrifugal Pump PMP-0058 | PMP-0058 | 4 | 1 | 3 |  | TRUE | 4056 | 386381.53 | 187.1 | 18.2 | 44.8 | 11.6 | 261.7 | 33 | 2.5 | 1825 | 0.82968 | 1825 | 3 | 5 | 3 | 15 | 17921.13 | -368460.4 | TRUE | INCLUDE
WO-00501 | Inspection – Reciprocating Compressor CMP-0017 | CMP-0017 | 3 | 3 | 4 |  | FALSE | 4834 | 6550.87 | 4.8 | 1 | 1.9 | 0.7 | 8.4 | 1 | 3 | 1460 | 1 | 1460 | 4.75 | 5 | 5 | 25 | 349125 | 342574.13 | TRUE | INCLUDE
WO-00502 | Replacement – Electrical Equipment ELEC-0074 | ELEC-0074 | 6 | 2 | 2 |  | FALSE | 1760 | 113684.13 | 9.6 | 4.4 | 15.8 | 7.3 | 37.1 | 5 | 2 | 1460 | 0.48585 | 455.4436 | 2.5 | 4 | 2 | 8 | 4372.65 | -109311.48 | FALSE | DEFER
WO-00503 | Cleaning – Centrifugal Pump PMP-0027 | PMP-0027 | 2 | 2 | 3 |  | FALSE | 3787 | 8641.27 | 17.3 | 1.3 | 1.9 | 5.6 | 26.1 | 3 | 2.5 | 1825 | 0.79898 | 1825 | 3 | 5 | 3 | 15 | 17257.88 | 8616.61 | TRUE | INCLUDE
WO-00504 | Cleaning – Instrument/Analyser INST-0024 | INST-0024 | 2 | 2 | 3 | WO-00383 | FALSE | 1785 | 8621.32 | 10.1 | 2 | 0.4 | 8.3 | 20.8 | 3 | 1.8 | 730 | 0.86316 | 730 | 2 | 5 | 2 | 10 | 1242.94 | -7378.38 | FALSE | DEFER
WO-00505 | Calibration – Control Valve VLV-0120 | VLV-0120 | 1 | 3 | 3 | WO-00377 | FALSE | 2323 | 720.04 | 1.9 | 7.5 | 5.4 | 0.7 | 15.5 | 2 | 1.5 | 1095 | 0.53053 | 1095 | 2.65 | 4 | 3 | 12 | 2846.98 | 2126.94 | TRUE | INCLUDE
WO-00506 | Replacement – Piping/Pipeline Segment PPL-0008 | PPL-0008 | 6 | 1 | 3 |  | FALSE | 3475 | 34984.64 | 45.4 | 15.3 | 10.5 | 8.9 | 80.1 | 10 | 2 | 3285 | 0.21919 | 1509.7483 | 3.65 | 3 | 4 | 12 | 10560.48 | -24424.16 | FALSE | DEFER
WO-00507 | Inspection – Electrical Equipment ELEC-0061 | ELEC-0061 | 3 | 2 | 3 | WO-00389 | FALSE | 4139 | 5039.02 | 2.9 | 0.6 | 3 | 0.3 | 6.8 | 1 | 2 | 1460 | 0.77235 | 1460 | 2.5 | 5 | 2 | 10 | 6951.19 | 1912.17 | FALSE | DEFER
WO-00508 | Calibration – Storage Tank TNK-0001 | TNK-0001 | 1 | 3 | 3 |  | FALSE | 5390 | 1731.6 | 1.7 | 6.6 | 11.7 | 0.3 | 20.3 | 3 | 3.5 | 5475 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | 50668.31 | 48936.71 | TRUE | INCLUDE
WO-00509 | Inspection – Control Valve VLV-0048 | VLV-0048 | 3 | 2 | 3 |  | FALSE | 648 | 2392.49 | 8.7 | 1.5 | 3.5 | 0 | 13.7 | 2 | 1.5 | 1095 | 0.35245 | 1261.3751 | 2.65 | 4 | 3 | 12 | 1891.34 | -501.15 | FALSE | DEFER
WO-00510 | Overhaul – Instrument/Analyser INST-0074 | INST-0074 | 4 | 3 | 3 |  | FALSE | 2581 | 451608.27 | 132.8 | 8.7 | 15.7 | 15.8 | 173 | 22 | 1.8 | 730 | 0.92649 | 730 | 2 | 5 | 2 | 10 | 1334.15 | -450274.12 | FALSE | DEFER
WO-00511 | Inspection – Instrument/Analyser INST-0144 | INST-0144 | 3 | 3 | 3 |  | FALSE | 4722 | 920.65 | 4.1 | 0.2 | 3.2 | 0.1 | 7.6 | 1 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | 519.35 | TRUE | INCLUDE
WO-00512 | Calibration – Piping/Pipeline Segment PPL-0025 | PPL-0025 | 1 | 3 | 3 | WO-00338 | FALSE | 2825 | 2917.45 | 1.9 | 4.2 | 4.5 | 0.3 | 10.9 | 1 | 2 | 3285 | 0.18409 | 2159.7481 | 3.65 | 3 | 4 | 12 | 8869.41 | 5951.96 | FALSE | DEFER
WO-00513 | Inspection – Centrifugal Pump PMP-0005 | PMP-0005 | 3 | 2 | 3 |  | FALSE | 4254 | 3261.87 | 4.4 | 0.4 | 3.8 | 0.7 | 9.3 | 1 | 2.5 | 1825 | 0.84976 | 1825 | 3 | 5 | 3 | 15 | 18354.81 | 15092.94 | TRUE | INCLUDE
WO-00514 | Repair – Piping/Pipeline Segment PPL-0031 | PPL-0031 | 5 | 1 | 3 | WO-00217 | FALSE | 4972 | 10044.83 | 21.8 | 14 | 13.8 | 6.3 | 55.9 | 7 | 2 | 3285 | 0.29439 | 12.7481 | 3.65 | 3 | 4 | 12 | 14183.6 | 4138.77 | TRUE | INCLUDE
WO-00515 | Testing – Control Valve VLV-0089 | VLV-0089 | 7 | 4 | 3 |  | FALSE | 3915 | 4923.44 | 8.5 | 16.5 | 22.9 | 1.3 | 49.2 | 6 | 1.5 | 1095 | 0.61983 | 1095 | 2.65 | 5 | 3 | 15 | 3326.16 | -1597.28 | FALSE | DEFER
WO-00516 | Inspection – Centrifugal Pump PMP-0080 | PMP-0080 | 3 | 1 | 3 |  | TRUE | 3570 | 5179.19 | 8.6 | 1 | 2.4 | 1 | 13 | 2 | 2.5 | 1825 | 0.77114 | 1825 | 3 | 5 | 3 | 15 | 16656.59 | 11477.4 | TRUE | INCLUDE
WO-00517 | Overhaul – Instrument/Analyser INST-0091 | INST-0091 | 4 | 4 | 3 |  | FALSE | 2944 | 525923.65 | 220.1 | 49.2 | 45.2 | 5 | 319.5 | 40 | 1.8 | 730 | 0.94394 | 730 | 2 | 5 | 2 | 10 | 1359.27 | -524564.38 | FALSE | DEFER
WO-00518 | Overhaul – Electrical Equipment ELEC-0014 | ELEC-0014 | 4 | 2 | 3 |  | FALSE | 3002 | 396197.22 | 118.9 | 42.2 | 32.2 | 20.9 | 214.2 | 27 | 2 | 1460 | 0.66398 | 1460 | 2.5 | 5 | 2 | 10 | 5975.81 | -390221.41 | FALSE | DEFER
WO-00519 | Inspection – Heat Exchanger HX-0001 | HX-0001 | 3 | 1 | 3 |  | TRUE | 3349 | 3858.79 | 2 | 1.4 | 2.2 | 0.6 | 6.2 | 1 | 2 | 2190 | 0.4158 | 2190 | 4 | 4 | 4 | 16 | 48649.09 | 44790.3 | TRUE | INCLUDE
WO-00520 | Inspection – Centrifugal Pump PMP-0026 | PMP-0026 | 3 | 2 | 3 |  | FALSE | 1524 | 5209.16 | 4.4 | 0.4 | 1.9 | 0.2 | 6.9 | 1 | 2.5 | 1825 | 0.36412 | 1023.705 | 3 | 4 | 3 | 12 | 7865.02 | 2655.86 | TRUE | INCLUDE
WO-00521 | Inspection – Storage Tank TNK-0001 | TNK-0001 | 3 | 4 | 3 |  | FALSE | 5390 | 3284.03 | 7.5 | 1 | 3.4 | 0.3 | 12.2 | 2 | 3.5 | 5475 | 0.21653 | 1558.2321 | 4 | 3 | 4 | 12 | 50668.31 | 47384.28 | TRUE | INCLUDE
WO-00522 | Overhaul – Piping/Pipeline Segment PPL-0004 | PPL-0004 | 4 | 1 | 3 |  | FALSE | 5368 | 182873.9 | 220.9 | 35.5 | 33.8 | 21.7 | 311.9 | 39 | 2 | 3285 | 0.31304 | 3285 | 3.65 | 3 | 4 | 12 | 15082.22 | -167791.68 | FALSE | DEFER
WO-00523 | Repair – Heat Exchanger HX-0018 | HX-0018 | 5 | 1 | 3 |  | FALSE | 2059 | 54873.42 | 41.1 | 10.7 | 3.9 | 9.5 | 65.2 | 8 | 2 | 2190 | 0.28906 | 1264.1654 | 4 | 3 | 4 | 12 | 33820.42 | -21053 | FALSE | DEFER
WO-00524 | Replacement – Storage Tank TNK-0006 | TNK-0006 | 6 | 3 | 3 |  | FALSE | 4911 | 84477.33 | 44.9 | 4.9 | 20.3 | 5.6 | 75.7 | 9 | 3.5 | 5475 | 0.17712 | 2037.2321 | 4 | 3 | 4 | 12 | 41445.54 | -43031.79 | FALSE | DEFER
WO-00525 | Inspection – Storage Tank TNK-0009 | TNK-0009 | 3 | 3 | 3 |  | FALSE | 5278 | 916.94 | 7.1 | 0.3 | 3.1 | 0 | 10.5 | 1 | 3.5 | 5475 | 0.20702 | 1670.2321 | 4 | 3 | 4 | 12 | 48441.95 | 47525.01 | TRUE | INCLUDE
WO-00526 | Repair – Piping/Pipeline Segment PPL-0044 | PPL-0044 | 5 | 3 | 3 |  | FALSE | 2433 | 67432.86 | 96.2 | 27.5 | 10 | 4.6 | 138.3 | 17 | 2 | 3285 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | 7813.03 | -59619.83 | FALSE | DEFER
WO-00527 | Testing – Control Valve VLV-0002 | VLV-0002 | 7 | 3 | 3 |  | FALSE | 5331 | 14606.12 | 15.8 | 8 | 22.9 | 1.9 | 48.6 | 6 | 1.5 | 1095 | 0.67434 | 1095 | 2.65 | 5 | 3 | 15 | 3618.69 | -10987.43 | FALSE | DEFER
WO-00528 | Repair – Instrument/Analyser INST-0068 | INST-0068 | 5 | 2 | 3 |  | FALSE | 5419 | 45771.76 | 94.9 | 6.4 | 17.6 | 1.5 | 120.4 | 15 | 1.8 | 730 | 1 | 730 | 2 | 5 | 2 | 10 | 1440 | -44331.76 | FALSE | DEFER
WO-00529 | Inspection – Piping/Pipeline Segment PPL-0042 | PPL-0042 | 3 | 1 | 3 |  | TRUE | 4121 | 4145.6 | 3.9 | 1.9 | 3.2 | 0.9 | 9.9 | 1 | 2 | 3285 | 0.25257 | 863.7481 | 3.65 | 3 | 4 | 12 | 12169.06 | 8023.46 | TRUE | INCLUDE
WO-00530 | Inspection – Storage Tank TNK-0005 | TNK-0005 | 3 | 2 | 1 |  | FALSE | 2449 | 6339.85 | 7.6 | 1.1 | 4.3 | 0.8 | 13.8 | 2 | 3.5 | 5475 | 0.036789 | 4499.2321 | 4 | 1 | 4 | 4 | 8608.56 | 2268.71 | TRUE | INCLUDE
WO-00531 | Testing – Instrument/Analyser INST-0084 | INST-0084 | 7 | 3 | 3 |  | FALSE | 3682 | 10935.82 | 14.2 | 11.2 | 4 | 0.5 | 29.9 | 4 | 1.8 | 730 | 0.96708 | 730 | 2 | 5 | 2 | 10 | 1392.6 | -9543.22 | FALSE | DEFER
WO-00532 | Calibration – Reciprocating Compressor CMP-0008 | CMP-0008 | 1 | 2 | 4 |  | FALSE | 1979 | 1126.86 | 1.3 | 3.6 | 8.2 | 0.9 | 14 | 2 | 3 | 1460 | 0.80752 | 1460 | 4.75 | 5 | 5 | 25 | 281925.94 | 280799.08 | TRUE | INCLUDE
WO-00533 | Replacement – Centrifugal Pump PMP-0053 | PMP-0053 | 6 | 2 | 3 |  | FALSE | 3211 | 61017.45 | 28.1 | 15.1 | 23.2 | 6.3 | 72.7 | 9 | 2.5 | 1825 | 0.71868 | 1825 | 3 | 5 | 3 | 15 | 15523.41 | -45494.04 | FALSE | DEFER
WO-00534 | Replacement – Control Valve VLV-0029 | VLV-0029 | 6 | 3 | 3 |  | FALSE | 1553 | 69932.56 | 24.6 | 2 | 21.3 | 4.9 | 52.8 | 7 | 1.5 | 1095 | 0.46697 | 356.375 | 2.65 | 4 | 3 | 12 | 2505.88 | -67426.68 | FALSE | DEFER
WO-00535 | Inspection – Centrifugal Pump PMP-0041 | PMP-0041 | 3 | 4 | 3 |  | FALSE | 3780 | 6794.62 | 3.4 | 0.8 | 4.4 | 0.5 | 9.1 | 1 | 2.5 | 1825 | 0.79812 | 1825 | 3 | 5 | 3 | 15 | 17239.43 | 10444.81 | TRUE | INCLUDE
WO-00536 | Replacement – Reciprocating Compressor CMP-0007 | CMP-0007 | 6 | 3 | 4 | WO-00024 | FALSE | 3016 | 87251.78 | 58.9 | 11.9 | 17.8 | 4.5 | 93.1 | 12 | 3 | 1460 | 0.97277 | 1460 | 4.75 | 5 | 5 | 25 | 339618.52 | 252366.74 | TRUE | INCLUDE
WO-00537 | Repair – Centrifugal Pump PMP-0047 | PMP-0047 | 5 | 3 | 3 |  | FALSE | 2596 | 56838.33 | 94.1 | 19.3 | 12.4 | 3.7 | 129.5 | 16 | 2.5 | 1825 | 0.60929 | 1825 | 3 | 5 | 3 | 15 | 13160.57 | -43677.76 | FALSE | DEFER
WO-00538 | Repair – Electrical Equipment ELEC-0002 | ELEC-0002 | 5 | 2 | 3 | WO-00425 | FALSE | 3812 | 52412.67 | 29.4 | 18.1 | 15.6 | 9.5 | 72.6 | 9 | 2 | 1460 | 0.74538 | 1460 | 2.5 | 5 | 2 | 10 | 6708.41 | -45704.26 | FALSE | DEFER
WO-00539 | Inspection – Instrument/Analyser INST-0075 | INST-0075 | 3 | 2 | 3 |  | FALSE | 1134 | 3655.78 | 3 | 2 | 2.7 | 0.5 | 8.2 | 1 | 1.8 | 730 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | 1099.43 | -2556.35 | FALSE | DEFER
WO-00540 | Overhaul – Instrument/Analyser INST-0030 | INST-0030 | 4 | 4 | 3 |  | FALSE | 1985 | 591045.95 | 137.7 | 8.4 | 18.2 | 23.6 | 187.9 | 23 | 1.8 | 730 | 0.88342 | 730 | 2 | 5 | 2 | 10 | 1272.12 | -589773.83 | FALSE | DEFER
WO-00541 | Replacement – Electrical Equipment ELEC-0032 | ELEC-0032 | 6 | 4 | 2 |  | FALSE | 2055 | 75755.37 | 12 | 12.4 | 6.5 | 8.4 | 39.3 | 5 | 2 | 1460 | 0.53526 | 160.4436 | 2.5 | 4 | 2 | 8 | 4817.3 | -70938.07 | FALSE | DEFER
WO-00542 | Inspection – Pressure Vessel VSL-0003 | VSL-0003 | 3 | 4 | 3 |  | FALSE | 2814 | 4024.07 | 2.8 | 0.7 | 1.3 | 0.3 | 5.1 | 1 | 2.8 | 3650 | 0.17838 | 2102.4951 | 5 | 3 | 5 | 15 | 38798.52 | 34774.45 | TRUE | INCLUDE
WO-00543 | Inspection – Control Valve VLV-0119 | VLV-0119 | 3 | 2 | 3 |  | FALSE | 2602 | 6956.37 | 2.6 | 1.1 | 2.8 | 0.9 | 7.4 | 1 | 1.5 | 1095 | 0.5494 | 1095 | 2.65 | 4 | 3 | 12 | 2948.24 | -4008.13 | FALSE | DEFER
WO-00544 | Inspection – Reciprocating Compressor CMP-0014 | CMP-0014 | 3 | 3 | 4 |  | FALSE | 992 | 6140.48 | 7.8 | 1.4 | 1.1 | 0.3 | 10.6 | 1 | 3 | 1460 | 0.38692 | 935.9307 | 4.75 | 4 | 5 | 20 | 135084.24 | 128943.76 | TRUE | INCLUDE
WO-00545 | Cleaning – Pressure Vessel VSL-0025 | VSL-0025 | 2 | 1 | 2 |  | TRUE | 1095 | 15452.68 | 11.1 | 0.5 | 1.9 | 7.8 | 21.3 | 3 | 2.8 | 3650 | 0.04163 | 3821.4951 | 5 | 1 | 5 | 5 | 9054.44 | -6398.24 | TRUE | INCLUDE
WO-00546 | Testing – Heat Exchanger HX-0029 | HX-0029 | 7 | 2 | 3 |  | FALSE | 1541 | 8944.37 | 8 | 11.9 | 18.5 | 0.8 | 39.2 | 5 | 2 | 2190 | 0.23074 | 1782.1654 | 4 | 3 | 4 | 12 | 26996.81 | 18052.44 | TRUE | INCLUDE
WO-00547 | Calibration – Instrument/Analyser INST-0075 | INST-0075 | 1 | 3 | 3 |  | FALSE | 1134 | 747.05 | 1.9 | 4.8 | 10.7 | 0.7 | 18.1 | 2 | 1.8 | 730 | 0.76349 | 26.2559 | 2 | 5 | 2 | 10 | 1099.43 | 352.38 | TRUE | INCLUDE
WO-00548 | Overhaul – Piping/Pipeline Segment PPL-0044 | PPL-0044 | 4 | 2 | 3 |  | FALSE | 2433 | 395099.09 | 220.6 | 41.6 | 42.6 | 9.2 | 314 | 39 | 2 | 3285 | 0.16216 | 2551.7481 | 3.65 | 3 | 4 | 12 | 7813.03 | -387286.06 | FALSE | DEFER
WO-00549 | Cleaning – Instrument/Analyser INST-0040 | INST-0040 | 2 | 2 | 3 |  | FALSE | 2207 | 2060.58 | 22.5 | 0.6 | 0.6 | 4.1 | 27.8 | 3 | 1.8 | 730 | 0.90208 | 730 | 2 | 5 | 2 | 10 | 1299 | -761.58 | FALSE | DEFER
WO-00550 | Replacement – Control Valve VLV-0054 | VLV-0054 | 6 | 1 | 3 |  | FALSE | 4714 | 74554.82 | 38.3 | 6.6 | 8.1 | 8.4 | 61.4 | 8 | 1.5 | 1095 | 0.65259 | 1095 | 2.65 | 5 | 3 | 15 | 3501.98 | -71052.84 | FALSE | DEFER